## Sheet1
PEG | Time lines for gap filling for talent (Action items)
Action item detailed
Elaborate master : Task categories, description
Training plan wrt PEG (team member)
Succession plan --> IDP --> Action Plan
| Digitalization as a scope for PEG | Largest contributor to process improvements, impact to biz objectives)
Last appraisal findings
| Schedule variance target | some releastic should not zero
When mitigation plan and when contigency plan need to make, write in processes as guidelines
PQA | SME (Functional heads) / PEG can do projects audits
Evidences of audit plan concenses in projects
| Audit checklist update | wrt model compliance
Data quality checking during audit
Causal analysis, estimation specially complexity factor in audit checklist
Effective usage of tool (i.e. Einframe) related
P-1 GGE295 | Complexity in efforts estimation
Live dashboard of project metrics
No need to log no defects in incident management
CAR & DAR missing
Opportuinty in Risk management missing
Integration design document missing
P-2 GGS151 | Elaboration required in FS | if not applicable then mention NA or "-"
Source of needs missing in FS
Multiple defects should not log in same entry
Potential defects words use for review functional defects
Risk --> Contigency plan capture missing
CM plan --> Tender doc should controlled type instead o baselined