## Sheet2
| Start | PEG plan making and approval | Requirements capturing, consolidated and analysis. | Discussion on Business goals, define BOTOPO | Implement and revise the QMS | New / Revised QMS Audit | Senior Management Review | QMS Release & Training | Process reviews | Measurement goals data entries monthly | Contract with KPMG for IR, CPR & SCAMPI | Budget, PR & PO related support | MBR present of Q-1 | PEG Audit | IR-1 | Consolidated and analysis of feedback received after IR-1 | After IR-1 : Changes in QMS as per feedbacks. | After IR-1 Audit of Revised QMS
Planned start | 2022-04-01 | 2022-04-01 | 2022-04-07 | 2022-04-19 | 2022-04-25 | 2022-05-06 | 2022-05-09 | 2022-05-10 | 2022-05-13 | 2022-05-13 | 2022-06-16 | 2022-06-16 | 2022-07-06 | 2022-07-08 | 2022-07-23 | 2022-07-26 | 2022-08-03 | 2022-08-12
Planned End | 2022-04-01 | 2022-04-07 | 2022-04-25 | 2022-04-21 | 2022-05-06 | 2022-05-09 | 2022-05-10 | 2022-05-12 |  |  | 2022-06-22 | 2022-06-22 | 2022-07-08 | 2022-07-09 | 2022-07-26 | 2022-08-03 | 2022-08-12 | 2022-08-13
Actual Start | 2022-04-01 | 2022-04-01 | 2022-04-09 | 2022-04-14 | 2022-04-18 | 2022-05-09 | 2022-05-10 | 2022-05-10 | 2022-05-16 | 2022-05-17 | 2022-05-28 | 2022-06-24
Actual End | 2022-04-01 | 2022-04-06 | 2022-04-18 | 2022-04-18 | 2022-05-07 | 2022-05-09 | 2022-05-10 | 2022-05-11 |  |  | 2022-07-15 | 2022-07-11
2022-04-01 | 2022-04-01: 22-22.05; 2022-04-06: 22.05-22.10
2022-04-02
2022-04-03
2022-04-04 | 2022-04-06: 14-17.30
2022-04-05
2022-04-06 | 2022-04-06: 17.45-18.15
2022-04-07
2022-04-08
2022-04-09 | 2022-04-18: 11-13.00
2022-04-10
2022-04-11 | 2022-04-18: 17-18
2022-04-12 | 2022-04-18: 9.30-10.30 14-17.30
2022-04-13 | 2022-04-18: 11.30-13.30
2022-04-14 | 2022-04-18: 9.30-13.00 15.30-17.30; 2022-04-18: 14-15 (discussed on business KPI and explore the viability)
2022-04-15
2022-04-16
2022-04-17
2022-04-18 | 2022-04-18: 11-13.00 (Consolidated sheet completed); 2022-04-18: 10.00-11.00 (Finalized the business KPIs); 2022-05-07: 13.0-13.30 (Worked on Project management procedures, measurement procedure, measurement report template)
2022-04-19
2022-04-20 | 2022-05-07: 16.0-18.0 (worked on configuration management procedure, worked on measurement procedure, Audit procedure)
2022-04-21 | 2022-05-07: 9.30-13.20 (Talent maps, Assest maps, metrics and process maps in einfrmae. Configuration management procedures completed.)
2022-04-22
2022-04-23 | 2022-05-07: 16.0-17.30
2022-04-24
2022-04-25 | 2022-05-07: 11.0-13.15
2022-04-26
2022-04-27
2022-04-28
2022-04-29 | 2022-05-07: 14.0-16.0
2022-04-30 | 2022-05-07: 15.0-17.0
2022-05-01
2022-05-02
2022-05-03
2022-05-04
2022-05-05
2022-05-06 | 2022-05-07: 14.0-17.30
2022-05-07 | 2022-05-07: 16.45-18.00 (Reviewed all changes and completed implementation.)
2022-05-08
2022-05-09 | 2022-05-09: 10.0-13.15 14.0-15.00; 2022-05-10: 15.30-16.0
2022-05-10 | 2022-05-11: 10.15-12.45 14.10-15.0
2022-05-11 | 2022-05-11: 9.45-11.0 11.30-12.0 14.30-16.15
2022-05-12
2022-05-13
2022-05-14
2022-05-15
2022-05-16 | [8 empty] | 11.0-13.15
2022-05-17 | [9 empty] | 11.30-12.15
2022-05-18
2022-05-19
2022-05-20
2022-05-21
2022-05-22
2022-05-23 | [8 empty] | 11.0-13.0
2022-05-24
2022-05-25
2022-05-26
2022-05-27
2022-05-28 | [10 empty] | 10.00-11.00
2022-05-29
2022-05-30
2022-05-31
2022-06-01
2022-06-02
2022-06-03
2022-06-04 | [9 empty] | 15.45-15.50
2022-06-05
2022-06-06 | [8 empty] | 11-13.00 |  | 14.00-15.00
2022-06-07
2022-06-08
2022-06-09
2022-06-10
2022-06-11
2022-06-12
2022-06-13
2022-06-14
2022-06-15
2022-06-16
2022-06-17
2022-06-18
2022-06-19
2022-06-20
2022-06-21
2022-06-22
2022-06-23
2022-06-24 | [11 empty] | 16.00-16.25
2022-06-25
2022-06-26
2022-06-27 | [8 empty] | 11.10-11.25
2022-06-28
2022-06-29
2022-06-30
2022-07-01
2022-07-02 | [12 empty] | 16.30-17.30 18.0-18.15
2022-07-03
2022-07-04
2022-07-05
2022-07-06
2022-07-07
2022-07-08
2022-07-09
2022-07-10
2022-07-11 | [11 empty] | 10.00-10.25
2022-07-12
2022-07-13 | [10 empty] | 11.00-12.15
2022-07-14
2022-07-15 | [10 empty] | 9.00-9.25
2022-07-16
2022-07-17
2022-07-18
2022-07-19
2022-07-20