## MPM
MPM
Level | Practice | Title | Source Reference | Link | Description | Type(Doc/ Aff) | S/W/I Description | S/W/I | Verified- Y/N | GNS011 | ORG |  | CHAR - GNS011-FI/LI | CHAR - ORG-FI/LI | CHAR -
Level 1 | 1.1 | Collect measures and record performance. | OK | GNS011_PRJPLN_12.5 | Identify the measures and collection methods in this section of project plan. | Doc | S: | S | Y | X |  | X | FM | FM
|  |  | OK | GNS011_MESRPT | Measurement report where collect and record measures to understand the performance. | Doc |  | - | N | X |  | X
|  |  | OK | ORG_MBR1019 | MBR for quarter jul-oct | Doc | I: Values of primary measures such as person hours, no of defects or NCs etc should be maintained as an annexure for traceability and verification. | I |  |  | X | X
|  |  | - |  | PM affirms that measures and collection methods were identified. | Aff |  | -
|  |  | - |  | PEG affirms that MBR is created. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 1.2 | Identify and address performance issues. | OK | GNS011_MESRPT | Measurement report where performace review and causal analysis and correction actions did. | Doc | S: | S |  | X |  | X | FM | FM
|  |  | OK | GNS011_MLSRVW | Milestone review checklist to discuss about measured perfromace and their issues. | Doc |  | S |  | X |  | X
|  |  | OK | ORG_MBR1019 | MBR for quarter jul-oct | Doc | S: | S |  |  | X | X
|  |  | - |  | PM affirms that performance issues were identified and addressed in measurement report. | Aff |  | -
|  |  | - |  | PEG affirms that MBR is created. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | S
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 2 | 2.1 | Derive and record measurement and performance objectives from selected business needs and objectives and keep them updated. | OK | GNS011_PRJPLN_12.5 | Identify the one project specific measurement "BOM Cost" as project specific business need is competitive price solution for export market. | Doc | W: BOM cost does not appear to be an appropriate project objective considering low volumes and 150% markup | W |  | X |  | X | LM | LM
|  |  | OK | GNS011_PRJPLN_12.5 | The organisation defined measurements have been inherited in the project with the operational definitions as defined in the QMS | Doc |  | - |  | X |  | X
|  |  | OK | ORG_BOTOPO | Business objective to process objective mapped. | Doc | I: Many to many relationships with respect to inetractions of objectives should be captured. | I |  |  | X | X
|  |  | - |  | PM affirms that BOM Cost is selected as measurement objective on the direction of SM due to business need. | Aff |  | -
|  |  | - |  | PEG affirms that business objectives are communicated to them and they maintain a business objective to process objective mapping. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.2 | Develop, keep updated, and use operational definitions for measures. | OK | GNS011_PRJPLN_12.5 | Section showing tools required which has reference of organisation definition and procedures of measurement. | Doc | I: Reporting of metrics data should be planned as a part of measurement planning. | I |  | X |  | X | FM | FM
|  |  | OK | GNS011_PRJPLN_12.5 | BOM cost related custom measurement has been defined as "This goal is selected based on competitor’s same product whose selling price is 6 lakh. We considered BOM cost of such type of products 30KVa and above is 40% of selling price. As per this calculation, reference BOM Cost can be taken as 2.4 Lakh. Formulae for BOM cost variance are as below. (Product’s BOM cost-2.4L)*100/2.4L" | Doc | I: Reporting of metrics data should be planned as a part of measurement planning. | I |  | X |  | X
|  |  | OK | ORG_PRCD_MEASUR | Measurement procedure where operation definitions mentioned of each measures related to business needs. | Doc | S: | S |  |  | X | X
|  |  | OK | ORG_MESURE | Measurement tool where the data comes according to definition of that particular mesure. | Doc |  | - |  |  | X | X
|  |  | - |  | PM affirms that operational definitions for BOM cost is maintained in the project plan. | Aff | I: Selection of appropriate measures based on projects objectives should be made. | I
|  |  | - |  | PEG affirms that measurement tool was created to automate data collection and analysis. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.3 | Obtain specified measurement data according to the operational definitions. | OK | GNS011_MESURE | Tool used to obtain mesurement data and verify the completeness. | Doc | S: High degree of automation in obtaining measurement data. | S |  | X |  | X | FM | FM
|  |  | OK | ORG_MESURE | Measurement tool where the data comes according to definition of that particular mesure. | Doc | S: | S |  |  | X | X
|  |  | - |  | PM affirms that Tool used to obtain mesurement data and verify the completeness. | Aff |  | -
|  |  | - |  | PEG affirms that measurement tool was used for data collection and analysis. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.4 | Analyze performance and measurement data according to the operational definitions. | OK | GNS011_MESRPT | Measurement report where performace review and causal analysis and correction actions did. | Doc | I: Effectiveness and specificity of causal analysis need to be improved. | I |  | X |  | X | FM | FM
|  |  | OK | ORG_MESURE | Measurement tool where the data comes according to definition of that particular mesure. | Doc |  | - |  |  | X | X
|  |  | OK | ORG_MBR1019 | MBR for quarter jul-oct : Causal analysis | Doc | I:Interaction of metrices should be analysed. | I |  |  | X | X
|  |  | - |  | PM affirms that metrics report is created and shared with the SM. | Aff |  | -
|  |  | - |  | PEG affirms that causal analysis of metrics is done in the MBR. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.5 | Store measurement data, measurement specifications, and analysis results according to the operational definitions. | OK | GNS011_MESRPT | Measurement report where graphs and analysis stored. | Doc | I: The measurement should be stored such that they can be readily queried, sliced and diced for future use. | I |  | X |  | X | FM | FM
|  |  | OK | GNS011_MESURE | Measurement data stored here also. | Doc |  | - |  | X |  | X
|  |  | OK | ORG_Measurement Repository | Measurement Repository use to store MBRs | Doc |  | - |  |  | X | X
|  |  | OK | ORG_Logs | Measurement data like timesheets, review and testing defects and audit NCs stored in logs. | Doc | I: The measurement should be stored such that they can be readily queried, sliced and diced for future use. | I |  |  | X | X
|  |  | - |  | PM affirms that metrics report is stored in the project repository on Sharepoint. | Aff |  | -
|  |  | - |  | PEG affirms that MBR is stored in the measurement repository on Sharepoint. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.6 | Take actions to address identified issues with meeting measurement and performance objectives. | OK | GNS011_MESRPT | Phase wise corrective actions accordingly to causal analysis of performace issue. | Doc | I: Effectiveness and specificity of causal analysis need to be improved. | I |  | X |  | X | FM | FM
|  |  | OK | GNS011_MPP | One corrective action was that to compensate schedule variance some activities do parallel of integration phase like system test case preparation, this showing in MPP (date wise) | Doc |  | - |  | X |  | X
|  |  | OK | ORG_MBR1019 | Corrective actions | Doc | S: | S |  |  | X | X
|  |  | OK | ORG_PEGPLN | Action plan | Doc |  | - |  |  | X | X
|  |  | - |  | PM affirms that Causal analysis is done for the metrics that are close to or beyond goal limits. | Aff |  | -
|  |  | - |  | PEG affirms that Causal analysis is done for the metrics that are close to or beyond goal limits. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 3 | 3.1 | Develop, keep updated, and use organizational measurement and performance objectives traceable to business objectives. | OK | GNS011_PRJPLN_12.5 | Identify the one project specific measurement "BOM Cost" as project specific business need is competitive price solution for export market. | Doc | W: BOM cost does not appear to be an appropriate project objective considering low volumes and 150% markup | W |  | X |  | X | LM | LM
|  |  | OK | GNS011_PRJPLN_12.5 | The organisation defined measurements have been inherited in the project with the operational definitions as defined in the QMS | Doc |  | - |  | X |  | X
|  |  | OK | ORG_BOTOPO | Business objective to process objective mapped. | Doc | I:Interaction of metrices should be analysed. | I |  |  | X | X
|  |  | - |  | PM affirms that BOM cost is used as project specific measurement which is linked to business objective. | Aff |  | -
|  |  | - |  | PEG affirms that organizational measurement and performance objectives are traceable to business objectives. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.2 | Follow organizational processes and standards to develop and use operational definitions for measures and keep them updated. | OK | GNS011_PRJPLN_12.5 | Section showing tools required which has reference of organisation definition and procedures of measurement. | Doc | S: | S |  | X |  | X | FM | FM
|  |  | OK | GNS011_PRJPLN_12.5 | BOM cost related custom measurement has been defined as "This goal is selected based on competitor’s same product whose selling price is 6 lakh. We considered BOM cost of such type of products 30KVa and above is 40% of selling price. As per this calculation, reference BOM Cost can be taken as 2.4 Lakh. Formulae for BOM cost variance are as below. (Product’s BOM cost-2.4L)*100/2.4L" | Doc |  | - |  | X |  | X
|  |  | OK | ORG_PRCD_MEASUR | Measurement procedure where operation definitions mentioned of each measures related to business needs. | Doc | S: | S |  |  | X | X
|  |  | OK | ORG_MESURE | Measurement tool where the data comes according to definition of that particular mesure. | Doc | S: High degree of automation in obtaining measurement data. | S |  |  | X | X
|  |  | - |  | PM affirms that measurement tool was used to collect , validate and analyse project data. | Aff |  | -
|  |  | - |  | PEG affirms that measurement procedure details the definitions of measures. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.3 | Develop, keep updated, and follow a data quality process. | OK | GNS011_MESURE | Measurement data collected by tool, and data validated through checks built in on the dashboard of the tool.. | Doc | I:Data quality process should also address deliberate mis-recording of data in addition to automatic checks of validity. | I |  | X |  | X | FM | FM
|  |  | OK | GNS011_AUDITT | Audit checklist as measurement data and metrics report audit did. | Doc |  | - |  | X |  | X
|  |  | OK | ORG_MESURE | Measurement tool where the data quality check at introduction sheet. | Doc | I:Data quality process should also address deliberate mis-recording of data in addition to automatic checks of validity. | I |  |  | X | X
|  |  | - |  | PM affirms that measurement tool was used to collect , validate and analyse project data. | Aff |  | -
|  |  | - |  | PEG affirms that that measurement toool is creaed to collect,validate and analyse project data. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.4 | Develop, keep updated, and use the organization’s measurement repository. | OK | GNS011_PRJPLN_12.5 | The organisation defined measurements have been inherited in the project with the operational definitions as defined in the QMS | Doc | I: The measurement should be stored such that they can be readily queried, sliced and diced for future use. | I |  | X |  | X | FM | FM
|  |  | OK | GNS011_ESTHDW_LFC Distribution | The LFC distribution which has been defined by organisation is used in the project. | Doc |  | - |  | X |  | X
|  |  | OK | ORG_Measurement Repository | Measurement Repository use to store MBRs | Doc | I: The measurement should be stored such that they can be readily queried, sliced and diced for future use. | I |  |  | X | X
|  |  | OK | ORG_Logs | Measurement data like timesheets, review and testing defects and audit NCs stored in logs. | Doc |  | - |  |  | X | X
|  |  | - |  | PM affirms that measurement tool was used to collect , validate and analyse project data. | Aff |  | -
|  |  | - |  | PEG affirms that that MBR is stored in measurement repository at Sharepoint. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.5 | Analyze organizational performance using measurement and performance data to determine performance improvement needs. | OK | GNS011_MESRPT | Phase wise corrective actions accordingly to causal analysis and corrective action of performace issue. | Doc | S: | S |  | X |  | X | FM | FM
|  |  | OK | GNS011_MLSRVW | Milestone review checklist to discuss about measured perfromace and their issues. | Doc |  | - |  | X |  | X
|  |  | OK | ORG_MBR1019 | MBR for quarter jul-oct : Causal analysis | Doc | S: | S |  |  | X | X
|  |  | - |  | PM affirms that Phase wise corrective actions according to causal analysis and corrective action of performace issue is taken. | Aff |  | -
|  |  | - |  | PEG affirms that Milestone reviews and MBR are discussed with SM to analyze org performance. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | S
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.6 | Periodically communicate performance results to the organization. | OK | GNS011_Metrics Report Mail to SM | Metrics report presented to Senior management | Doc | S: | S |  | X |  | X | FM | FM
|  |  | OK | GNS011_Metric Report Mail to PEG | Metrics report submitted to PEG after each phase. | Doc |  | - |  | X |  | X
|  |  | OK | ORG_PEGMOM | MBR Review by senior management. (C-137) | Doc | S: | S |  |  | X | X
|  |  | - |  | PM affirms that metrics report I sent to the PEG and SM after each phase. | Aff |  | -
|  |  | - |  | PEG affirms that Milestone reviews and MBR are discussed with SM to analyze org performance. | Aff |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
** Minimum 2 and maximum 3 evidences require for each practice