## Sheet1
Id | Identification Date | Description | Reproduction Steps | Configuration Info | Logged On | Resolved On | Ageing | Status | Type | Assignor | Assignee | Report Type | Product KPI Affected | Source | Task Category | Found In | Fixed In | Classification | Resolution Type | Effort Spent | Material Cost | Schedule Impact
26 | Apr 01, 2022 | Because of unavailability of proper inductive load, charger and proper cells/battery pack, testing for the voltage spikes on the MOSFETs are not done. Need the higher management to make arrangements for the same so that proper testing can be done. | None available with us. | The test is not conducted, as there is unavailability of the resources. | Apr 01, 2022 | Jan 04, 2022 | - | Closed | Project RelatedBMS DEVELOPMENT AND TESTING | Abhishek Kumar | Tarun Gupta | New Feature | Reliability | New Implementation | Project Management | 2022-08-09 - During reliability testing of product. | 2022-08-09 - During reliability testing of product. | Functional | Will Fix in Future | 0 | 0 | 0
27 | May 09, 2022 | If risk rpn changes, history of previous rpn scores looses. | point no. 10 & 11 of procedure | QMS 4.0, PRCD_RSKMGM | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | New Implementation | Testing | 2022-05-09 - QMS_4.0 : PRCD_RSKMGM | 2022-05-09 - QMS_4.0 : PRCD_RSKMGM | Functional | Fixed |  | 0 | 0
28 | May 09, 2022 | when risk rpn is in "serious", then also to inform senior management. | point no. 8 of procedure | QMS 4.0, PRCD_RSKMGM | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | New Implementation | Testing | 2022-05-09 - QMS_4.0 : PRCD_RSKMGM | 2022-05-09 - QMS_4.0 : PRCD_RSKMGM | Non Functional | Fixed |  | 0 | 0
29 | May 09, 2022 | RPN table snapshot figures should match with Einframe definition, | page no. 8, guidelines | QMS 4.0, PRCD_RSKMGM | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | New Implementation | Testing | 2022-05-09 - QMS_4.0 : PRCD_RSKMGM | 2022-05-09 - QMS_4.0 : PRCD_RSKMGM | Observation | Fixed |  | 0 | 0
30 | May 09, 2022 | reference of old tools still remains in checklist of Audit (for project) | RD phase, point no. 6,9,11 | QMS, CHKL_AUDITT | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | Regression in untouched module | Testing | 2022-05-09 - QMS_4.0 : CHKL_AUDITT_Rev.4 | 2022-05-09 - QMS_4.0 : CHKL_AUDITT_Rev.5 | Non Functional | Fixed | 1 | 0 | 0
31 | May 09, 2022 | typographical corrections are suggested, blank extra rows to be deleted from time sheet bold | point no. 6, 18 in training, point no. 9 in measurement, point no. 2.4 in metrics report, point no. 1 in project monitoring and control | PRCD_TRAING, PRCD_MEASUR, TMPL_MESRPT, PRCD_PRJMAC | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | Modified Implementation | Testing | 2022-05-09 - QMS_4.0 : PRCD_TRAING, PRCD_MEASUR & PRCD_PRJMAC & TMPL_MESRPT | 2022-05-09 - QMS_4.0 : PRCD_TRAING, PRCD_MEASUR & PRCD_PRJMAC & TMPL_MESRPT | Observation | Fixed | 0 | 0 | 0
32 | May 09, 2022 | checklist for IT audit to move in AUDITT folder | audit checklist for IT | CHKL_ITAUDT | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | Regression in untouched module | Testing | 2022-05-09 - QMS_4.0 : IT audit checklist | 2022-05-09 - QMS_4.0 : IT audit checklist | Non Functional | Fixed | 0 | 0 | 0
33 | May 09, 2022 | old tools references are still available in some documents | configuration items name, point no. 27 | MSTL_CMLIST, PRCD_CONFIG | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | Regression in untouched module | Testing | 2022-05-09 - QMS_4.0 : PRCD_CONFIG & MSTL_CMLIST | 2022-05-09 - QMS_4.0 : PRCD_CONFIG & MSTL_CMLIST | Observation | Fixed | 1 | 0 | 0
34 | May 09, 2022 | Project review frequency table to move in procedure for project monitoring and control | page no. 10, of procedure | PRCD_PRJPLN | May 09, 2022 | May 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Assembly (Integration) | Modified Implementation | Testing | 2022-05-09 - QMS_4.0 : PRCD_PRJMAC | 2022-05-09 - QMS_4.0 : PRCD_PRJMAC | Observation | Fixed | 0 | 0 | 0
35 | Jul 02, 2022 | 1. THD, Crest Factor : 3:1, peak Efficiency not Elaboration 2. Easy to Service and Manufacturability need does not measurable. please Elaborate it. | 1. THD, Crest Factor : 3:1, peak Efficiency not Elaboration 2. Easy to Service and Manufacturability need does not measurable. please Elaborate it. | GGS151_FUNSPC | Jul 22, 2022 | Jul 22, 2022 | - | Closed | Project RelatedGGS151 | Umesh Likhitkar | Chandrashekhar Sharma | BUG | Protections | Regression in untouched module | Testing | 2022-07-22 - FS for 3KW MPPT Off grid PCU. | 2022-07-22 - New rev of FS for 3KW MPPT Off grid PCU. | Observation | Fixed |  | 0 | 0
36 | Jul 22, 2022 | For new segment project effort estimation template need to more align . | During effort estimation of project GGE295 - | QMS_4.0 | Jul 23, 2022 | Sep 09, 2022 | - | Closed | Project Related- | Sobhag Prajapat | Jalaj Mathur | BUG | Documentation | Modified Implementation | Project Management | 2022-09-12 - QMS_4.0 --> TMPL_ESTFNL (Version 7) | 2022-09-12 - QMS_4.1 --> TMPL_ESTFNL (Version 8) | Functional | Fixed |  | 0 | 0
37 | Jul 25, 2022 | Working folder is not available at project defined storage location (SVN), but on a local computer, | project folder is lying on local computer | project folder is lying on local computer | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-07-29 - http://192.168.100.9:8080/svn/DC_DC_Converter/SP9_GGE295 | 2022-07-29 - http://192.168.100.9:8080/svn/DC_DC_Converter/SP9_GGE295 | Functional | Fixed | 0 | 0 | 0
38 | Jul 25, 2022 | document name does not contain project name, also project name is missed in a few documents | TMPL_FUNSPC, TMPL_REQVAL, ESFNL, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - All document rename with GGE295 DC-DC Converter 12V-10A & 5V-1A | 2022-07-27 - GGE295 DC-DC Converter 12V-10A & 5V-1A | Non Functional | Fixed | 0 | 0 | 0
39 | Jul 25, 2022 | Period meeting for project review can not be seen, also MOM pattern is required in details, no mom could find after kick off meeting, no action item is noted down, | MOM meeting details, action items details | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | 3rd Party Component | Project Management | 2022-07-27 - GGE295_MINMET for project DC-DC converter | 2022-07-27 - GGE295_MINMET for project DC-DC converter | Functional | Fixed | 6 | 0
40 | Jul 25, 2022 | Review defect/no-defect log is not seen, review time sheet is not in sync., | incident log is not seen | rev.00 | Jul 26, 2022 | Aug 01, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | 3rd Party Component | Project Management | 2022-08-06 - GGE295 DC-DC Converter 12V-10A & 5V-1A task -Audit2022-07-27 - review check list and review time sheet of project GGE295 | 2022-08-06 - GGE295 DC-DC Converter 12V-10A & 5V-1A task -Audit NC resolve2022-07-27 - review check list and review time sheet of project GGE295 | Non Functional | Will Fix in Future | 3 | 0 | 4
41 | Jul 25, 2022 | Related requirements are not clearly mentioned RTT, signs are not clearly mentioned, RTT review can not seen in plan, | related requirement IDs in RTT, Project tasks in plan, incident management | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - GGE295_REQRTT format in project GGE295 | 2022-07-27 - GGE295_REQRTT format in project GGE295 | Non Functional | Fixed | 0 | 0 | 0
42 | Jul 25, 2022 | FS is not baselined and communicated to the team, Customer approval on FS is not seen, external interface need to review again, | FUNSPC, project tasks | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - FS review on GGE295 DC-DC Converter 12V-10A & 5V-1A | 2022-07-27 - FS review on GGE295 DC-DC Converter 12V-10A & 5V-1A | Non Functional | Fixed | 0 | 0 | 0
43 | Jul 25, 2022 | efforts for many phases is not available, No risk is identified, planning phase is not completed, metrics reports are not prepared. | ESTFNL_ Risk plan in project plan, MESRPT, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - GGE295_ESTFNL for GGE295 DC-DC Converter 12V-10A & 5V-1A | 2022-07-27 - GGE295_ESTFNL for GGE295 DC-DC Converter 12V-10A & 5V-1A | Functional | Fixed | 0 | 0 | 0
44 | Jul 25, 2022 | few typographic errors are observed in documents, | Functional specifications, RTT | REV.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - all document of GGE295 DC-DC Converter 12V-10A & 5V-1A | 2022-07-27 - all document of GGE295 DC-DC Converter 12V-10A & 5V-1A | Observation | Fixed | 0 | 0 | 0
45 | Jul 25, 2022 | Working folder is not available at project defined storage location (SVN), but on a local computer, | project folder is lying on local computer | project folder is lying on local computer | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-07-29 - http://192.168.100.9:8080/svn/BMS/BMS_20S_40A | 2022-07-29 - http://192.168.100.9:8080/svn/BMS/BMS_20S_40A | Functional | Fixed | 0 | 0 | 0
46 | Jul 25, 2022 | document name does not contain project name, also project name is missed in a few documents | TMPL_FUNSPC, TMPL_REQVAL, ESFNL, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | 2022-07-27 - All documents rename with GEE300 BMS 20S40A NMC 72V | 2022-07-27 - All documents rename with GEE300 BMS 20S40A NMC 72V | Non Functional | Fixed | 0 | 0 | 0
47 | Jul 25, 2022 | Period meeting for project review can not be seen, also MOM pattern is required in details, no mom could find after kick off meeting, no action item is noted down, | MOM meeting details, action items details | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | 2022-07-27 - GGE300_MINMET FOT PROJECT BMS 20S 40A NMC 72V | 2022-07-27 - GGE300_MINMET FOT PROJECT BMS 20S 40A NMC 72V | Functional | Fixed | 6 | 0
48 | Jul 25, 2022 | Review defect/no-defect log is not seen, review time sheet is not in sync., | incident log is not seen | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - Review check list and review time sheet of project GGE300 | 2022-07-27 - Review check list and review time sheet of project GGE300 | Non Functional | Will Fix in Future | 0 | 0 | 0
49 | Jul 25, 2022 | Related requirements are not clearly mentioned RTT, signs are not clearly mentioned, RTT review can not seen in plan, | related requirement IDs in RTT, Project tasks in plan, incident management | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | 2022-07-27 - Related task linked each other GEE300 BMS 20S 40A NMC 72V | 2022-07-27 - Related task linked each other GEE300 BMS 20S 40A NMC 72V | Non Functional | Fixed | 0 | 0 | 0
50 | Jul 25, 2022 | FS is not baselined and communicated to the team, Customer approval on FS is not seen, external interface need to review again, | FUNSPC, project tasks | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - FS review on GEE300 BMS 20S 40A NMC 72V. | 2022-07-27 - FS review on GEE300 BMS 20S 40A NMC 72V. | Non Functional | Fixed | 0 | 0 | 0
51 | Jul 25, 2022 | efforts for many phases is not available, No risk is identified, planning phase is not completed, metrics reports are not prepared. | ESTFNL_ Risk plan in project plan, MESRPT, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-07-27 - GGE300_ESTFNL for BMS 20S 40A NMC 72V | 2022-07-27 - GGE300_ESTFNL for BMS 20S 40A NMC 72V | Non Functional | Fixed | 0 | 0 | 0
52 | Jul 25, 2022 | few typographic errors are observed in documents, | Functional specifications, RTT | REV.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | 2022-07-27 - All documents of GEE300 BMS 20S 40A NMC 72V | 2022-07-27 - All documents of GEE300 BMS 20S 40A NMC 72V | Observation | Fixed | 0 | 0 | 0
53 | Jul 25, 2022 | project measurement goals are not found. | refer to project plan detail | REV.00 | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-07-29 - Project GGE295 DC-DC Converter 12V-10A & 5V-1A RD Phase | 2022-07-29 - Project GGE295 DC-DC Converter 12V-10A & 5V-1A RD Phase | Functional | Fixed | 0 | 0 | 0
54 | Jul 25, 2022 | project measurement goals are not found. | refer to project plan detail | REV.00 | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-07-29 - Project GEE300_20S 40A NMC 72V in RD phase | 2022-07-29 - Project GEE300_20S 40A NMC 72V in RD phas | Functional | Fixed | 0 | 0 | 0
55 | Jul 25, 2022 | Audit repitition in a phase | before and after Metrics report audit is time consuming for team, pls change to to once after metrics report preparation only. | PRCD_PRJPLN | Jul 26, 2022 | Sep 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Documentation | Regression in untouched module | Systems Engineering | 2022-09-12 - QMS 4.0 --> PRCD_PRJPLN | 2022-09-12 - QMS 4.1 --> PRCD_PRJPLN | Functional | Fixed | 0 | 0 | 0
56 | Jul 25, 2022 | Audit checklist to be sync with GIL.ef | Category of NC is to be sync with term functional/non-functional | CHKL_AUDITT | Jul 26, 2022 | Sep 09, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Documentation | Modified Implementation | Systems Engineering | 2022-09-12 - QMS 4.0 --> CHKL_AUDITT ((Ver.5), CHKL_ADTPEG (Ver.1), CHKL_ADTTRN (Ver.2), CHKL_ITAUDT (Ver.3) | 2022-09-12 - QMS 4.0 --> CHKL_AUDITT ((Ver.6), CHKL_ADTPEG (Ver.2), CHKL_ADTTRN (Ver.3), CHKL_ITAUDT (Ver.4) | Functional | Fixed | 2 | 0 | 0
57 | Jul 27, 2022 | Project plan is missing talent need, asset, knowledge, risk details, link to project data, review project financials | project plan requirements | PEG Plan | Jul 28, 2022 | Jul 29, 2022 | - | Closed | Project Related- | Shweta Aggarwal | Jalaj Mathur | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-07-29 - PEG_Plan_2022-23 version 0 | 2022-07-29 - PEG_Plan_2022-23 Version 1 | Functional | Fixed | 1 | 0 | 0
58 | Jul 27, 2022 | PEG activities after december'22 can not seen in project plan | project tasks are missing for Q4 | PEG plan | Jul 28, 2022 | Jul 30, 2022 | - | Closed | Project RelatedPEG_Plan_2022-23 | Shweta Aggarwal | Jalaj Mathur | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-07-30 - PEG_PLAN_2022-23 Version 0 | 2022-07-30 - PEG_PLAN_2022-23 Version 1 | Non Functional | Will Fix in Future | 0 | 0 | 0
59 | Jul 27, 2022 | SCAMPI words is not appropriate, task name to be appropriate, task category should be appropriate, duration process review task duration is not appropriate. | project task contains "SCAMPI', CPR is CPR execution, project task to be appropriate, project review task is shortly mentioned in task. | PEG plan | Jul 28, 2022 | Jul 30, 2022 | - | Closed | Project RelatedPEG_Plan_2022-23 | Shweta Aggarwal | Jalaj Mathur | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-07-30 - PEG_PLAN_2022-23 Version 0 | 2022-07-30 - PEG_PLAN_2022-23 Version 1 | Observation | Fixed | 1 | 0 | 0
60 | Aug 03, 2022 | Measurement goals Defect Density tolerance mentioned in percentage, it should be same as number. | During review of Project plan in einframe : Section "Description" | Project Plan GGS151 (Aug 03, 2022 03:59:55 (UTC)) | Aug 03, 2022 | Aug 03, 2022 | - | Closed | Project RelatedGGS151 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-08-03 - Aug 03, 2022 08:43:37 (UTC) | 2022-08-03 - Aug 03, 2022 11:09:10 (UTC) | Functional | Fixed | 0 | 0 | 0
61 | Aug 03, 2022 | Some members resource loading showing more than 120% in this particular project for dates 23-25 Aug.22 | During Project plan review : Project Team--> Resource Loading | Project Plan GGS151 (Aug 03, 2022 03:59:55 (UTC)) | Aug 03, 2022 | Aug 03, 2022 | - | Closed | Project RelatedGGS151 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-08-03 - Aug 03, 2022 03:59:55 (UTC) | 2022-08-03 - Aug 03, 2022 11:09:10 (UTC) | Non Functional | Will Fix in Future | 0 | 0 | 0
62 | Aug 03, 2022 | Resource loading show above 120% of two members at some dates in project ,while actual resource loading is less then 120%. | Found during plan review verify resource loading . | Ein Frame | Aug 03, 2022 | Sep 09, 2022 | - | Closed | Project RelatedGGS151 | Chandrashekhar Sharma | Jalaj Mathur | BUG | Reliability | 3rd Party Component | Systems Engineering | 2022-09-12 - Einframe --> Resource loading | 2022-09-12 - Einframe --> Resource loading | Functional | Fixed | 0 | 0 | 0
63 | Aug 04, 2022 | Plan review checklist is not found on defined path | open project data link- no plan review checklist is found. | SVN server/GGS151 | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-08-05 - http://10.141.1.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | 2022-08-05 - GGS151_PLNREV at http://10.141.1.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | Non Functional | Fixed | 0 | 0 | 0
64 | Aug 04, 2022 | MOM_preliminary efforts are not discussed in meeting, decision/action items not mentioned in last MOM, few grammatical errors | MIMMET, last MOM decision/action items column | MINMET | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-08-05 - SVN Log History (Found in revision wrong fill)2022-08-05 - GGS151_MINMET Revision 17 | 2022-08-05 - Found In :GGS151_MINMET Revision 162022-08-05 - GGS151_MINMET Revision 18 | Non Functional | Fixed | 0 | 0 | 0
65 | Aug 04, 2022 | FS baselined not communicated, RTT review not done | Finalized FS communication missing, RTT review is not seen | RTT review | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Regression in untouched module | Project Management | 2022-08-05 - Incident Management log | 2022-08-05 - Incident Management log in further | Non Functional | Will Fix in Future | 0 | 0 | 0
66 | Aug 04, 2022 | No action against asset requirement could seen | asset/ Microsoft office/no action plan | asset plan in project plan | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | 3rd Party Component | Project Management | 2022-08-05 - Asset plan of GGS151 | 2022-08-05 - Mail to Concern department | Non Functional | Fixed | 0 | 0 | 0
67 | Aug 04, 2022 | review artefact could not recognised | incident management/review log/artefact under review could not identify | review incident management | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Regression in untouched module | Project Management | 2022-08-05 - Incident Log in Ein frame | 2022-08-05 - Incident Log in Ein frame further | Observation | Will Fix in Future | 0 | 0 | 0
68 | Aug 02, 2022 | Protel is not working in PC (footprint are not saved) | Reopen the protel software | Protel 99SE {PC- Windows 11) | Aug 05, 2022 | Aug 05, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Gajesh Sharma | Sobhag Prajapat | New Feature | Reliability | 3rd Party Component | Systems Engineering | 2022-08-06 - GGE295 DC-DC Converter 12V-10A & 5V-1A task- Design & Implementation (Ckts, PCBs, Drawings, firmwares & Softwares) | 2022-08-06 - GGE295 DC-DC Converter 12V-10A & 5V-1A task- Design & Implementation (Ckts, PCBs, Drawings, firmwares & Softwares) | Functional | Platform / Design Limitations | 6 | 0 | 16
69 | Aug 04, 2022 | Project measurement BOM cost is not taken in tasks | project task- no task related to BOM cost | project tasks | Aug 05, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Project Management | 2022-08-05 - GGS151Plan_ Aug 03, 2022 11:09:10 (UTC) | 2022-08-05 - GGS151Plan_Aug 05, 2022 05:59:27 (UTC) | Non Functional | Fixed | 0 | 0 | 0
70 | Aug 03, 2022 | No NC Found in review for design document | No NC Found in review for design document | No NC Found in review for design document | Aug 05, 2022 | Aug 03, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Sobhag Prajapat | Syojiram Sharma | BUG | Protections | 3rd Party Component | Hardware | 2022-08-06 - During hardware design pair review no found any NCs by reviewer | 2022-08-06 - During hardware design pair review no found any NCs by reviewer | Observation | Fixed | 0 | 0 | 0
71 | Aug 03, 2022 | during hardware design review of project GGE295 no any NCs found. | during hardware design review of project GGE295 no any NCs found. | hardware design review | Aug 06, 2022 | Aug 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Syojiram Sharma | Sobhag Prajapat | BUG | Reliability | 3rd Party Component | Hardware | 2022-08-06 - no NC found in PCB Design implement review | 2022-08-06 - no NC found in PCB Design implement review | Functional | Platform / Design Limitations | 0 | 0 | 0
72 | Aug 05, 2022 | No defects found in enclouser design | No defects found in enclouser design | No defects found in enclouser design | Aug 06, 2022 | Aug 05, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Sandeep Jain | Bharat Kakra | BUG | Reliability | 3rd Party Component | Mechanical | 2022-08-06 - No bug found in review of encloser design | 2022-08-06 - No bug found in review of encloser design | Observation | By Design, Won't Fix | 0 | 0 | 0
73 | Aug 06, 2022 | Review of all three PCBs | Review of all three PCBs | Review of all three PCBs | Aug 06, 2022 | Aug 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Sobhag Prajapat | Gajesh Sharma | BUG | Reliability | 3rd Party Component | Hardware | 2022-08-06 - PCB design and circuit | 2022-08-06 - PCB design and circuit | Observation | By Design, Won't Fix | 0 | 0 | 0
74 | Aug 06, 2022 | no NC found in PCB layout and design | no NC found in PCB layout and design | no NC found in PCB layout and design | Aug 06, 2022 | Aug 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Sobhag Prajapat | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Hardware | 2022-08-06 - review done no NC observed in PCB layout and circuit | 2022-08-06 - review done no NC observed in PCB layout and circuit | Functional | Platform / Design Limitations | 0 | 0 | 0
75 | Aug 03, 2022 | Hardware Design document review | Hardware Design document review | Hardware Design document review | Aug 06, 2022 | Aug 03, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Syojiram Sharma | Sobhag Prajapat | BUG | Reliability | 3rd Party Component | Hardware | 2022-08-06 - No NC found in design document | 2022-08-06 - No NC found in design document | Functional | Will Fix in Future | 0 | 0 | 0
76 | Aug 09, 2022 | no NC found in module test case | no NC found in module test case | no NC found in module test case | Aug 09, 2022 | Aug 09, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Syojiram Sharma | Sobhag Prajapat | New Feature | Reliability | 3rd Party Component | Testing | 2022-08-09 - no NC found in review of Module test caes | 2022-08-09 - no NC found in review of Module test caes | Non Functional | Fixed | 0 | 0 | 0
77 | Aug 09, 2022 | no any NC found in mohule test caes | no any NC found in mohule test caes | no any NC found in mohule test caes | Aug 09, 2022 | Aug 09, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Sobhag Prajapat | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Hardware | 2022-08-09 - Module test cases. No NC PROVIDED BY REVIEWER | 2022-08-09 - Module test cases. No NC PROVIDED BY REVIEWER | Non Functional | By Design, Won't Fix | 0 | 0 | 0
78 | Aug 10, 2022 | no NC found during review for integration test case | no NC found during review for integration test case | no NC found during review for integration test case | Aug 10, 2022 | Aug 10, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Sobhag Prajapat | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Testing | 2022-08-10 - no NC found in Review of integration test case | 2022-08-10 - no NC found in Review of integration test case | Functional | Fixed | 0 | 0 | 0
79 | Aug 10, 2022 | no NC found in integration test case | no NC found in integration test case | no NC found in integration test case | Aug 10, 2022 | Aug 10, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Syojiram Sharma | Sobhag Prajapat | BUG | Reliability | 3rd Party Component | Testing | 2022-08-10 - no NC found in integration test case | 2022-08-10 - no NC found in integration test case | Functional | Fixed | 0 | 0 | 0
83 | Aug 12, 2022 | PQA member is itself just like a process owner, so process management skills must be there as need. Which is missing in talent/skills need for Audit function. Missing of this skill may impact on objectively evaluate the processes followed by practitioners. | Project Plan --> Project Team --> Talent needs | QA-22-23_ADTPLN Aug 10, 2022 10:14:29 (UTC) | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - project plan 1.0 dated 26th July 20222022-08-13 - Project plan 1.0 dated 26th July 2022 | 2022-08-13 - project plan 2.0 dated 13th August 20222022-08-13 - Project plan 2.0 dated 13th August 2022 | Functional | Fixed | 0 | 0 | 0
84 | Aug 12, 2022 | Regarding Risk identification & plan, PQA auditor identification, goals discussion, PQA reports discussion with SM, although recorded but not put in repository. Due to this may be next time latest MOM file not used to record further discussion and previous actions tracing may skip. | Check repository --> PQA | http://10.141.1.9:8080/svn/PQA/ Rev.1 | Aug 12, 2022 | Aug 16, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-08-17 - SVN PQA data at revision 1 | 2022-08-17 - SVN PQA data at revision 3 | Non Functional | Fixed | 0 | 0 | 0
85 | Aug 12, 2022 | In schedule some tasks are repeated monthly, as those need to be done monthly. But the task descriptions are the same for all these tasks. This may create confusion during monitoring and control as well as during timesheet filling. It should be defined either by Month name as prefix or else. | Project Plan --> Project Tasks | QA-22-23_ADTPLN Aug 10, 2022 10:14:29 (UTC) | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - Project plan --->1.0 | 2022-08-13 - Project plan --->2.0 | Non Functional | Fixed | 0 | 0 | 0
86 | Aug 12, 2022 | In Audit reports the suggestions mentioned are not showing impact of processes non compliance and not fully defined what are actual suggestions to practitioners and PEG. This may lead to misguide SM and PEG. | PQA Repository --> ADTRPT (May & Jul. 22) | http://10.141.1.9:8080/svn/PQA/ Rev.1 | Aug 12, 2022 | Aug 16, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-08-17 - JULY_ADTRPT 1.0 | 2022-08-17 - JULY_ADTRPT 2.0 | Functional | Fixed | 0 | 0 | 0
87 | Aug 12, 2022 | Although recorded in MOM regarding external auditor for the PQA audit did not respond on time, but this issue was not logged in Incident management to further trace. | Shweta Agarwal --> Incident Management | Incident Management | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - MOM available on desktop | 2022-08-13 - MOM updated on SVN first time | Non Functional | Fixed | 0 | 0 | 0
88 | Aug 12, 2022 | No assets are identified in QA plan, while QMS itself is big asset provided by PEG as process assets development. | Project Plan --> Asset Requirements | QA-22-23_ADTPLN Aug 10, 2022 10:14:29 (UTC) | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - project plan 1.0 | 2022-08-13 - project plan 2.0 | Observation | Fixed | 0 | 0 | 0
89 | Aug 12, 2022 | Knowledge requirements section is blank, as new tool (Einframe) introduced, and corresponding understanding sessions also organized. This should be knowledge requirement for this function. | Project Plan --> Knowledge Requirements | QA-22-23_ADTPLN Aug 10, 2022 10:14:29 (UTC) | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - project plan 1.0 | 2022-08-13 - project plan 2.0 | Non Functional | Fixed | 0 | 0 | 0
90 | Aug 12, 2022 | Risk identification is inadequate. Herself individual bus factor is high, which understands but not identified as risk. | Project Plan --> Project Risk | QA-22-23_ADTPLN Aug 10, 2022 10:14:29 (UTC) | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - project plan 1.0 | 2022-08-13 - project plan 2.0 | Functional | Fixed | 0 | 0 | 0
91 | Aug 12, 2022 | Efforts are zero despite of selection of team members. So overall efforts coming zero for this function as project. | Project Plan --> Project Tasks | QA-22-23_ADTPLN Aug 10, 2022 10:14:29 (UTC) | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - project plan 1.0 | 2022-08-13 - project plan 2.0 | Functional | Fixed | 0 | 0 | 0
92 | Aug 12, 2022 | Plan sample audits vertical wise to provide more adherence of processes. | Project Plan --> Project Tasks | QA-22-23_ADTPLN Aug 10, 2022 10:14:29 (UTC) | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project Related- | Jalaj Mathur | Shweta Aggarwal | BUG | Reliability | New Implementation | Systems Engineering | 2022-08-13 - project plan 1.0 | 2022-08-13 - project plan 2.0 | Observation | Fixed | 0 | 0 | 0
93 | Aug 12, 2022 | Block diagram not proper moter will replace with Power TX | Block diagram not proper moter will replace with Power TX | Block diagram not proper moter will replace with Power TX | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Assembly (Integration) | Modified Implementation | Hardware | 2022-08-13 - GGS151_HDWDSN Rev 23 | 2022-08-13 - GGS151_HDWDSN Rev 25 | Functional | Fixed | 0 | 0 | 0
94 | Aug 12, 2022 | Driver Details not found | Driver Details not found | Driver Details not found | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Assembly (Integration) | Modified Implementation | Hardware | 2022-08-13 - GGS151_HDWDSN Rev 23 | 2022-08-13 - GGS151_HDWDSN Rev 25 | Functional | Fixed | 0 | 0 | 0
95 | Aug 12, 2022 | Heat sink related data not available | Heat sink related data not available | Heat sink related data not available | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Assembly (Integration) | Modified Implementation | Hardware | 2022-08-13 - GGS151_HDWDSN Rev 23 | 2022-08-13 - GGS151_HDWDSN Rev 25 | Functional | Fixed | 0 | 0 | 0
96 | Aug 12, 2022 | schematic layout - already used schematic need to put | schematic layout - already used schematic need to put | schematic layout - already used schematic need to put | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Assembly (Integration) | Modified Implementation | Hardware | 2022-08-13 - GGS151_HDWDSN Rev 23 | 2022-08-13 - GGS151_HDWDSN Rev 25 | Functional | Fixed | 0 | 0 | 0
97 | Aug 12, 2022 | Toroidal Core releted data not found | Toroidal Core releted data not found | Toroidal Core releted data not found | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Assembly (Integration) | Modified Implementation | Hardware | 2022-08-13 - GGS151_HDWDSN Rev 23 | 2022-08-13 - GGS151_HDWDSN Rev 25 | Functional | Fixed | 0 | 0 | 0
98 | Aug 12, 2022 | Development and Exsolution environment - related data not found | Development and Exsolution environment - related data not found | Development and Exsolution environment - related data not found | Aug 12, 2022 | Aug 13, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Assembly (Integration) | Modified Implementation | Hardware | 2022-08-13 - GGS151_HDWDSN Rev 23 | 2022-08-13 - GGS151_HDWDSN Rev 25 | Functional | Fixed | 0 | 0 | 0
99 | Aug 16, 2022 | 1. Concept diagram missing | During Mechanical concept design review | GGS151_MCHDSN DOCUMENT | Aug 16, 2022 | Aug 16, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | New Implementation | Mechanical | 2022-08-16 - GGS151_MCHDSN.DOCX_16 | 2022-08-16 - GGS151_MCHDSN.DOCX_17 | Functional | Fixed | 0 | 0 | 0
100 | Aug 16, 2022 | 3.1 Base Module : Internal dependencies details missing | During mechanical design review | GGS151_MCHDSN Document | Aug 16, 2022 | Aug 16, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | New Implementation | Mechanical | 2022-08-16 - GGS151_MCHDSN.DOCX_16 | 2022-08-16 - GGS151_MCHDSN.DOCX_17 | Functional | Fixed | 0 | 0 | 0
101 | Aug 16, 2022 | 3.2 Top Cover Internal & external dependencies details are missing | During Mechanical concept design review | GGS151_MCHDSN Document | Aug 16, 2022 | Aug 16, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | New Implementation | Mechanical | 2022-08-16 - GGS151_MCHDSN.DOCX_16 | 2022-08-16 - GGS151_MCHDSN.DOCX_17 | Functional | Fixed | 0 | 0 | 0
102 | Aug 16, 2022 | Sticker :- Many details missing related to sticker concept design | During Mechanical Concept design Review | GGS151_MCHDSN Document | Aug 16, 2022 | Aug 16, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | New Implementation | Mechanical | 2022-08-16 - GGS151_MCHDSN.DOCX_16 | 2022-08-16 - GGS151_MCHDSN.DOCX_17 | Functional | Fixed | 0 | 0 | 0
103 | Aug 17, 2022 | Designer itself do module testing by making module test cases, so to do this formally like log the defects and resolve by himself is extra burden, practically it is part of design & implementation and do in each projects. So see this and revise processes accordingly. | During Implementation | QMS_4.0 --> PRCD_IMPINT | Aug 17, 2022 | Sep 09, 2022 | - | Closed | Project RelatedGGS151 | Chandrashekhar Sharma | Jalaj Mathur | New Feature | Reliability | Regression in untouched module | Systems Engineering | 2022-09-12 - QMS 4.0 --> PRCD_IMPINT | 2022-09-12 - QMS 4.1 --> PRCD_IMPINT | Functional | By Design, Won't Fix | 0 | 0 | 0
104 | Aug 17, 2022 | The while loop in the firmware never ends and if any fault occurs it will direct to starting of main() function. | Flow chart needs to correct. | GGS151_FRWDSN_0.1_Harish Nagar_ | Aug 17, 2022 | Aug 17, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Reliability | Modified Implementation | Firmware | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_ | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_ | Functional | Fixed |  | 0 | 0
105 | Aug 17, 2022 | There is no programmer mentioned used that will be used at the time of designing and manufacturing. | At the time of selection of controller also select the programmer for both design and manufacturing. | GGS151_FRWDSN_0.1_Harish Nagar_ | Aug 17, 2022 | Aug 17, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Reliability | Modified Implementation | Project Management | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=10.2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=10. | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=13.2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=12. | Non Functional | Fixed |  | 0 | 0
106 | Aug 17, 2022 | Mention the ADC configuration details needed to be set in the ADC configuration of the MCU. | At the time of theoretical analysis details of the ADC configuration needs to be set. | GGS151_FRWDSN_0.1_Harish Nagar_ | Aug 17, 2022 | Aug 17, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Mains Mode | Modified Implementation | Project Management | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=10. | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=15. | Functional | Fixed |  | 0 | 0
107 | Aug 17, 2022 | Topic 3.4.8 Only AC voltage was measured not current | This will help in calculated the proper data at the time of writing the firmware code. | GGS151_FRWDSN_0.1_Harish Nagar_ | Aug 17, 2022 | Aug 17, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Mains Mode | Modified Implementation | Project Management | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=10. | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=14. | Observation | Fixed |  | 0 | 0
108 | Aug 17, 2022 | Topic 3.10.2 The conditional block is empty | Misunderstanding occurs at the time of firmware development. | GGS151_FRWDSN_0.1_Harish Nagar_ | Aug 17, 2022 | Aug 17, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Reliability | Modified Implementation | Project Management | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=14. | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=15. | Observation | Fixed |  | 0 | 0
109 | Aug 17, 2022 | Topic 3.5.2 There is not error definition in the flow chart. | At the time of firmware wring what will be written to calculate the error. | GGS151_FRWDSN_0.1_Harish Nagar_ | Aug 17, 2022 | Aug 17, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Reliability | Modified Implementation | Project Management | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=15. | 2022-08-17 - GGS151_FRWDSN_0.1_Harish Nagar_, Revision=16. | Observation | Fixed |  | 0 | 0
110 | Aug 17, 2022 | Topic 3.5.2 There is not error definition in the flow chart. | At the time of firmware wring what will be written to calculate the error. | GGS151_FRWDSN_0.1_Harish Nagar_ | Aug 17, 2022 | Sep 18, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Reliability | Modified Implementation | Firmware | 2022-09-13 - GGS151_FRWDSN_0.1_Harish Nagar_ | 2022-09-13 - GGS151_FRWDSN_0.1_Harish Nagar_ | Observation | Fixed | 0 | 0 | 0
111 | Aug 16, 2022 | PNP Transistor BC557 Emitter collector interchange. | During Solar Charger Schematic Review. | Solar Charger Schematic | Aug 19, 2022 | Aug 19, 2022 | - | Closed | Project RelatedGGS151 | Chandrashekhar Sharma | Rakesh Pandey | BUG | Reliability | Modified Implementation | Hardware | 2022-08-19 - Solar Charger SCH Rev 1 | 2022-08-19 - Solar Charger SCH Rev 1.0 | Functional | Fixed | 0 | 0 | 0
112 | Aug 16, 2022 | OP amp IC ground required Signal ground but in SCH connected with SMPS supply ground. | During Solar charger Schematic Review | Solar charger Schematic | Aug 19, 2022 | Aug 19, 2022 | - | Closed | Project RelatedGGS151 | Chandrashekhar Sharma | Rakesh Pandey | BUG | Reliability | Modified Implementation | Hardware | 2022-08-19 - Solar Charger SCH 1.0 | 2022-08-19 - Solar Charger SCH 1.0 | Functional | Fixed | 0 | 0 | 0
113 | Aug 19, 2022 | Heat sink HS2 mounting holes required isolate but in PCB holes are connected with drain of mosfet. | During Solar charger PCB Review. | Solar charger PCB | Aug 19, 2022 | Aug 19, 2022 | - | Closed | Project RelatedGGS151 | Chandrashekhar Sharma | Rakesh Pandey | BUG | Reliability | Modified Implementation | Hardware | 2022-08-19 - Solar Charger PCB G0449P1134 Rev1.0 | 2022-08-19 - Solar Charger PCB G0449P1134 Rev1.1 | Functional | Fixed | 0 | 0 | 0
114 | Aug 19, 2022 | Mosfet Drain(Q7,8) to hex bolt track thickness is not sufficient to carrying current 45-50A. | During Solar charger PCB Review. | Solar charger PCB | Aug 19, 2022 | Aug 19, 2022 | - | Closed | Project RelatedGGS151 | Chandrashekhar Sharma | Rakesh Pandey | BUG | Reliability | Modified Implementation | Hardware | 2022-08-19 - Solar Charger PCB G0449P1134 Rev1.1 | 2022-08-19 - Solar Charger PCB G0449P1134 Rev1.1 | Functional | Fixed | 0 | 0 | 0
115 | Aug 23, 2022 | Bottom Channel missing below Transformer location | During Chassis Drawing Review | Drawing No HW_2758 | Aug 23, 2022 | Aug 23, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | Modified Implementation | Mechanical | 2022-08-23 - Chassis Drawing HW_A_2758_00 | 2022-08-23 - Chassis Drawing HW_A_2758_01 | Functional | Fixed | 0 | 0 | 0
116 | Aug 23, 2022 | Some Tolerance and critical dimension missing | During Chassis Design review | Chassis HW_2758 | Aug 23, 2022 | Aug 23, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | Modified Implementation | Mechanical | 2022-08-23 - Chassis drawing HW_2758_00 | 2022-08-23 - Chassis drawing HW_2758_01 | Functional | Fixed | 0 | 0 | 0
117 | Aug 23, 2022 | LCD Plate Position not correct according to welding requirement | During Chassis Design review | Chassis HW_2758 | Aug 23, 2022 | Aug 23, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | Modified Implementation | Mechanical | 2022-08-23 - Chassis drawing HW_A_2758_00 | 2022-08-23 - Chassis drawing HW_A_2758_01 | Functional | Fixed | 0 | 0 | 0
118 | Aug 23, 2022 | Connector J4 Direction reverse . | During PCB design review. | Power PCB G0449P1136 REV-1.0 | Aug 23, 2022 | Aug 23, 2022 | - | Closed | Project RelatedGGS151 | Chandrashekhar Sharma | Rakesh Pandey | BUG | Reliability | Modified Implementation | Hardware | 2022-08-23 - Power PCB G0449P1136 REV-1.0 | 2022-08-23 - Power PCB G0449P1136 REV-1.1 | Functional | Fixed | 0 | 0 | 0
119 | Aug 23, 2022 | It is not easy to understand the functions definition. | There should be short comments for the function so that it is easy to understand. | Mdk Arm Keil u5 | Aug 23, 2022 | Aug 23, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Reliability | Modified Implementation | Firmware | 2022-08-23 - GGS151_3KW_MPPT_PCU.mcp, Revision 19 | 2022-08-23 - GGS151_3KW_MPPT_PCU.mcp, Revision 20 | Observation | Fixed |  | 0 | 0
120 | Aug 23, 2022 | Temperature value masking for open connection and short connection. | Need to put the condition if the value crosses the particular limit it will initialize the specific value. | Codewarrior 8.3 | Aug 23, 2022 | Aug 23, 2022 | - | Closed | Project RelatedGGS151 | Abhishek Gupta | Harish Nagar | BUG | Reliability | Modified Implementation | Firmware | 2022-08-23 - 2022-08-23 - GGS151_3KW_MPPT_PCU.mcp, Revision 19 | 2022-08-23 - 2022-08-23 - GGS151_3KW_MPPT_PCU.mcp, Revision 20 | Functional | Fixed |  | 0 | 0
121 | Aug 26, 2022 | Threads Check for all studs with Thread gauge | During review of test case | Mechanical Test case in Chassis 2758 | Aug 26, 2022 | Aug 26, 2022 | - | Closed | Project RelatedGGS151 | Sandeep Jain | Bharat Kakra | BUG | Reliability | Modified Implementation | Mechanical | 2022-08-26 - GGS151_MCTCAS_REV20 In Mechanical test case | 2022-08-26 - GGS151_MCTCAS REV21 In Mechanical test case | Functional | Fixed | 0 | 0 | 0
122 | Aug 25, 2022 | Module test case start up ,UVLO ,High Cut and High cut recovery related spec. not identify | reviewing the test case test not full fill the spec. | hardware test case | Aug 27, 2022 | Aug 27, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Hardware | 2022-08-27 - GGS151_HWTCAS Rev-32 | 2022-08-27 - GGS151_HWTCAS Rev-35 | Functional | Fixed | 0 | 0 | 0
123 | Aug 25, 2022 | Test case ID name need to corelated with as hardware module | during review of hardware test case | hardware test case document | Aug 27, 2022 | Aug 27, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Hardware | 2022-08-27 - GGS151_HWTCAS Rev-32 | 2022-08-27 - GGS151_HWTCAS Rev-35 | Non Functional | Fixed | 0 | 0 | 0
124 | Aug 29, 2022 | Supply series diode getting very hot and burnt | During testing of heat run | System test case ID 6 and 11 | Sep 01, 2022 | Aug 29, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Adarsh Kumar Bairwa | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Hardware | 2022-09-01 - Validation phase during testing of 6 and 11 no test case | 2022-09-01 - validation phase during testing of 6 and 11 no. test case | Functional | Fixed | 0 | 0 | 0
125 | Aug 29, 2022 | at full capacity load 10 A Encloser getting hot and reach up to 80 Deg C | During testing of test case id 6 and 11 | During testing of test case id 6 and 11 | Sep 01, 2022 | Aug 29, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Adarsh Kumar Bairwa | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Hardware | 2022-09-01 - during validation testing with test case 6 and 11 | 2022-09-01 - during validation testing with test case 6 and 11 | Functional | Fixed | 0 | 0 | 0
126 | Sep 02, 2022 | Firmware integration details is missing | During review of integration documents review | Integration documents of GGE151 | Sep 02, 2022 | Sep 03, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Hardware | 2022-09-03 - GGS151_INTDSN(Interface and Integration) | 2022-09-03 - GGS151_INTDSN Rev_40 | Functional | Fixed | 0 | 0 | 0
127 | Sep 01, 2022 | DC Voltage between pin no.4 & 8 of U1 found 4.6V but the specification is 5V±0.2V | Check at IC U1 between pin no. 4 and 8 | Multimeter, Solar simulator | Sep 02, 2022 | Sep 02, 2022 | - | Closed | Project RelatedGGS151 | Alok Kumar Singh | Chandrashekhar Sharma | BUG | Charging Profile | Modified Implementation | Hardware | 2022-09-02 - PCBG0449P1134 REV1.2 | 2022-09-02 - PCBG0449P1134 REV1.2 | Functional | Fixed | 0 | 0 | 0
128 | Sep 02, 2022 | SCR and SCr driver PCb Integration related information missisng | In integration document | In integration document of GGE151 | Sep 02, 2022 | Sep 03, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Hardware | 2022-09-03 - GGS151_INTDSN (Interface and Integration) | 2022-09-03 - GGS151_INTDSN Rev-40 | Functional | Fixed | 0 | 0 | 0
129 | Sep 01, 2022 | In Power PCB_G0449P1136Rev-1.1,found Voltage 3.0V between pin no.2 & 4 of connector. | Set simulator at 48V and check voltage at pin no 2 & 4 | Solar simulator | Sep 02, 2022 | Sep 02, 2022 | - | Closed | Project RelatedGGS151 | Alok Kumar Singh | Chandrashekhar Sharma | BUG | Display | Modified Implementation | Hardware | 2022-09-02 - Power PCB G0449P1136 REV-1.1 | 2022-09-02 - Power PCB G0449P1136 REV-1.1 | Functional | Fixed | 0 | 0 | 0
130 | Sep 02, 2022 | Solar charging salection releted integration test case missing | During review of integration test case | Integration test case document of GGE151 | Sep 02, 2022 | Sep 03, 2022 | - | Closed | Project RelatedGGS151 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-03 - GGS151_INTCAS Rev 38 | 2022-09-03 - GGS151_INTCAS Rev 38 | Functional | Fixed | 0 | 0 | 0
131 | Sep 06, 2022 | Corrective actions, process & product defect density are not mentioned in final metrics report while calculated separately in draft report at local computer. | metrics report- end of report, corrective actions, product defect density, process defect density. | metrics report available at svn on revision 20 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - matrix report updated with defect and process density | 2022-09-07 - matrix report updated with defect and process density | Functional | Fixed | 0 | 0 | 0
132 | Sep 06, 2022 | project measurement are missing in project definition | go to project description | project plan- description | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - project unpublish and publish with update | 2022-09-07 - project unpublish and publish with update | Non Functional | Fixed | 0 | 0 | 0
133 | Sep 06, 2022 | Risk RPN is not revised at the end of project, also risk related to new PCB designer is not identified in any records, while training action is already taken. | projects- project risk, action plan | project plan- project risk | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - project unpublish and publish with update | 2022-09-07 - project unpublish and publish with update | Non Functional | Fixed | 0 | 0 | 0
134 | Sep 06, 2022 | final MOM is not updated at SVN server, but available on a local computer, | SVN server- refer MOM | revision 20 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - MOM updated and update action item | 2022-09-07 - MOM updated and update action item | Non Functional | Fixed | 0 | 0 | 0
135 | Sep 06, 2022 | No review evidence could seen for RTT review after adding design, integration, system IDs. | RTT review log, timesheet not seen | RTT review | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - During audit at validation phase | 2022-09-06 - During audit at validation phase | Observation | Fixed | 0 | 0 | 0
136 | Sep 06, 2022 | updated HWTCAS are not available at SVN server | SVN server - HWTCAS not updated | HWTCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - Audit of hardware test case | 2022-09-06 - Audit of hardware test case | Non Functional | Fixed | 0 | 0 | 0
137 | Sep 06, 2022 | user & CFT support documentation, BOM are not placed at SVN server | SVN server -documentation | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - all supporting document provide and make SVN access also | 2022-09-07 - all supporting document provide and make SVN access also | Non Functional | Fixed | 0 | 0 | 0
138 | Sep 06, 2022 | updated SYSCAS are not available at SVN server | SVN server - SYSCAS not updated | SYSCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - System test case during validation phase | 2022-09-06 - System test case during validation phase | Non Functional | Fixed | 0 | 0 | 0
139 | Sep 06, 2022 | Updated RTT is not found on SVN server | SVN- RTT not updated | SVN server- RTT | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - RTT updated with system test case id | 2022-09-07 - RTT updated with system test case id | Non Functional | Fixed | 0 | 0 | 0
140 | Sep 06, 2022 | Validation report is not found on SVN | SVN- Validation report missing | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - audit of validation phase | 2022-09-06 - audit of validation phase | Non Functional | Fixed | 0 | 0 | 0
141 | Sep 06, 2022 | no formal defect analysis is seen | defect analysis missing | defect analysis | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - two number of testing defect log by adarsh and analysis then resolved the defect. | 2022-09-07 - two number of testing defect log by adarsh and analysis then resolved the defect. | Functional | Fixed | 0 | 0 | 0
142 | Sep 06, 2022 | Corrective actions, process & product defect density are not mentioned in final metrics report while calculated separately in draft report at local computer. | metrics report- end of report, corrective actions, product defect density, process defect density. | metrics report available at svn on revision 20 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - metrics report updated with product defect density | 2022-09-07 - metrics report updated with product defect density | Functional | Fixed | 0 | 0 | 0
143 | Sep 06, 2022 | project measurement are missing in project definition | go to project description | project plan- description | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | Non Functional | Fixed | 0 | 0 | 0
144 | Sep 06, 2022 | Risk RPN is not revised at the end of project, also risk related to new PCB designer is not identified in any records, while training action is already taken. | projects- project risk, action plan | project plan- project risk | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | Non Functional | Fixed | 0 | 0 | 0
145 | Sep 06, 2022 | final MOM is not updated at SVN server, but available on a local computer, | SVN server- refer MOM | revision 9 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - sheet updated and svn access provided access provided | 2022-09-07 - sheet updated and svn access provided access provided | Non Functional | Fixed | 0 | 0 | 0
146 | Sep 06, 2022 | No review evidence could seen for RTT review after adding design, integration, system IDs. | RTT review log, timesheet not seen | RTT review | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - RTT updated and svn committed | 2022-09-07 - RTT updated and svn committed | Observation | Fixed | 0 | 0 | 0
147 | Sep 06, 2022 | updated HWTCAS are not available at SVN server | SVN server - HWTCAS not updated | HWTCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - sheet updated and committed on svn access. | 2022-09-07 - sheet updated and committed on svn access. | Non Functional | Fixed | 0 | 0 | 0
148 | Sep 06, 2022 | user & CFT support documentation, BOM are not placed at SVN server | SVN server -documentation | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - all supporting documents provided on svn access. | 2022-09-07 - all supporting documents provided on svn access. | Non Functional | Fixed | 0 | 0 | 0
149 | Sep 06, 2022 | updated SYSCAS are not available at SVN server | SVN server - SYSCAS not updated | SYSCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - sheet updated and committed on svn access. | 2022-09-07 - sheet updated and committed on svn access. | Non Functional | Fixed | 0 | 0 | 0
150 | Sep 06, 2022 | Updated RTT is not found on SVN server | SVN- RTT not updated | SVN server- RTT | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - RTT UPDATED AND COMMITTED ON SVN ACCESS. | 2022-09-07 - RTT UPDATED AND COMMITTED ON SVN ACCESS. | Non Functional | Fixed | 0 | 0 | 0
151 | Sep 06, 2022 | Validation report is not found on SVN | SVN- Validation report missing | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - VALIDATION REPORT UPDATED AND COMMITTED ON SVN ACCESS. | 2022-09-07 - VALIDATION REPORT UPDATED AND COMMITTED ON SVN ACCESS. | Non Functional | Fixed | 0 | 0 | 0
152 | Sep 06, 2022 | no formal defect analysis is seen | defect analysis missing | defect analysis | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - ANALYSIS DONE IN METRICS REPORT. | 2022-09-07 - ANALYSIS DONE IN METRICS REPORT. | Functional | Fixed | 0 | 0 | 0
153 | Sep 08, 2022 | Documents location link should be as hyper link. | Project Closure report. | SVN rev. 30 | Sep 08, 2022 | Sep 08, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-08 - resolved . All link converted in to hyper link | 2022-09-08 - resolved . All link converted in to hyper link | Non Functional | Fixed | 0 | 0 | 0
154 | Sep 08, 2022 | Backup location and restoration occurrence not mentioned. | Project Closure report. | SVN Rev. 30 | Sep 08, 2022 | Sep 08, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-08 - resolved . Location defined in sheet . | 2022-09-08 - resolved . Location defined in sheet . | Non Functional | Fixed | 0 | 0 | 0
155 | Sep 08, 2022 | Low battery alarm and low battery cut off found out of specification | Give full load at backup mode and check low battery alarm and cut. | Multimeter | Sep 08, 2022 | Sep 09, 2022 | - | Closed | Project RelatedGGS151 | Alok Kumar Singh | Harish Nagar | BUG | Protections | Modified Implementation | Testing | 2022-09-13 - GGS151_3KW_MPPT_PCU_R0.elf.S | 2022-09-13 - GGS151_3KW_MPPT_PCU_R1.elf.S | Functional | Fixed |  | 0 | 0
156 | Sep 12, 2022 | As per need id 17 enclosure written as Aluminum, but for more elaboration we should mention either grade or thickness or other technical details of Aluminum. As may be aluminum available in various qualities, then what we should use and what we need should be mentioned in elaboration. | Functional Specification need id 17 | SVN --> DC_DC_Converter repository version 41 | Sep 12, 2022 | Sep 12, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-09-13 - SVN --> DC_DC_Converter repository version 412022-09-12 - During RD phase FS review on http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302/Requirment/Toll%20Gate%201/ | 2022-09-13 - SVN --> DC_DC_Converter repository version 442022-09-12 - http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302/Requirment/Toll%20Gate%201/ | Functional | Fixed | 0 | 0 | 0
157 | Sep 12, 2022 | As per need id 16 Cooling mentioned as Free air cooling : We should mention either air flow criteria or permissible temperature by this air cooling. Because how can someone test cooling as needed? | Functional Specification need id 16 | SVN --> DC_DC_Converter repository version 41 | Sep 12, 2022 | Sep 12, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-09-13 - SVN --> DC_DC_Converter repository version 412022-09-12 - In RD Phase Review Of FS at http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302/Requirment/Toll%20Gate%201/ | 2022-09-13 - SVN --> DC_DC_Converter repository version 442022-09-12 - http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302/Requirment/Toll%20Gate%201/ | Functional | Fixed | 0 | 0 | 0
158 | Sep 12, 2022 | There are some spelling mistakes, please run spelling check feature of Microsoft Word to correct things. | Functional Specification | SVN --> DC_DC_Converter repository version 41 | Sep 12, 2022 | Sep 12, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-09-13 - SVN --> DC_DC_Converter repository version 412022-09-12 - in RD Phase Review of FS http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302/Requirment/Toll%20Gate%201/ | 2022-09-13 - SVN --> DC_DC_Converter repository version 442022-09-12 - http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302/Requirment/Toll%20Gate%201/ | Non Functional | Fixed | 0 | 0 | 0
159 | Sep 13, 2022 | Need id 13 should also related to need ids 16, 17, 21, 23, 25 & 26, as IP rating depends upon these requirements also. | Review of GGE302_REQTRT | SVN --> DC_DC_Converter Repository version 46 | Sep 13, 2022 | Sep 13, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-09-13 - SVN --> DC_DC_Converter Repository version 46 | 2022-09-13 - SVN --> DC_DC_Converter Repository version 47 | Functional | Fixed | 0 | 0 | 0
160 | Sep 13, 2022 | Need id 26 should also related to need ids 17, 21, 24, 25 & Vice versa | Review of GGE302_REQTRT | SVN --> DC_DC_Converter Repository version 46 | Sep 13, 2022 | Sep 13, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-09-13 - SVN --> DC_DC_Converter Repository version 46 | 2022-09-13 - SVN --> DC_DC_Converter Repository version 47 | Functional | Fixed | 0 | 0 | 0
161 | Sep 13, 2022 | Some need ids elaboration not came from FS properly, please re-check and do the needful. | Review of GGE302_REQTRT | SVN --> DC_DC_Converter Repository version 46 | Sep 13, 2022 | Sep 13, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-09-13 - SVN --> DC_DC_Converter Repository version 46 | 2022-09-13 - SVN --> DC_DC_Converter Repository version 47 | Observation | Fixed | 0 | 0 | 0
162 | Sep 07, 2022 | metrics report- corrective actions are not filled phase wise, inappropriate, | metrics report at SVN server | metrics report at SVN | Sep 13, 2022 | Sep 14, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-09-14 - GGS151_MESRPT REV_44 | 2022-09-14 - GGS151_MESRPT REV_49 | Functional | Fixed | 0 | 0 | 0
163 | Sep 07, 2022 | Updated RTT, HTCAS, code review checklist are not available at SVN server but on a local computer, | RTT, HWTCAS, CODRVW at svn | SVN server | Sep 13, 2022 | Sep 26, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Project Management | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | Non Functional | Fixed | 0 | 0 | 0
164 | Sep 07, 2022 | Defect analysis is not done | defect analysis missing | defect analysis missing | Sep 13, 2022 | Sep 26, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | Non Functional | Fixed | 0 | 0 | 0
165 | Sep 07, 2022 | testing defects are logged in issue category. | incident management - testing defects log for this proect | incident management | Sep 13, 2022 | - | 20 Days | Open | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | - | - | - | - | null | null | Observation
166 | Sep 15, 2022 | In need id 4 restart should replaced by reboot. | GGE289 Functional specification review | SVN --> LKVA_inc Repository version 13 | Sep 15, 2022 | Sep 15, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Discharging Profile | Modified Implementation | Systems Engineering | 2022-09-15 - 13th version of function specifications | 2022-09-15 - 15th version of function specifications | Non Functional | Fixed | 0 | 0 | 0
167 | Sep 15, 2022 | In need id 6 THD assumption should mention as "on linear load". | GGE289 Functional specification review | SVN --> LKVA_inc Repository version 13 | Sep 15, 2022 | Sep 15, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Discharging Profile | Modified Implementation | Systems Engineering | 2022-09-15 - 13th version of Functional specification | 2022-09-15 - 15th version of Functional specification | Non Functional | Fixed | 0 | 0 | 0
168 | Sep 15, 2022 | In need id 6 : for non linear load THD value should also mention. | GGE289 Functional specification review | SVN --> LKVA_inc Repository version 13 | Sep 15, 2022 | Sep 15, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Discharging Profile | Modified Implementation | Systems Engineering | 2022-09-15 - 13th version of Functional specification | 2022-09-15 - 15th version of Functional specification | Functional | Fixed | 0 | 0 | 0
169 | Sep 15, 2022 | In need id 10 : elaboration written as "Battery charging current will be 25A or 15A", here "OR" should replaced by "AND", as you will give both option in model. | GGE289 Functional specification review | SVN --> LKVA_inc Repository version 13 | Sep 15, 2022 | Sep 15, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Charging Profile | New Implementation | Systems Engineering | 2022-09-15 - 13th version of Functional specification | 2022-09-15 - 15th version of Functional specification | Functional | Fixed | 0 | 0 | 0
170 | Sep 15, 2022 | In need id 15 & 16 the external interfaces mentioned looks not related. | GGE289 Functional specification review | SVN --> LKVA_inc Repository version 13 | Sep 15, 2022 | Sep 15, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Protections | Modified Implementation | Systems Engineering | 2022-09-15 - 13th version of Functional specification | 2022-09-15 - 15th version of Functional specification | Observation | Fixed | 0 | 0 | 0
171 | Sep 15, 2022 | Regarding user support documents like SOP, QA & LT, service manuals, user manuals etc related need not identified. | GGE289 Functional specification review | SVN --> LKVA_inc Repository version 13 | Sep 15, 2022 | Sep 15, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Assembly (Integration) | Modified Implementation | Systems Engineering | 2022-09-15 - 13th version of Functional specification | 2022-09-15 - 15th version of Functional specification | Functional | Fixed | 0 | 0 | 0
172 | Sep 16, 2022 | In house or Out source Assets not listed in plan. | Einframe --> Project SP10 GGE302 --> Asset Requirements tab. | Einframe --> Project SP10 GGE302 Sep 16, 2022 02:02:50 (UTC) | Sep 16, 2022 | Sep 16, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-16 - Einframe --> Project SP10 GGE302 Sep 16, 2022 02:02:50 (UTC) | 2022-09-16 - Einframe --> Project SP10 GGE302 Sep 16, 2022 02:02:50 (UTC) | Functional | Fixed | 0 | 0 | 0
173 | Sep 16, 2022 | Estimated efforts in filled template of Efforts estimation not matched with Projects planned efforts after enter tasks in einframe. | Efforts estimation doc and efforts in einframe. | SVN Repository -- DC DC Converter version 51 | Sep 16, 2022 | Sep 16, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-16 - SVN Repository -- DC DC Converter version 51 | 2022-09-16 - SVN Repository -- DC DC Converter version 53 | Functional | Fixed | 0 | 0 | 0
174 | Sep 16, 2022 | HW, FW & Mech master library link not correct. | CM plan of SP10 GGE302 | SVN Repository -- DC DC Converter version 51 | Sep 16, 2022 | Sep 16, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Hardware | 2022-09-16 - SVN Repository -- DC DC Converter version 51 | 2022-09-16 - SVN Repository -- DC DC Converter version 54 | Non Functional | Fixed | 0 | 0 | 0
175 | Sep 16, 2022 | Module test cases making task should be plan before its review. | Einframe --> Project SP10 GGE302 -- Project tasks tab | Einframe --> Project SP10 GGE302 Sep 16, 2022 02:02:50 (UTC) | Sep 16, 2022 | Sep 16, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-16 - Einframe --> Project SP10 GGE302 Sep 16, 2022 02:02:50 (UTC) | 2022-09-16 - Einframe --> Project SP10 GGE302 Sep 16, 2022 018:12:50 (UTC) | Non Functional | Fixed | 0 | 0 | 0
176 | Sep 16, 2022 | Module testing is also part of D&I phase, so D&I phase audit should do after that. | Einframe --> Project SP10 GGE302 -- Project tasks tab | Einframe --> Project SP10 GGE302 Sep 16, 2022 02:02:50 (UTC) | Sep 16, 2022 | Sep 16, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-16 - Einframe --> Project SP10 GGE302 Sep 16, 2022 02:02:50 (UTC) | 2022-09-16 - Einframe --> Project SP10 GGE302 Sep 16, 2022 18:12:50 (UTC) | Observation | Fixed | 0 | 0 | 0
177 | Sep 16, 2022 | In CM plan the artefacts name wrongly mentioned as GGE295 instead of GGE302. | CM plan of SP10 GGE302 | SVN Repository -- DC DC Converter version 51 | Sep 16, 2022 | Sep 16, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-16 - SVN Repository -- DC DC Converter version 51 | 2022-09-16 - SVN Repository -- DC DC Converter version 55 | Non Functional | Fixed | 0 | 0 | 0
178 | Sep 17, 2022 | time sheet for few task-person is missing, ex. Sobhag for plan review is missed | time sheet not available | time sheet is missed | Sep 17, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Documentation | 3rd Party Component | Project Management | 2022-09-19 - audit phase during time sheet captured | 2022-09-19 - audit phase during time sheet captured | Observation | Fixed | 0 | 0 | 0
179 | Sep 17, 2022 | product & process defect density to be calculated at the end of project only as per QMS. | Metrics report-defect density calculation is not required. | metrics report- product defect density | Sep 17, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Documentation | 3rd Party Component | Project Management | 2022-09-19 - matrix report during RD phase 2022-09-19 - During Audit in RD phase | 2022-09-19 - SVN-DC-DC converter-Revision 582022-09-19 - SVN-DC-DC converter-Revision 58 | Observation | Fixed | 0 | 0 | 0
180 | Sep 17, 2022 | Kick off meeting- project major requirements should be briefly discussed with the team, eg. IP test, product ratings | kick off meeting MOM | MIMET- kick off meeting | Sep 17, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Documentation | 3rd Party Component | Project Management | 2022-09-19 - audit phase in RD phase2022-09-19 - During Audit in R&D phase | 2022-09-19 - further will take care in mom making2022-09-19 - SVN-DC-DC converter -Revision 59 | Observation | Will Fix in Future | 0 | 0 | 0
181 | Sep 17, 2022 | MOM does not show any discussion on pending or previous action item which in turn may lead to miss that action item if not mentioned in MOM. | MINMET meetings, action items | MINMET | Sep 19, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Protections | Modified Implementation | Project Management | 2022-09-19 - Audit during RD phase | 2022-09-19 - Audit during RD phase | Observation | Will Fix in Future | 0 | 0 | 0
182 | Sep 19, 2022 | In house or Out source Assets not listed in plan. | Einframe --> Project GGE289 --> Asset Requirements tab. | Einframe --> Sep 19, 2022 11:32:33 (UTC) | Sep 19, 2022 | Sep 20, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Charging Profile | Modified Implementation | Project Management | 2022-09-20 - Einframe --> Sep 19, 2022 11:32:33 (UTC) | 2022-09-20 - Einframe -->Sep 20, 2022 12:08:25 (UTC) | Functional | Fixed | 0 | 0 | 0
183 | Sep 19, 2022 | Resource loading of some persons showing more than 150%, need to re-look the allocation. | Einframe --> Project GGE289 --> Project team --> Resource loading | Einframe --> Sep 19, 2022 11:32:33 (UTC) | Sep 19, 2022 | Sep 20, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Charging Profile | Modified Implementation | Project Management | 2022-09-20 - Einframe --> Sep 19, 2022 11:32:33 (UTC) | 2022-09-20 - Einframe -->Sep 20, 2022 12:08:25 (UTC) | Non Functional | Fixed | 0 | 0 | 0
184 | Sep 19, 2022 | In CM plan firmware repository not mentioned, although its exists. | CM plan of project GGE289 | SVN --> LKVA_inv repository version 21 | Sep 19, 2022 | Sep 20, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Jalaj Mathur | Deepesh Jain | BUG | Charging Profile | Modified Implementation | Project Management | 2022-09-20 - SVN --> LKVA_inv repository version 21 | 2022-09-20 - in rev 23 (firmware repository link added in document) | Non Functional | Fixed | 0 | 0 | 0
189 | Sep 17, 2022 | System is not taking overload protection at 3300 , by changing the maximum discharging current to 80 A, problem Fixes. | While putting the load on the inverter for checking overload protection. | SVN repository FW_17801 - inverter_firmware - projects - GGS151_version 42 | Sep 20, 2022 | Sep 20, 2022 | - | Closed | Project RelatedGGS151 | Mayur Sharma | Harish Nagar | BUG | Protections | Modified Implementation | Firmware | 2022-09-20 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU SVN_version42 GGS151_3KW_MPPT_PCU_R1.elf.S | 2022-09-20 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU SVN_version44 GGS151_3KW_MPPT_PCU_R2.elf.S | Functional | Fixed |  | 0 | 0
190 | Sep 17, 2022 | LCD is not showing PROTECTION LOW BATTERY at 42.4 V. | By doing some changes in the Firmware program. | SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU_version42 | Sep 20, 2022 | Sep 21, 2022 | - | Closed | Project RelatedGGS151 | Mayur Sharma | Harish Nagar | BUG | Display | Modified Implementation | Firmware | 2022-09-21 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU_LCD_1602_Rev_0 | 2022-09-21 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU_LCD_1602_Rev_1 | Functional | Fixed |  | 0 | 0
191 | Sep 17, 2022 | At 64 V solar battery charging not started. | By Changing the address on solar parameters data 1CC = 20F0 1CD = 38FC | SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU_version42 | Sep 20, 2022 | Sep 21, 2022 | - | Closed | Project RelatedGGS151 | Mayur Sharma | Harish Nagar | BUG | Tuning | Modified Implementation | Firmware | 2022-09-21 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU SVN_version44 GGS151_3KW_MPPT_PCU_R2.elf.S | 2022-09-21 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU SVN_version45 GGS151_3KW_MPPT_PCU_R3.elf.S | Functional | Fixed |  | 0 | 0
192 | Sep 19, 2022 | System is not Over PV capacity at 3300W solar power. | By setting Over PV at 3300W in controller firmware . | SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU_version42 | Sep 20, 2022 | Sep 21, 2022 | - | Closed | Project RelatedGGS151 | Mayur Sharma | Harish Nagar | BUG | Solar Mode | Modified Implementation | Firmware | 2022-09-21 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU SVN_version44 GGS151_3KW_MPPT_PCU_R2.elf.S | 2022-09-21 - SVN Repository FW_17801 - Inverter_Firmware - Projects - GGS151_3KW_MPPT_PCU SVN_version45 GGS151_3KW_MPPT_PCU_R3.elf.S | Functional | Fixed |  | 0 | 0
193 | Sep 15, 2022 | Project Objective and Scope not identify in project definition | Project Description should have objective and clearly mention scope | Ein-fream | Sep 20, 2022 | Sep 21, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Sobhag Prajapat | Syojiram Sharma | BUG | Documentation | Modified Implementation | Testing | 2022-09-21 - during plan review by reviewer. | 2022-09-21 - Objective and Scope defined in project | Non Functional | Fixed | 0 | 0 | 0
194 | Sep 15, 2022 | effort estimation must be match project efforts | need to optimize the plan to match the effort | ein frame project plan effort | Sep 20, 2022 | Sep 21, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Sobhag Prajapat | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-21 - project efforts are modified as per effort estimation . | 2022-09-21 - project efforts are modified as per effort estimation | Non Functional | Fixed | 0 | 0 | 0
195 | Sep 15, 2022 | Tool in testing phase not available | Tools need to add in each testing related task | Ein Frame - Project task OBH012 | Sep 20, 2022 | Sep 21, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Sobhag Prajapat | Syojiram Sharma | BUG | Reliability | Modified Implementation | Systems Engineering | 2022-09-21 - All required measurement tool added in all testing stage of plan | 2022-09-21 - All required measurement tool added in all testing stage of plan | Non Functional | Fixed | 0 | 0 | 0
196 | Sep 22, 2022 | At need id 7 there should be constraint that Input AC supply is of 50Hz supply. | Functional specification review need id 7 | SVN repositories\HKVA_inv\GNE114 Rev.3 | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGNE114 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Systems Engineering | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.3 | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.4 | Non Functional | Fixed | 0 | 0 | 0
197 | Sep 22, 2022 | In need id 10 LCD size should be as constraint due to chassis and front facia as well as availability context. | Functional specification review need id 10 | SVN repositories\HKVA_inv\GNE114 Rev.3 | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGNE114 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Systems Engineering | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.3 | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.4 | Functional | Fixed | 0 | 0 | 0
198 | Sep 22, 2022 | In need id 12 there should be constraint that manual by-pass will be given as cost and complexity are constraints, to more clear. | Functional specification review need id 12 | SVN repositories\HKVA_inv\GNE114 Rev.3 | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGNE114 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Systems Engineering | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.3 | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.4 | Non Functional | Fixed | 0 | 0 | 0
199 | Sep 22, 2022 | In need id 17, the BOM cost considered very high, re-confirmation from customer should require. | Functional specification review need id 17 | SVN repositories\HKVA_inv\GNE114 Rev.3 | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGNE114 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Systems Engineering | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.3 | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.4 | Observation | Fixed | 0 | 0 | 0
200 | Sep 22, 2022 | There were no need statements found regarding Testability and Transportation. That should also cover. | Functional specification review : Points to consider when identifying needs | SVN repositories\HKVA_inv\GNE114 Rev.3 | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGNE114 | Sobhag Prajapat | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Systems Engineering | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.3 | 2022-09-22 - SVN repositories\HKVA_inv\GNE114 Rev.4 | Functional | Fixed | 0 | 0 | 0
201 | Sep 21, 2022 | MOM- kick off shall concerned about project basic requirements, action items are not discussed in further meetings as per MOM | GGE289_MINMET, action items | GGE289_MINMET | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | BUG | Charging Profile | New Implementation | Project Management | 2022-09-22 - it is found in current version of MOM. which is lying in project repository dated 22 sep 22 15:40PM | 2022-09-22 - No need to fix the problem so version will not change. | Observation | Fixed | 0 | 0 | 0
202 | Sep 21, 2022 | no findings are observed for RTT review in incident log. | no log for RTT review | RTT review incident | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | BUG | Charging Profile | New Implementation | Systems Engineering | 2022-09-22 - found in EIN frame --> defect logs | 2022-09-22 - no need to fix. Same EIN frame --> defect logs | Observation | Fixed | 0 | 0 | 0
203 | Sep 21, 2022 | sequence of project task- validation defect closure (1615) BOM finalization (1618) shall come before validation phase end, | project task sequence | project task sequence | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | BUG | Charging Profile | Modified Implementation | Project Management | 2022-09-22 - EIN frame:- Sep 20, 2022 12:08:25 (UTC) | 2022-09-22 - EIN frame:- Sep 22, 2022 11:07:15 (UTC) | Non Functional | Fixed | 0 | 0 | 0
204 | Sep 22, 2022 | CM plan, Plan review checklist, reviewer time sheet, review defect log are not available at project site but on a local computer. | plan review documents missed at SVN | plan review | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - CM plan, Plan review checklist, reviewer time sheet, review defect log are not available at project site updated | Non Functional | Fixed | 0 | 0 | 0
205 | Sep 22, 2022 | FS review checklist, defect log for FS& RTT review are not available at project site. | FS & RTT review logs | FS& RTT | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - FS review checklist, defect log & RTT review are updated on svn | Non Functional | Fixed | 0 | 0 | 0
206 | Sep 22, 2022 | measurement goals of schedule variance are conflicting in project plan and MOM | schedule variance mismatch | SV mismatch | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | Modified Implementation | Testing | 2022-09-24 - Project published - plan updated after plan review issue resolve Sep 21, 2022 07:07:18 (UTC) | 2022-09-24 - Updated schedule variance instead of measurement goals in project description. | Non Functional | Fixed | 0 | 0 | 0
207 | Sep 22, 2022 | manage mails at separate folder "MAILS" instead of keeping them separately in individual folder | management of mails in separate folder | mails management | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - managed mails at separate folder "MAILS" | Observation | Fixed | 0 | 0 | 0
208 | Sep 22, 2022 | In test case id PRT_9, the IP20 enclosure checking expected result not mentioned. | System test case review against need id 7.01 | draft version of system test cases | Sep 22, 2022 | Sep 23, 2022 | - | Closed | Project RelatedGGS151 | Jalaj Mathur | Vikash Sharma | BUG | Protections | Modified Implementation | Mechanical | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW/Testing/GGS151_SYSCAS.xlsx REV_60 | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW/Testing/GGS151_SYSCAS.xlsxREV_63 | Functional | Fixed | 0 | 0 | 0
209 | Sep 22, 2022 | sequence of project task- validation defect closure (1592) BOM finalization (1596) shall come before validation phase end, | project task sequence | project task sequence | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - In project plan, sequence of project task updated - | Non Functional | Fixed | 0 | 0 | 0
210 | Sep 22, 2022 | MINMET-project name has typing error kick off meeting, no action item is addressed in action items sheet, nor discussed in later meetings | team meetings, kick off meeting | MINMET | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - MINMET-project name has typing error kick off meeting corrected. | Non Functional | Fixed | 0 | 0 | 0
211 | Sep 22, 2022 | effort estimation task shall include all relevant core team members | effort estimation members | members in effort estimation | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolvesSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - included relevant team member in effort estimation task in project plan. | Observation | Fixed | 0 | 0 | 0
212 | Sep 22, 2022 | Against need id 9.02 there are not any test cases. | System test case review against baselined FS | draft version of system test cases | Sep 22, 2022 | Sep 23, 2022 | - | Closed | Project RelatedGGS151 | Jalaj Mathur | Vikash Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW/Testing/GGS151_SYSCAS.xlsx REV_60 | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW/Testing/GGS151_SYSCAS.xlsx REV_63 | Functional | Fixed | 0 | 0 | 0
213 | Sep 24, 2022 | no defect is logged for RTT review. | incident of no finding of RTT review | incident RTT review | Sep 24, 2022 | - | 10 Days | Open | Project RelatedGNE114 | Shweta Aggarwal | Chandrashekhar Sharma | - | - | - | - | null | null | Observation
214 | Sep 24, 2022 | FS review checklist is not updated at SVN server | FS review checklist at SVN | FS review checklist not available | Sep 24, 2022 | Nov 01, 2022 | - | Closed | Project RelatedGNE114 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-10-01 - http://10.141.1.9:8080/svn/HKVA_inv/GNE114/RD%20Phase/ | 2022-10-01 - http://10.141.1.9:8080/svn/HKVA_inv/GNE114/RD%20Phase/ | Non Functional | Fixed | 0 | 0 | 0
215 | Sep 23, 2022 | charging profile points are not described properly. | Please describe full charging profile points. | GGE289_FRWDSN SVN_Rev=51 | Sep 24, 2022 | Sep 24, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Abhishek Gupta | Harish Nagar | BUG | Documentation | Modified Implementation | Firmware | 2022-09-24 - GGE289_FRWDSN SVN_Rev=51 | 2022-09-24 - GGE289_FRWDSN SVN_Rev=52 | Observation | Fixed |  | 0 | 0
216 | Sep 26, 2022 | efficiency related id for module 2 not mapped in RTT | During RTT verification. | Revision 59 of dc dc converter. | Sep 26, 2022 | Sep 26, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Syojiram Sharma | Sobhag Prajapat | BUG | Reliability | 3rd Party Component | Hardware | 2022-09-26 - During review of design document and mapped RTT | 2022-09-26 - RTT updated in Revision 61 | Non Functional | Fixed | 0 | 0 | 0
217 | Sep 23, 2022 | integration test case not mapped with RTT. and author name is missing | During Integration test case review | Integration test case of GGE289 | Sep 26, 2022 | Sep 24, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Sobhag Prajapat | Mahesh Joshi | BUG | Documentation | Modified Implementation | Testing | 2022-09-29 - SVN GGE289_INTCAS(23-09-2022) | 2022-09-29 - SVN GGE289_INTCAS(24-09-2022) | Non Functional | By Design, Won't Fix |  | 0 | 0
218 | Sep 10, 2022 | output voltage tolerance must be +_/- with narrow band to maintain the 9A | need to update the output voltage tolerance limite | functional specification | Sep 26, 2022 | Sep 26, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Sobhag Prajapat | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Testing | 2022-09-30 - output voltage tolerance maintain 2 20V+/- 2% for output current maintain 9A | 2022-09-30 - output voltage tolerance maintain 2 20V+/- 2% for output current maintain 9A | Non Functional | Fixed | 0 | 0 | 0
219 | Sep 26, 2022 | Driver card related module missing in design document | need to add driver design in document | Design document of OBH012 | Sep 28, 2022 | Sep 28, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Sobhag Prajapat | Syojiram Sharma | BUG | Reliability | 3rd Party Component | Testing | 2022-09-30 - Driver module designing documents updated in design document | 2022-09-30 - Driver module designing documents updated in design document | Non Functional | Fixed | 0 | 0 | 0
220 | Sep 30, 2022 | BOM cost as measurement goal mentioned 18K +/- 10%, which not matched with baselined FS, in which 14K mentioned. | Description box of Project | Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | Sep 30, 2022 | Oct 01, 2022 | - | Closed | Project RelatedGNE114 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Documentation | Modified Implementation | Systems Engineering | 2022-10-01 - Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | 2022-10-01 - Oct 01, 2022 03:42:02 (UTC) | Functional | Fixed | 0 | 0 | 0
221 | Sep 30, 2022 | PROJECT FINANCIALS not mentioned | Overview page of project | Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | Sep 30, 2022 | Oct 01, 2022 | - | Closed | Project RelatedGNE114 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Documentation | Modified Implementation | Project Management | 2022-10-01 - Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | 2022-10-01 - Einframe --> Project GNE114 (Oct 01, 2022 04:07:12 (UTC)) | Observation | Fixed | 0 | 0 | 0
222 | Sep 30, 2022 | Module teste cases preparation merged with module testing tasks, create confusion, looks skip the task. | Project GNE114 tasks list. | Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | Sep 30, 2022 | Oct 01, 2022 | - | Closed | Project RelatedGNE114 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Documentation | Modified Implementation | Project Management | 2022-10-01 - Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | 2022-10-01 - Einframe --> Project GNE114 Oct 01, 2022 03:53:23 (UTC) | Observation | Fixed | 0 | 0 | 0
223 | Sep 30, 2022 | Integration design doc preparation merged with integration tasks, create confusion, looks skip the task. | Project GNE114 tasks list | Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | Sep 30, 2022 | Oct 01, 2022 | - | Closed | Project RelatedGNE114 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Documentation | Modified Implementation | Project Management | 2022-10-01 - Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | 2022-10-01 - Einframe --> Project GNE114 (Oct 01, 2022 03:52:22 (UTC)) | Observation | Fixed | 0 | 0 | 0
224 | Sep 30, 2022 | Integration testing and validation running parallel as per schedule shows, while as you affirmed that only system test cases will made parallelly, So that particular task look too big. Either separate that or squeeze that. | Project GNE114 Tasks list | Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | Sep 30, 2022 | Oct 01, 2022 | - | Closed | Project RelatedGNE114 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Documentation | Modified Implementation | Project Management | 2022-10-01 - Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | 2022-10-01 - Einframe --> Project GNE114 (Oct 01, 2022 04:07:12 (UTC)) | Functional | Fixed | 0 | 0 | 0
225 | Sep 30, 2022 | Start gate not approved yet, looks project not approved for start, while it actually started. | Gate review of project GNE114 | Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | Sep 30, 2022 | Oct 01, 2022 | - | Closed | Project RelatedGNE114 | Jalaj Mathur | Chandrashekhar Sharma | BUG | Documentation | Modified Implementation | Project Management | 2022-10-01 - Einframe --> Project GNE114 (Sep 28, 2022 01:05:13 (UTC)) | 2022-10-01 - Einframe --> Project GNE114 (Oct 01, 2022 05:11:47 (UTC)) | Non Functional | Fixed | 0 | 0 | 0
226 | Oct 27, 2022 | THD is not under specs | Back up on and mix load should run on inverter output | Backout_3 in validation test | Oct 01, 2022 | - | 3 Days | Open | Project RelatedGGS151 | Vikash Sharma | Harish Nagar | - | - | - | - | null | null | Observation
227 | Oct 01, 2022 | Final version of few documents are not available at SVN server, HDWDSN, RTT | HDWDSN, RTT not updated at SVN | SNV server | Oct 01, 2022 | - | 2 Days | Open | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | - | - | - | - | null | null | Non Functional
228 | Oct 01, 2022 | If no defect is found, same shall be logged in incident management for better understanding. | incident management- review- no defects | incident management- review- no defects | Oct 01, 2022 | - | 2 Days | Open | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | - | - | - | - | null | null | Observation
229 | Oct 01, 2022 | baseline can be mentioned while actually baselining documents, example: design documents, RTT, | use baseline word in baselining artefacts | use baseline word in baselining artefacts | Oct 01, 2022 | - | 2 Days | Open | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | - | - | - | - | null | null | Observation