## QMS_Next Change Requirement (2
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev.
1 | Validation plan not clearly mention, which type of validation we are performing. It should be clearly mentioned that whether it is Internal validation or external validation. | Process Improvement Log | Rejected |  |  | As in each project it is not mandatory to perform internal and external vaildation. The choice is dependent upon Project's team.
2 | Action item tracking difficulty in action item sheet, add action item detection date, and actual completion date | Process Improvement Log | Postponed | TMPL_MINMET | Small | Need to analyse on more projects and then implement accordingly.
3 | Audit checklist should contain similar points nearer to ease filling. Checklist points should be categorized on basis of similarity. | Process Improvement Log | Rejected |  |  | As new checkpoints will always be added at the end of list, so there is no significance in collecting the relative checkpoints at same place. Although Process area wise points are already placed together.
4 | There is no defined template for analysis of Verification and Validation defects. We can add a template (Excel Format) which pulls defects' data from Logs project wise and then we analyse the defects. | Process Improvement Log | Postponed | New Template or Tool | Large | Need to analyse methods being followed in projects and then implement accordingly.
5 | Tool Measurement: As this tool use to calculate density of defects and by dividing total number of defects by total expended person hours, but this not clear the total picture, as defects depends upon many thing also such as complexity of project, persons experience, etc. So analysis of defect density not easy if we use this tool and procedure. Some other concept need to calculate defect density, so that actual picture come. | Process Improvement Log | Postponed | PRCD_MEASUR TOOL_MEASUR | Large | Need to analyse on more projects and then implement accordingly.
6 | There is no particular format of the version history sheet maintained by the project managers The version history sheet used for the version tracking of the documents on the server repository processdoc should be made as a template &amp; it should contain the path column also so that the exact path of the folder to which the file belongs can be tracked | Process Improvement Log | Postponed | New Template | Large | Need to discuss and create a template and folder structures on Processdrive for Projects' data
7 | CHKL_AUDITT Validation and closure Missing checkpoint regarding defect analysis. checkpoint should be added about defect analysis. | Process Improvement Log | Accepted | CHKL_AUDITT | Small | These points will be added in checklist
8 | TMPL_BKPPLN doesn't contains the Plan applicable period. | Process Improvement Log | Accepted | TMPL_BKPPLN | Small | This field will be added in plan template
9 | There is no specific way for the user to apply for restoration of data to the configuration manager. There should be a template for request for data restoration which should contain all the required data for the restoration purpose | Process Improvement Log | Postponed | New Template | Medium | Need to create a new template if it will be required.
10 | In Pending Action Sheet of the TMPL_MINMET there is no complete information There should be a column of Action Item Identified Date &amp; Separate Column for Actual Date of Completion of Action Item., also there should be a column of Assigned Responsibility To, for the action item. It will help to better track the action items. | Process Improvement Log | Accepted | TMPL_MINMET | Small | Field will be added in template
11 | There should be valid sources of requirements | Process Improvement Log | Accepted | TMPL_FUNSPC | Small | Source coloumn will be added in template
12 | Closure audit and Configuration audit are different, there should be a different closure procedure | Process Improvement Log | Accepted | PRCD_CONFIG | Small | Will add configuration audit section in procedure
13 | Definiion of product support documentation | Process Improvement Log | Accepted | PRCD_IMPINT | Small | Definition / details will add for user support docs in procedure of implementation
Points to Cover in Training
1
2
3

## Revision History
Genus Innovation Limited
Template Version -1

## Instructions for Use
Instructions for Use

## QMS_1.3 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev.
1 | Condcut Kick-off meetimg in two parts: Part 1: General kick-off for intimation to team about project Part 2: Technical kick-off for requirements capture | IR - 1 | Accepted | PRCD_PRJPLN | Small |  | 151
2 | CI type should be managed and controlled for Project Plan, MPP type should be controlled. | Process Improvement Log | Accepted | MSTL_CMLIST, PRCD_CONFIG | Small | MPP type chnaged from baselined to controlled, but project plan will be baselined | 169
3 | Review Checklist for Senior management review which shuold include all agendas (Milestone review, PEG Review, QA Review etc.) | Process Improvement Log | Accepted | MSTL_CMLIST, PRCD_PRJMAC | Large | Add new Template for Checklist | 164, 166,167
4 | Project code selection at one sheet in measurement tool, Graph input data should be modified for range | Process Improvement Log | Accepted | TOOL_MEASUR | Medium |  | 152
5 | VER/ VAL sec. of RTT: Id's for different type of testing should be differentiable | Process Improvement Log | Accepted | TMPL_REQTRT | Small | It can be done by changing the VER/VAL to Testing--> Module ¦ Integration ¦Validation | 153
6 | Audit schedule template should contain actual start date and actual finish date instead of actual date | Process Improvement Log | Accepted | TMPL_ADTSCH | Small |  | 155
7 | Review Plan Sec. in project plan should be modified | IR-1 | Accepted | TMPL_PRJPLN | Medium | It can be done in tabular format as: Work Product ¦ Review type (Peer/SME)¦Frequency (Peer/SME) | 154
8 | There should be zero '0' efforts for no complexity in estimation templates | Process Improvement Log | Accepted | TMPL_ESTFRW, TMPL_ESTMCH, TMPL_ESTHDW, TMPL_ESTFNL | Medium |  | 168
9 | In audit checklist add a point has the approved project plan mailed to relevant stakeholders? | Process Improvement Log | Accepted | CHKL_AUDITT | Small |  | 156
10 | In PRCD_CONFIG naming convention of Audit plan should as for whole year eg. QA Genus 2015-16 | Process Improvement Log | Accepted | PRCD_CONFIG | Small |  | 157
11 | CHKL_PLNREV.xlsx - S. No. 7 SDLC should PDLC | Process Improvement Log | Accepted | CHKL_PLNREV | Small |  | 158
12 | Closure should be included in Project lifecycle (Make Release to Release and Closure) | Process Improvement Log | Accepted | GDLN_TAILOR | Small |  | 159
13 | List of CI in project plan should be maintained in separate excel file so that It can be managed and tracked easily during audit. | Process Improvement Log | Rejected | TMPL_PRJPLN | Medium
14 | Add category and sub-category description of risk in risk list | Process Improvement Log | Postpone | INFO_RSKLST | Medium
15 | Audit activity time should be considered in Overheads | Process Improvement Log | Rejected | TOOL_MEASUR, Timesheet entities | Medium | Changes may also be done in procedures
16 | RPN should be calculated automaticallyin risk matrix, drop down not coming in source column of risk matrix table | Process Improvement Log | Accepted | TMPL_RSKMTX | Small |  | 162
17 | Decision, action item and issue item should be sepearte in minutes of meeting | Process Improvement Log | Rejected | TMPL_MINMET | Small
18 | There should be some provision for project data back up testing and retrival | Process Improvement Log | Accepted | PRCD_PRJMAC | Small | Changes may also be done in procedures | 160
19 | Audit check list should be categorized in accoradane with project lifecycle. | Process Improvement Log | Accepted | CHKL_AUDITT | Large |  | 165
20 | Data back up restoration plan (sec. of project plan) should not include table, as this plan would always be inline with org. level back up and restoration plan | Process Improvement Log | Rejected | TMPL_PRJPLN | Small
21 | Audit checklist (Planning) should not include point 13 and 14, as these are already being checked in plan review checklist | Process Improvement Log | Accepted | CHKL_AUDITT | Small |  | 156
22 | In Project plan "Help text" is only for support so it must be (not may be) deleted after plan preparation | Process Improvement Log | Rejected | TMPL_PRJPLN | Small
23 | Remove the name of reviewer from review plan (sec. of project plan), as reviewer may change at the time time of review which conflicts with plan | Process Improvement Log | Accepted | TMPL_PRJPLN | Small |  | 154
24 | CHKL_AUDITT Sheet - Initiation & RD-RM PMC Point 3 Point 4 should not be there (Because Milestone Review is done after Audit, There is no point of Measurement Report Audit | Process Improvement Log | Accepted | CHKL_AUDITT | Small |  | 165
25 | Add Following check points Are the Backups made regularly as per defined schedule? Are All the Backup Items are there in the Plan | Process Improvement Log | Accepted | CHKL_ITAUDT | Small |  | 171

## QMS_2.0 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev.
1 | TMPL_PRJPLN Roles & Responsibility Matrix Point 15 position is not appropriate as it needs to scroll down to the last. Position should be there after the work environment Plan Point No. 4 | Process Improvement Log | Rejected | TMPL_PRJPLN | Small | R&R is potentially volatile, so it should be at the bottom due to CM considerations
2 | Point No. 7 Resource Plan position is not appropriate. It should come after the Point 4 Work Environment | Process Improvement Log | Rejected | TMPL_PRJPLN | Small
3 | TMPL_PRJPLN According to procedure in point 7. Resource Plan the phase column is missing. Add a Column in the Resource plan table with description phase | Process Improvement Log | Rejected | TMPL_PRJPLN | Small | Schedule in resource plan, involvement in R&R
4 | PRCD_PRJLN In above document point no. 28 Review and approve Project Plan. Use “Plan Review Checklist” (CHKL_PLNREV). Senior Management . It is not possible for senior management to fill checklist. Give the review with checklist option responsibility to PEER or other reviewer | Process Improvement Log | Accepted | PRCD_PRJPLN | Small | Project plan will be reviewed by either Peer or SME, after this it will be sent to Sr. Mgmt for review and approval | 191
5 | If a Document is not uploaded like MOM during Audit what is to be done. Audit should be stopped till the document is not uploaded as resolving of the active NC or the Audit should be completed and let the project manager to resolve the NC & then if any finding are there in the uploaded document then a new NC is to be logged. | Process Improvement Log | Rejected
6 | There is not any checklist for Firmware design review. CHKL_CODRVW includes checkpoints related to implemented code review only. Add another checklist for Firmware design review or add design related points in existing checklist i.e. CHKL_CODRVW | Process Improvement Log | Accepted |  | Medium |  | 206
7 | CHKL_TSTCAS is for test case review, there are various test cases i.e. Firmware, Hardware and Mechanical. These may conflict if we use same name for all test cases. Naming convention should be different if we use same test case review checklist. | Process Improvement Log | Rejected |  |  | CHKL_TSTCAS review will be used for ssytem test case review only.
8 | For such type of project no need of seprate integration phase (GGE055) | Process Improvement Log | Postponed
9 | Review chek list sheet. For peer and SME review checklist should be different. | Process Improvement Log | Rejected |  | Medium
10 | There is no column for Remarks in RTT. Remarks for "what type relation between the IDs". Add Remarks column in RTT | Process Improvement Log | Accepted |  | Small |  | 199
11 | Action item in milestone review should be traceable, if there is any condition should be mentioned | PEG | Accepted | PRCD_PRJMAC | Medium | Action item identified, will be traced through MOM so use of MOM added in Project monitoring and control procedure. | 192
12 | Release note should include principle changes | PEG | Accepted | TMPL_QMSREL | Small |  | 193
13 | Requirement template for process improvements (TMPL_QMSREQ) should include points to cover in training | PEG | Accepted | TMPL_QMSREQ | Small |  | 194
14 | There should be List of requirement providers, Sample Heads for requirements (needs) and INVEST Concept | PEG | Accepted | TMPL_FUNSPC | Small |  | 195
15 | Process to add, delete, update documents in PAL for future reference | PEG | Accepted |  | Medium |  | 202
16 | Process to modify the speed of change in QMS, Major/Minor version release guidelines | PEG | Accepted |  | Large |  | 202
17 | Organizational Training tool, training checklist needs to be relooked | Training coordinator | Accepted |  | Large |  | 203208
18 | Criteria for conducting configuratin audit should be mantioned in audit plan sec. of project plan | IR-2 | Accepted | TMPL_PRJPLN | Small |  | 201
19 | Review checklist for sr. mgmt review of PPQA group and PEG Group | IR-2 | Accepted |  | Medium |  | 203207
20 | Criiteria selected to perform audit analysis needs to be revisited. Categories in audit log can be in accordance with phases of project lifecycle. | IR-2 | Postponed | AUDIT LOG, TOOL_ADTRPT | Large | Now audit analysis should be done effectively, so now no need to change in Audit reporting tool
21 | Process to update the personnel datbase in organisation | PEG | Accepted | PRCD_TRAING | Medium |  | 200
Points to Cover in Training
1 | Guidelines to prepare functional specification, Change in Functional specification template
2 | Modifications in Training feedback assessment, Bugs fixed in Training tool
3 | Checklist added for Senior Management Review of PEG and PPQA Group
4 | Process for QMS Change Revised (It will be roll out on Pilot)
5 | Senior Management Review Plan, Audit plan and Review Plan sections of Project Plan template
6 | Modifications in checklist for Firmaware Review (CHKL_CODRVW)
7 | Process to Update Personnel database

## QMS_2.1 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev.
1 | The 'TMPL_REQTRT' at present has link to the need statement of FS which are not elaborated. So while planning/reviewing one needs to switch between different sheets. So 'TMPL_REQTRT'should include Elaboration along with need statement | Process Improvement Log | Accepted | TMPL_REQTRT | Small |  | 223
2 | Release plan is not in project plan,It should be in TMPL_PRJPLN | Process Improvement Log | Rejected | TMPL_PRJPLN | Medium | As release plan ia already included in CM plan sec.
3 | It is written that When one of PEG member is Project Manager, then tailoring request will approve / reject Dy. Head of PEG. But as per PEG plan there is no Dy. Head mentioned, only one head and 3 members mentioned. It should be such that PEG as team will take care this proposals if any one member of PEG as project manage | Process Improvement Log | Accepted | PRCD_PRJPLN | Small |  | 224
4 | In Firmware effort estimation template, complexity not replicate in final estimation sheet. check in firmware estimation of GGS028 and GSM052. | Process Improvement Log | Accepted | TMPL_ESTFRW | Small |  | 221
5 | Risk log and tailoring log not available. Both log should be available on share point other wise remove the risk log section from TMP_CLOSRE | Process Improvement Log | Accepted | TMPL_CLOSRE | Small |  | 225
6 | At present Customer/Requesting department/Need gathering does not get specifically introduced in Project Plan. There should be two fields i.e. 1. Need Source- To specify whether need is from customer or own design improvement or any feedback from Servicing, Marketing etc. 2. Target Customer | Process Improvement Log | Accepted | TMPL_PRJPLN | Small |  | 226
7 | TMPL_MINMET Their no option of segregation of Team Meeting to which phase the team meeting belongs | Process Improvement Log | Accepted | TMPL_MINMET | Small |  | 222
Points to Cover in Training
1 | Project's phase added in TMPL_MINMET
2 | Elaboration column added in RTT sheet
3 | Project Information section in Project Plan template

## QMS_2.2 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev.
1 | There should a mechanism for tracking the negative efforts logging and overlapping of efforts in timesheets. | Process Improvement Log | Accepted | TOOL_MEASUR | Large |  | 237
2 | There are conflicts whether only completed Project plan is to be reviewed or individual plans (e.g. Measurement Plan, CM Plan etc.) are to be reviewed as and when they are made by the assigned person. Please clearly define review requirements in Procedure_Project Plan. | Process Improvement Log | Postponed | PRCD_PRJPLN | Medium
3 | Procedure does not clearly mention Whether review and approval of SM is required once in a year or everytime when a Major version of QMS is released. Please clearify in procedure | Process Improvement Log | Rejected | PRCD_ORGFCS
4 | As per Current Practice Access Rights for Work products to be used in RD phase gets introduced in Planning Phase. So how to know access rights during RD Phase. Either access rights for Work Products which are to be used in RD Phase should be universally defined in Procedure_REQDEV or Preliminary planning should include CM Plan. | Process Improvement Log | Postponed | PRCD_REQDEV, PRCD_CONFIG,TMPL_PRJPLN | Medium
5 | Functional Specifications should include a field for Brief dscription of project | Internal review | Accepted | TMPL_FUNSPC | Small |  | 239
6 | Lifecycle distribution needs to be revised in Size/Effort estimation templates | Projects' metrices review | Postponed | TMPL_EFTFRW, TMPL_ESTHDW, TMPL_ESTMCH, TMPL_ESTFNL | Large
7 | In Firmware Design Document Template field to mention module tests is not available. Please add field for testing | Process Improvement Log | Rejected
8 | At present if phases specific tailoring (e.g. merging phases) are taken in any project then still those phases do not get merged on share point Any phase merging or other tailoring should also get reflected on Sharepoint, if possible. As it will make effort calculations, Logs, Measurements more accurate. | Process Improvement Log | Rejected
9 | TMPL_PQARVW Naming convention of TMPL_PQARVW is not found in configuration procedure. suggested naming convention for TMPL_PQARVW is QA_XXX-YY_PQARVW. where XXX represents initial for month and YY represents last two digits of current year | Process Improvement Log | Accepted | PRCD_CONFIG | Small |  | 248
10 | It require validation report number whereas in validation report template there is no option to put number. Either remove this point from release note or give option in validation report to write number. | Process Improvement Log | Accepted | TMPL_VALRPT | Small |  | 243
11 | As any testcase document go through following 3 stages: 1. Creation of test Cases 2. Review 3. Testing Test case document heading should include space for mentioning- 1. Created By Creation Date 2. Reviewd By Review Date 3. Tested By Tested on | Process Improvement Log | Accepted | All test case templates | Medium | Accepted in next QMS 2.3
12 | in guideline of Hardware effort estimation PCB layout complexity not fulfill definition of high and medium complexity. It should be interchanged | Process Improvement Log | Postponed | GDLN_ESTMAT
13 | In this template no any guideline or elaboration for Identify Test Schedule and Test Environment for validation. There must be guideline which help to identify test type like environmental test,humming test etc. | Process Improvement Log | Postponed | TMPL_SYSCAS | Medium
14 | Which type of date format will be use in date column : DD/MM/YYYY or MM/DD/YYYY . it make confuse for every one because at share point we use date in MM/DD/YYYY but generally we write date in DD/MM/YYYY format. In document date format is DD_Month name in short _YYYY. as Exam. - 02 JAN 2016 | Process Improvement Log | Rejected
15 | In our project we are taking maximum number of tested module so no need of module test ID in RTT ; our hardware and firmware modules are dependent on each other, so practically not possible to test each module with dummy firmware. practically we are testing after integration. Remove the Module test ID from RTT | Process Improvement Log | Rejected
16 | Point No. 24 Capture the lessons learnt and best practices and submit them to the Process Engineering Group (PEG) using “Process Improvement Proposals Database”is wrong. It should be as Point No. 24 Capture the lessons learnt and best practices and submit them to the Process Engineering Group (PEG) using “Project Learnings” log | Process Improvement Log | Accepted | PRCD_PRJMAC | Small |  | 241
17 | In Project Plan Document the schedule dates in any plan should not be there as it is very problematic to update them in project plan document if the schedule changes due to any reason Plan dates are already taken in MPP, so there is no need of giving them elsewhere | Process Improvement Log | Rejected |  | Small
18 | Point 25 of procedure says Document defects in “Validation and Testing Log. Please replace it with Review and Testing Defect Log | Process Improvement Log | Accepted | PRCD_IMPINT | Small |  | 240
19 | when Designer Fill RTT of Design Document and relate Need ID with module design, that is consume more efforts. In module design section of design document should have related need ID. that help to designer to full RTT. | Process Improvement Log | Rejected
20 | Process Quality Assurance first requirement of QA personnel "Be a regular employee of the organization, with experience within the development projects that will be served by the PEG Members", seems inappropriate. language should be corrected. | Process Improvement Log | Postponed | GDLN_TEAMNG | Medium
21 | TMPL_MINMET Agenda for PPQA team meeting is not available in instruction for use add below agenda in TMPL_MINMET 1. PPQA Objectives 2. Audit activities monitoring 3. Team pain points 4. Audit log status 5. Measurement of last month ADTRPT | Process Improvement Log | Accepted | TMPL_MINMET | Small |  | 245
22 | footer at pg 1 quality Assurance plan template has been migrated from an MS Excel based template to a MS Word based template, and hence the version numbers 1 and 2 cannot be traced using the version control tool. See prior releases of the QMS for the same; seems inappropriate in this ADTPLN context. this should be removed. | Process Improvement Log | Accepted | TMPL_ADTPLN | Small |  | 247
23 | Escalation plan is not available in template audit plan. Add escalation plan and also some small note to be removed. make it as per mailed template. | Process Improvement Log | Accepted | TMPL_ADTPLN | Small |  | 247
24 | associated documents should be mentioned in PRCD_CONFIG. As of now only for ADTPLN & ADTSCH is mentioned in PRCD_CONFIG.(MOM pending) Also sr. mgmt. review checklist to be inserted in PRCD_CONFIG. mention rename all QA associated documents to be renamed like ADTPLN and add about sr. mgmt. review checklist. | Process Improvement Log | Accepted | PRCD_CONFIG | Medium |  | 248
25 | Baseline start and finish dates are missing in current audit schedule template. add baseline start and finish dates (as per mailed TMPL_ADTSCH) | Process Improvement Log | Accepted | TMPL_ADTSCH | Small |  | 246
Points to Cover in Training
1 | Modifications in Measurement tool to track overlapped and negative efforts
2 | Brief description to be added in FS template
3 | Naming conventions changed for support group activities artefacts

## QMS_2.3 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev.
1 | Phase wise details of NC can't be seen as on date, Explore possibility to check project then phase wise details of NCs, if possible. | Process Improvement Log | Postponed | Audit NC Log on SharePoint, TOOL_ADTRPT | Medium | Need to change in audit log, analyse its impact in old data.
2 | There should be naming convention oprtion for Implementation artefacts in Project Plan, so that there traceability in RTT can be umambiguous | Audit/PPQA Team | Accepted | TMPL_PRJPLN | Small |  | 255
3 | There should be mechanism for Trainer's feedback collection in process. | Training Coordinator | Accepted |  | Large | Need to create a template for Trainer's Feedback collection | 256
4 | As any testcase document go through following 3 stages: 1. Creation of test Cases 2. Review 3. Testing Test case document heading should include space for mentioning- 1. Created By Creation Date 2. Reviewd By Review Date 3. Tested By Tested on | Process Improvement Log | Accepted | All test case templates | Medium |  | 258
5 | Monthly training calendar or Plan format is older format.Please update it. | Process Improvement Log | Accepted | Monthly Training Calendar | Medium |  | 256
6 | Attendance sheet template, feedback form template does not exist in QMS. Please add the attendance sheet template, Feedback form template in Process and also describe their reference in Training procedure. | Process Improvement Log | Accepted | PRCD_TRAING | Medium |  | 256
7 | Base measure for Product's Defect Density written in measurement procedure needs to be corrected as actual. Correct it as functional defects found in review, testins and validation. | Internal Review by PEG | Accepted | PRCD_MEASUR | Small |  | 257
Points to Cover in Training
1 | Naming for Implementation artefacts to be added in CM plan sec. of Project Plan
2 | Templates for attendance sheet and feebcak forms of training added.
3 | Existing Date field modified as 'date of preparation' and 'date of testing' field added in testing templates

## QMS_2.4 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev.
1 | Validation plan not clearly mention, which type of validation we are performing. It should be clearly mentioned that whether it is Internal validation or external validation. | Process Improvement Log | Rejected |  |  | As in each project it is not mandatory to perform internal and external vaildation. The choice is dependent upon Project's team.
2 | Action item tracking difficulty in action item sheet, add action item detection date, and actual completion date | Process Improvement Log | Postponed | TMPL_MINMET | Small | Need to analyse on more projects and then implement accordingly.
3 | Audit checklist should contain similar points nearer to ease filling. Checklist points should be categorized on basis of similarity. | Process Improvement Log | Rejected |  |  | As new checkpoints will always be added at the end of list, so there is no significance in collecting the relative checkpoints at same place. Although Process area wise points are already placed together.
4 | There is no defined template for analysis of Verification and Validation defects. We can add a template (Excel Format) which pulls defects' data from Logs project wise and then we analyse the defects. | Process Improvement Log | Postponed | New Template or Tool | Large | Need to analyse methods being followed in projects and then implement accordingly.
5 | Tool Measurement: As this tool use to calculate density of defects and by dividing total number of defects by total expended person hours, but this not clear the total picture, as defects depends upon many thing also such as complexity of project, persons experience, etc. So analysis of defect density not easy if we use this tool and procedure. Some other concept need to calculate defect density, so that actual picture come. | Process Improvement Log | Postponed | PRCD_MEASUR TOOL_MEASUR | Large | Need to analyse on more projects and then implement accordingly.
6 | There is no particular format of the version history sheet maintained by the project managers The version history sheet used for the version tracking of the documents on the server repository processdoc should be made as a template &amp; it should contain the path column also so that the exact path of the folder to which the file belongs can be tracked | Process Improvement Log | Postponed | New Template | Large | Need to discuss and create a template and folder structures on Processdrive for Projects' data
7 | CHKL_AUDITT Validation and closure Missing checkpoint regarding defect analysis. checkpoint should be added about defect analysis. | Process Improvement Log | Postponed | CHKL_AUDITT | Small | These points will be added in checklist
8 | TMPL_BKPPLN doesn't contains the Plan applicable period. | Process Improvement Log | Postponed | TMPL_BKPPLN | Small | This field will be added in plan template
9 | There is no specific way for the user to apply for restoration of data to the configuration manager. There should be a template for request for data restoration which should contain all the required data for the restoration purpose | Process Improvement Log | Postponed | New Template | Medium | Need to create a new template if it will be required.
10 | In Pending Action Sheet of the TMPL_MINMET there is no complete information There should be a column of Action Item Identified Date &amp; Separate Column for Actual Date of Completion of Action Item., also there should be a column of Assigned Responsibility To, for the action item. It will help to better track the action items. | Process Improvement Log | Postponed | TMPL_MINMET | Small | Field will be added in template
11 | There should be valid sources of requirements | Process Improvement Log | Accepted | TMPL_FUNSPC | Small | Source coloumn will be added in template | 306
12 | Absentee should be mention in MOM | SCAMPI findings | Accepted | TMPL_MINMET | Small | One row add to mention Absentee | 298
13 | Assumptions and dependencies also trigger for Risks identification | SCAMPI findings | Accepted | TMPL_RSKMTX | Small | Key assumptions, Constraints and dependencies section will add in Risk matrix template | 299
14 | Varriancies upto phase also require to show | SCAMPI findings | Accepted | TOOL_MESURE | Medium | Incorporated and formulas accordingly updated | 300
15 | The project metrics report should also share with relevant stackholders | SCAMPI findings | Accepted | PRCD_MEASUR | Small | Mentioned in procedure | 301
16 | The details of QMS changes also in QMS release note | SCAMPI findings | Accepted | TMPL_QMSREL | Small | Deployment criteria section mentioned in template | 304
17 | There should be centralised concept of tailoring | SCAMPI findings | Accepted | PRCD_ORGFCS | Small | Tailoring google form and centralised excell sheet introduced | 305
18 | Critical to quality should be mention during design | SCAMPI findings | Accepted | TMPL_INTDSN | Medium | CTQ section mentioned in design document template | 307
19 | Design / alternate soultion identification guidline need more effective | SCAMPI findings | Accepted | TMPL_DESIGN | Medium | Guidelines updated | 308
Points to Cover in Training
1 | Varriances phase wise understanding
2 | Tailoring google form uses understanding
3 | CTQ understanding
4 | Risk matrix triggers as assumptions, constraints and dependencies understanding

## QMS_3.0 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev. | Impact on Projects
1 | Action item tracking difficulty in action item sheet, add action item detection date, and actual completion date | Process Improvement Log | Accepted | TMPL_MINMET | Small | Need to analyse on more projects and then implement accordingly. | 322 | Minor
2 | There is no defined template for analysis of Verification and Validation defects. We can add a template (Excel Format) which pulls defects' data from Logs project wise and then we analyse the defects. | Process Improvement Log | Postponed | New Template or Tool | Large | Need to analyse methods being followed in projects and then implement accordingly.
3 | Tool Measurement: As this tool use to calculate density of defects and by dividing total number of defects by total expended person hours, but this not clear the total picture, as defects depends upon many thing also such as complexity of project, persons experience, etc. So analysis of defect density not easy if we use this tool and procedure. Some other concept need to calculate defect density, so that actual picture come. | Process Improvement Log | Postponed | PRCD_MEASUR TOOL_MEASUR | Large | Need to analyse on more projects and then implement accordingly.
4 | There is no particular format of the version history sheet maintained by the project managers The version history sheet used for the version tracking of the documents on the server repository processdoc should be made as a template &amp; it should contain the path column also so that the exact path of the folder to which the file belongs can be tracked | Process Improvement Log | Postponed | New Template | Large | Need to discuss and create a template and folder structures on Processdrive for Projects' data
2 | CHKL_AUDITT Validation and closure Missing checkpoint regarding defect analysis. checkpoint should be added about defect analysis. | Process Improvement Log | Accepted | CHKL_AUDITT | Small | These points will be added in checklist | 323 | Minor
3 | TMPL_BKPPLN doesn't contains the Plan applicable period. | Process Improvement Log | Accepted | TMPL_BKPPLN | Small | This field will be added in plan template | 346 | Minor
7 | There is no specific way for the user to apply for restoration of data to the configuration manager. There should be a template for request for data restoration which should contain all the required data for the restoration purpose | Process Improvement Log | Postponed | New Template | Medium | Need to create a new template if it will be required.
4 | In Pending Action Sheet of the TMPL_MINMET there is no complete information There should be a column of Action Item Identified Date &amp; Separate Column for Actual Date of Completion of Action Item., also there should be a column of Assigned Responsibility To, for the action item. It will help to better track the action items. | Process Improvement Log | Accepted | TMPL_MINMET | Small | Field will be added in template | 322 | Minor
9 | Closure audit and Configuration audit are different, there should be a different closure procedure | Process Improvement Log | Accepted | PRCD_CONFIG | Small | Will add configuration audit section in procedure
10 | Definiion of product support documentation | Process Improvement Log | Accepted | PRCD_IMPINT | Small | Definition / details will add for user support docs in procedure of implementation
11 | In PRCD_ESTMAT.docx input is written as Customer Requirements and Developed Requirements. | Process Improvement Log | Accepted | PRCD_ESTMAT | Small | In procedure of Estimation write Functional specifications as input.
5 | checkpoint should be added about defect analysis | Process Improvement Log | Accepted | CHKL_AUDITT | Small | Will add in Audit checklist | 323 | Minor
6 | The applicable period field for the plan should be there specified in the template so that scope period of the plan can be traced | Process Improvement Log | Accepted | TMPL_BKPLN | Small | Applicable period section will add in template | 346 | Minor
14 | Release sec. should be move to technical (validtaion procedure or separate release proecedure). | Process Improvement Log | Accepted | PRCD_CONFIG | Medium | Move to Validation procedure
15 | A List of all artefacts with their appropriate revision should be maintained separately in excel format in order to reduce the time & ambiguity in using the updated artefacts. This will also help in tracking the artefacts. | Process Improvement Log | Accepted | QMS | Large | Whole flow chart type will made for 4 processes
7 | Please fix the hrs for release & closure phase as I suggest it should require atleast on an average 8hrs, or you can provide different different life cycle distribution according to project types. | Process Improvement Log | Accepted | TMPL_ESTFNL | Medium | Will fix the hours for this phase | 347 | Minor
17 | In {PRCD_CONFIG_Section-Guidelines:Naming Convention} Following are missing from Naming Convention 1. TMPL_DARRSC 2. TMPL_MESRPT 3. Different Naming Conventions for same word {Measurement} is being used as TMPL_MESURE vs PRCD_MEASUR {Review} as REV V/s RVW (Audit} as AUDITT vs ADT {PPQA} as PPQA vs PQA 4. Similarly PRCD_RSKMGM V/s TMPL_RSKMTX both these could be same either RSKMGM or RSKMTX 5. TMPL_HDWDSN {Hardware=HDW} V/s TMPL_HWTCAS (Hardware=HW} TMPL_SYSCAS and TMPL_INTCAS {T=Test not Used here as like HWTCAS} as of now their are conflicts these could be inlined with each other. Similarly TMPL_FRWDSN V/s TMPL_FWTCAS and TMPL_MCHDSN V/s TMPL_MCTCAS | Process Improvement Log | Accepted | QMS | Medium | Some of will correct.
8 | Following Log names are used in Procedures but in actual these do not exist- 1. Validation Log 2. Tailoring Log 3. Change Request Log 4. Risk Logs (PRCD_CONFIG_Section-TDP) 5. Peer Review and Defects Log {PRCD_IMPINT_SN6} | Process Improvement Log | Accepted | PRCD_CONFIG PRCD_IMPINT | Small | Some of will correct. | 324 | Minor
9 | {MSTL_CMLIST Sheet3-Role Based Access Right_Row no. 53-PEG Minutes of Meeting} is missing in {MSTL_CMLIST Sheet2-List of CI} | Process Improvement Log | Accepted | MSTL_CMLIST | Small | In list of CI PEG MOM add | 325 | Minor
20 | Risk Handling Options as stated in PRCD_RSKMGM S.No. 4 is not available in Template | Process Improvement Log | Accepted | TMPL_RSKMTX | Small | Risk handling options will give in Risk matrix
21 | TDP defined in {PRCD_CONFIG} is conflicting with the one defined in {PRCD_DESIGN} | Process Improvement Log | Accepted | PRCD_DESIGN | Small | TDP make identical in both PRCD_CONFIG and PRCD_DESIGN
22 | In TMPL_MLSRVW checkpoint number seven can not be applied for RD phase as RD phase is already first then how can we take action to control project performance various from previous phases and also how can they effective if there is no previous phases. | Process Improvement Log | Accepted | TMPL_MLSRVW | Small | Change accordingly in milestone review checklist
Points to Cover in Training
1
2
3

## QMS_3.1 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev. | Impact on Projects
1 | Required skill matrix in project plan | IR | Rejected |  |  |  |  | Minor
2 | Contstraints / assumption coloum in FS | IR | Accepted | TMPL_FUNSPC | Small | Add one column for that | 360 | Minor
3 | Opportunity in risk matrix | IR | Accepted | TMPL_RSKMTX | Small | Include opportunity handling Consolidated Action Plans Actual Date of Completion added to Action Plans | 359 | Minor
4 | Senior Management Roles & Responsibility more effectively explain | IR | Accepted | GDLN_TEAMING | Small | Updates to SM R&R | 361 | Minor
9 | Closure audit and Configuration audit are different, there should be a different closure procedure | Process Improvement Log | Accepted | PRCD_CONFIG | Small | Will add configuration audit section in procedure
10 | Definiion of product support documentation | Process Improvement Log | Accepted | PRCD_IMPINT | Small | Definition / details will add for user support docs in procedure of implementation
11 | In PRCD_ESTMAT.docx input is written as Customer Requirements and Developed Requirements. | Process Improvement Log | Accepted | PRCD_ESTMAT | Small | In procedure of Estimation write Functional specifications as input.
Minor
Minor
Minor
Minor
Minor
20 | Risk Handling Options as stated in PRCD_RSKMGM S.No. 4 is not available in Template | Process Improvement Log | Accepted | TMPL_RSKMTX | Small | Risk handling options will give in Risk matrix
21 | TDP defined in {PRCD_CONFIG} is conflicting with the one defined in {PRCD_DESIGN} | Process Improvement Log | Accepted | PRCD_DESIGN | Small | TDP make identical in both PRCD_CONFIG and PRCD_DESIGN
22 | In TMPL_MLSRVW checkpoint number seven can not be applied for RD phase as RD phase is already first then how can we take action to control project performance various from previous phases and also how can they effective if there is no previous phases. | Process Improvement Log | Accepted | TMPL_MLSRVW | Small | Change accordingly in milestone review checklist
Points to Cover in Training
1
2
3

## QMS_4.0 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | SVN Repository Rev. | Impact on Projects
1 | Modify the entire QMS with respect to EinFram | Process Improvement Proposal via Einframe | Accepted | All QMS | Large | QMS refers to templates that are already in GIL.ef | 105 | Minor
2 | [7 empty] | Minor
3 | [7 empty] | Minor
4 | [7 empty] | Minor
9 | Closure audit and Configuration audit are different, there should be a different closure procedure | Process Improvement Log | Accepted | PRCD_CONFIG | Small | Will add configuration audit section in procedure
10 | Definiion of product support documentation | Process Improvement Log | Accepted | PRCD_IMPINT | Small | Definition / details will add for user support docs in procedure of implementation
11 | In PRCD_ESTMAT.docx input is written as Customer Requirements and Developed Requirements. | Process Improvement Log | Accepted | PRCD_ESTMAT | Small | In procedure of Estimation write Functional specifications as input.
Minor
Minor
Minor
Minor
Minor
20 | Risk Handling Options as stated in PRCD_RSKMGM S.No. 4 is not available in Template | Process Improvement Log | Accepted | TMPL_RSKMTX | Small | Risk handling options will give in Risk matrix
21 | TDP defined in {PRCD_CONFIG} is conflicting with the one defined in {PRCD_DESIGN} | Process Improvement Log | Accepted | PRCD_DESIGN | Small | TDP make identical in both PRCD_CONFIG and PRCD_DESIGN
22 | In TMPL_MLSRVW checkpoint number seven can not be applied for RD phase as RD phase is already first then how can we take action to control project performance various from previous phases and also how can they effective if there is no previous phases. | Process Improvement Log | Accepted | TMPL_MLSRVW | Small | Change accordingly in milestone review checklist
Points to Cover in Training
1 | Project management module of Einframe
2 | Effort Estimation Procedure
3 | Measurements Procedure
4 | Incident Management module of Einframe
5 | Training Module of Einframe

## QMS_4.1 Change Requirements
QMS Change Requirements
Sr. No. | Input | Source of Input | Decision | Artefacts to be modified | Size | Remarks | Repository Rev. | Impact on Projects
1 | For new segment project effort estimation template need to more align . | Process Improvement Proposal via Einframe | Accepted | Efforts Estimation Template | Medium | size in terms of Complexity more clearly defined and to identify complexity guidelines added. | 2e7743a70c945aebc315fb7c8b0b270613d02a22 | Minor
2 | Audit repitition in a phase : before and after Metrics report audit is time consuming for team, pls change to to once after metrics report preparation only. | Process Improvement Proposal via Einframe | Accepted | Project Plan Procedure | Small | Updated in planning procedure | 547dbdc3cd09e7b9ecad634eef0fc5691115e6ea
3 | Audit checklist to be sync with GIL.ef : Category of NC is to be sync with term functional/non-functional | Process Improvement Proposal via Einframe | Accepted | Audit checklist | Small | Major and Minor words replaced by Functional & Non-Functional respectively | be4787ad0e20208cfa1468e98429759a70c40490
4 | Designer itself do module testing by making module test cases, so to do this formally like log the defects and resolve by himself is extra burden, practically it is part of design & implementation and do in each projects. So see this and revise processes accordingly. | Process Improvement Proposal via Einframe | Rejected | Implementation Procedure, Module Test Cases | Large | Already mentioned that log the incidents if required | NA | Minor
5 | Audit Chaecklist updation w.r.t. Einframe | External Review (IR) | Accepted | Audit checklist | Medium | Asset, knowledge, technology related points mentioned in checklist | 13ef27ab8de43dec6dd69d89d39a7c1414861a46 | Minor
6 | Measurement Goals should have some relastic figures, should not zero | External Review (IR) | Accepted | Organization performance goal page of Einframe | Small | Line rejection ration goal changed to 2.5
7 | Size via complexity should reflect in efforts estimation template | External Review (IR) | Accepted | Efforts Estimation Template | Medium | size in terms of Complexity more clearly defined and to identify complexity guidelines added. | 2e7743a70c945aebc315fb7c8b0b270613d02a22 | Minor
9 | Closure audit and Configuration audit are different, there should be a different closure procedure | Process Improvement Log | Accepted | PRCD_CONFIG | Small | Will add configuration audit section in procedure
10 | Definiion of product support documentation | Process Improvement Log | Accepted | PRCD_IMPINT | Small | Definition / details will add for user support docs in procedure of implementation
11 | In PRCD_ESTMAT.docx input is written as Customer Requirements and Developed Requirements. | Process Improvement Log | Accepted | PRCD_ESTMAT | Small | In procedure of Estimation write Functional specifications as input.
8 | Google form for Training feedback need to mention | By Training coordinator | Accepted | OT procedure | Small | Training feedback google form link mentioned in Training procedure. | 96f68c42cf66a5a78399585f9ae1844f99a0d590 | Minor
Minor
Minor
Minor
Minor
20 | Risk Handling Options as stated in PRCD_RSKMGM S.No. 4 is not available in Template | Process Improvement Log | Accepted | TMPL_RSKMTX | Small | Risk handling options will give in Risk matrix
21 | TDP defined in {PRCD_CONFIG} is conflicting with the one defined in {PRCD_DESIGN} | Process Improvement Log | Accepted | PRCD_DESIGN | Small | TDP make identical in both PRCD_CONFIG and PRCD_DESIGN
22 | In TMPL_MLSRVW checkpoint number seven can not be applied for RD phase as RD phase is already first then how can we take action to control project performance various from previous phases and also how can they effective if there is no previous phases. | Process Improvement Log | Accepted | TMPL_MLSRVW | Small | Change accordingly in milestone review checklist
Points to Cover in Training
1 | Estimation : Size in terms of complexity
2 | Escalation Guidelines
3 | Training feedback google form
4
5