## Introduction
Genus Innovation Limited
Audit Reporting Tool
Template version 1

## Audit Data
Id | found in | NC type | Identification Date | Description | Reproduction Steps | Configuration Info | Logged On | Resolved On | Ageing | Status | Type | Assignor / Assignee | Report Type | Product KPI Affected | Source | Task Category | Resolution Type | Effort Spent | Material Cost | Schedule Impact
37 | SVN sync | Functional | Jul 25, 2022 | Working folder is not available at project defined storage location (SVN), but on a local computer, | project folder is lying on local computer | project folder is lying on local computer | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
38 | Requirements | NonFunctional | Jul 25, 2022 | document name does not contain project name, also project name is missed in a few documents | TMPL_FUNSPC, TMPL_REQVAL, ESFNL, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
39 | MOM | Functional | Jul 25, 2022 | Period meeting for project review can not be seen, also MOM pattern is required in details, no mom could find after kick off meeting, no action item is noted down, | MOM meeting details, action items details | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | 3rd Party Component | Project Management | Fixed | 6 | 0
40 | logs | NonFunctional | Jul 25, 2022 | Review defect/no-defect log is not seen, review time sheet is not in sync., | incident log is not seen | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Will Fix in Future | 0 | 0 | 0
41 | Requirements | NonFunctional | Jul 25, 2022 | Related requirements are not clearly mentioned RTT, signs are not clearly mentioned, RTT review can not seen in plan, | related requirement IDs in RTT, Project tasks in plan, incident management | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
42 | Requirements | NonFunctional | Jul 25, 2022 | FS is not baselined and communicated to the team, Customer approval on FS is not seen, external interface need to review again, | FUNSPC, project tasks | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
43 | Plan | Functional | Jul 25, 2022 | efforts for many phases is not available, No risk is identified, planning phase is not completed, metrics reports are not prepared. | ESTFNL_ Risk plan in project plan, MESRPT, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
44 | Requirements | Observation | Jul 25, 2022 | few typographic errors are observed in documents, | Functional specifications, RTT | REV.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
45 | SVN sync | Functional | Jul 25, 2022 | Working folder is not available at project defined storage location (SVN), but on a local computer, | project folder is lying on local computer | project folder is lying on local computer | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
46 | Requirements | NonFunctional | Jul 25, 2022 | document name does not contain project name, also project name is missed in a few documents | TMPL_FUNSPC, TMPL_REQVAL, ESFNL, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | Fixed | 0 | 0 | 0
47 | MOM | Functional | Jul 25, 2022 | Period meeting for project review can not be seen, also MOM pattern is required in details, no mom could find after kick off meeting, no action item is noted down, | MOM meeting details, action items details | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | Fixed | 6 | 0
48 | logs | NonFunctional | Jul 25, 2022 | Review defect/no-defect log is not seen, review time sheet is not in sync., | incident log is not seen | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | Will Fix in Future | 0 | 0 | 0
49 | Requirements | NonFunctional | Jul 25, 2022 | Related requirements are not clearly mentioned RTT, signs are not clearly mentioned, RTT review can not seen in plan, | related requirement IDs in RTT, Project tasks in plan, incident management | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | Fixed | 0 | 0 | 0
50 | Requirements | NonFunctional | Jul 25, 2022 | FS is not baselined and communicated to the team, Customer approval on FS is not seen, external interface need to review again, | FUNSPC, project tasks | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
51 | Plan | NonFunctional | Jul 25, 2022 | efforts for many phases is not available, No risk is identified, planning phase is not completed, metrics reports are not prepared. | ESTFNL_ Risk plan in project plan, MESRPT, | rev.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
52 | Requirements | Observation | Jul 25, 2022 | few typographic errors are observed in documents, | Functional specifications, RTT | REV.00 | Jul 26, 2022 | Jul 27, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | 3rd Party Component | Project Management | Fixed | 0 | 0 | 0
53 | Plan | Functional | Jul 25, 2022 | project measurement goals are not found. | refer to project plan detail | REV.00 | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta AggarwalSobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
54 | Plan | Functional | Jul 25, 2022 | project measurement goals are not found. | refer to project plan detail | REV.00 | Jul 26, 2022 | Jul 29, 2022 | - | Closed | Project RelatedBMS 20S 40A NMC 72V | Shweta AggarwalSyojiram Sharma | BUG | Reliability | Modified Implementation | Project Management | Fixed | 0 | 0 | 0
57 | Plan | Functional | Jul 27, 2022 | Project plan is missing talent need, asset, knowledge, risk details, link to project data, review project financials | project plan requirements | PEG Plan | Jul 28, 2022 | Jul 29, 2022 | - | Closed | Project Related- | Shweta AggarwalJalaj Mathur | BUG | Reliability | Modified Implementation | Systems Engineering | Fixed | 1 | 0 | 0
58 | Plan | NonFunctional | Jul 27, 2022 | PEG activities after december'22 can not seen in project plan | project tasks are missing for Q4 | PEG plan | Jul 28, 2022 | Jul 30, 2022 | - | Closed | Project RelatedPEG_Plan_2022-23 | Shweta AggarwalJalaj Mathur | BUG | Reliability | Modified Implementation | Systems Engineering | Will Fix in Future | 0 | 0 | 0
59 | Plan | Observation | Jul 27, 2022 | SCAMPI words is not appropriate, task name to be appropriate, task category should be appropriate, duration process review task duration is not appropriate. | project task contains "SCAMPI', CPR is CPR execution, project task to be appropriate, project review task is shortly mentioned in task. | PEG plan | Jul 28, 2022 | Jul 30, 2022 | - | Closed | Project RelatedPEG_Plan_2022-23 | Shweta AggarwalJalaj Mathur | BUG | Reliability | Modified Implementation | Systems Engineering | Fixed | 1 | 0 | 0

## Analysis
Count of NC type | Column Labels
Row Labels | Functional | NonFunctional | Observation | (blank) | Grand Total
logs |  | 2 |  |  | 2
MOM | 2 |  |  |  | 2
Plan | 4 | 2 | 1 |  | 7
Requirements |  | 6 | 2 |  | 8
SVN sync | 2 |  |  |  | 2
(blank)
Grand Total | 8 | 10 | 3 |  | 21
Analysis
NCs are found majorly in Team meetings, plan documents and function specifications (as shown in above graph)
Area | Problem | Elaboration |  |  |  | Impacts | Suggestions
Requirements | document name does not contain project name | project name is not available in file name |  |  |  | - | Cross sectional audit is recommended acorss projects.
| FS not baselined and communicated | FS not baselined and communciated to the team. |  |  |  | -
| Review gaps | Review of FS, RTT should be in more details |  |  |  | if taken reference in future, product's specifications can be affected | Self review of project management at toll gates/review with peer experienced project manager is recommended to avoid these issues.
Plan Documents | Estimation is incomplete | Estimation is not derived for some phases. |  |  |  | reference for future projects can be affected in the terms of efforts.
| Project plan is incomplete | project plan does not contain asset, talent requirements, risks, link to project data, project financials. |  |  |  | Missed project information may lead communication gap about projects information.