## Introduction
Genus Innovation Limited
Audit Reporting Tool
Template version 1

## Audit Data
Id | Area | Identification Date | Description | Reproduction Steps | Configuration Info | Logged On | Resolved On | Ageing | Status | Type | Assignor | Assignee | Report Type | Product KPI Affected | Source | Task Category | Found In | Fixed In | Classification | Resolution Type | Effort Spent | Material Cost | Schedule Impact
131 | Metrics report | Sep 06, 2022 | Corrective actions, process & product defect density are not mentioned in final metrics report while calculated separately in draft report at local computer. | metrics report- end of report, corrective actions, product defect density, process defect density. | metrics report available at svn on revision 20 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - matrix report updated with defect and process density | 2022-09-07 - matrix report updated with defect and process density | Functional | Fixed | 0 | 0 | 0
132 | Project plan | Sep 06, 2022 | project measurement are missing in project definition | go to project description | project plan- description | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - project unpublish and publish with update | 2022-09-07 - project unpublish and publish with update | Non Functional | Fixed | 0 | 0 | 0
133 | Project plan | Sep 06, 2022 | Risk RPN is not revised at the end of project, also risk related to new PCB designer is not identified in any records, while training action is already taken. | projects- project risk, action plan | project plan- project risk | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - project unpublish and publish with update | 2022-09-07 - project unpublish and publish with update | Non Functional | Fixed | 0 | 0 | 0
134 | MINMET | Sep 06, 2022 | final MOM is not updated at SVN server, but available on a local computer, | SVN server- refer MOM | revision 20 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-07 - MOM updated and update action item | 2022-09-07 - MOM updated and update action item | Non Functional | Fixed | 0 | 0 | 0
135 | Review | Sep 06, 2022 | No review evidence could seen for RTT review after adding design, integration, system IDs. | RTT review log, timesheet not seen | RTT review | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - During audit at validation phase | 2022-09-06 - During audit at validation phase | Observation | Fixed | 0 | 0 | 0
136 | HWTCAS | Sep 06, 2022 | updated HWTCAS are not available at SVN server | SVN server - HWTCAS not updated | HWTCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - Audit of hardware test case | 2022-09-06 - Audit of hardware test case | Non Functional | Fixed | 0 | 0 | 0
137 | Documentation | Sep 06, 2022 | user & CFT support documentation, BOM are not placed at SVN server | SVN server -documentation | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - all supporting document provide and make SVN access also | 2022-09-07 - all supporting document provide and make SVN access also | Non Functional | Fixed | 0 | 0 | 0
138 | SYSCAS | Sep 06, 2022 | updated SYSCAS are not available at SVN server | SVN server - SYSCAS not updated | SYSCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - System test case during validation phase | 2022-09-06 - System test case during validation phase | Non Functional | Fixed | 0 | 0 | 0
139 | RTT | Sep 06, 2022 | Updated RTT is not found on SVN server | SVN- RTT not updated | SVN server- RTT | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - RTT updated with system test case id | 2022-09-07 - RTT updated with system test case id | Non Functional | Fixed | 0 | 0 | 0
140 | VALRPT | Sep 06, 2022 | Validation report is not found on SVN | SVN- Validation report missing | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-06 - audit of validation phase | 2022-09-06 - audit of validation phase | Non Functional | Fixed | 0 | 0 | 0
141 | Defect analysis | Sep 06, 2022 | no formal defect analysis is seen | defect analysis missing | defect analysis | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Shweta Aggarwal | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - two number of testing defect log by adarsh and analysis then resolved the defect. | 2022-09-07 - two number of testing defect log by adarsh and analysis then resolved the defect. | Functional | Fixed | 0 | 0 | 0
142 | Metrics report | Sep 06, 2022 | Corrective actions, process & product defect density are not mentioned in final metrics report while calculated separately in draft report at local computer. | metrics report- end of report, corrective actions, product defect density, process defect density. | metrics report available at svn on revision 20 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - metrics report updated with product defect density | 2022-09-07 - metrics report updated with product defect density | Functional | Fixed | 0 | 0 | 0
143 | Project plan | Sep 06, 2022 | project measurement are missing in project definition | go to project description | project plan- description | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | Non Functional | Fixed | 0 | 0 | 0
144 | Project plan | Sep 06, 2022 | Risk RPN is not revised at the end of project, also risk related to new PCB designer is not identified in any records, while training action is already taken. | projects- project risk, action plan | project plan- project risk | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | 2022-09-07 - PROJECT UNPUBLISH AND AUDIT NCs RESOLVE. | Non Functional | Fixed | 0 | 0 | 0
145 | MINMET | Sep 06, 2022 | final MOM is not updated at SVN server, but available on a local computer, | SVN server- refer MOM | revision 9 | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - sheet updated and svn access provided access provided | 2022-09-07 - sheet updated and svn access provided access provided | Non Functional | Fixed | 0 | 0 | 0
146 | Review | Sep 06, 2022 | No review evidence could seen for RTT review after adding design, integration, system IDs. | RTT review log, timesheet not seen | RTT review | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - RTT updated and svn committed | 2022-09-07 - RTT updated and svn committed | Observation | Fixed | 0 | 0 | 0
147 | HWTCAS | Sep 06, 2022 | updated HWTCAS are not available at SVN server | SVN server - HWTCAS not updated | HWTCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - sheet updated and committed on svn access. | 2022-09-07 - sheet updated and committed on svn access. | Non Functional | Fixed | 0 | 0 | 0
148 | Documentation | Sep 06, 2022 | user & CFT support documentation, BOM are not placed at SVN server | SVN server -documentation | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - all supporting documents provided on svn access. | 2022-09-07 - all supporting documents provided on svn access. | Non Functional | Fixed | 0 | 0 | 0
149 | SYSCAS | Sep 06, 2022 | updated SYSCAS are not available at SVN server | SVN server - SYSCAS not updated | SYSCAS | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - sheet updated and committed on svn access. | 2022-09-07 - sheet updated and committed on svn access. | Non Functional | Fixed | 0 | 0 | 0
150 | RTT | Sep 06, 2022 | Updated RTT is not found on SVN server | SVN- RTT not updated | SVN server- RTT | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - RTT UPDATED AND COMMITTED ON SVN ACCESS. | 2022-09-07 - RTT UPDATED AND COMMITTED ON SVN ACCESS. | Non Functional | Fixed | 0 | 0 | 0
151 | VALRPT | Sep 06, 2022 | Validation report is not found on SVN | SVN- Validation report missing | SVN server | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - VALIDATION REPORT UPDATED AND COMMITTED ON SVN ACCESS. | 2022-09-07 - VALIDATION REPORT UPDATED AND COMMITTED ON SVN ACCESS. | Non Functional | Fixed | 0 | 0 | 0
152 | Defect analysis | Sep 06, 2022 | no formal defect analysis is seen | defect analysis missing | defect analysis | Sep 06, 2022 | Sep 06, 2022 | - | Closed | Project RelatedGGE300_BMS 20S 40A NMC 72V | Shweta Aggarwal | Syojiram Sharma | BUG | Reliability | Modified Implementation | Testing | 2022-09-07 - ANALYSIS DONE IN METRICS REPORT. | 2022-09-07 - ANALYSIS DONE IN METRICS REPORT. | Functional | Fixed | 0 | 0 | 0
153 | Closure report | Sep 08, 2022 | Documents location link should be as hyper link. | Project Closure report. | SVN rev. 30 | Sep 08, 2022 | Sep 08, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-08 - resolved . All link converted in to hyper link | 2022-09-08 - resolved . All link converted in to hyper link | Non Functional | Fixed | 0 | 0 | 0
154 | Closure report | Sep 08, 2022 | Backup location and restoration occurrence not mentioned. | Project Closure report. | SVN Rev. 30 | Sep 08, 2022 | Sep 08, 2022 | - | Closed | Project RelatedSP9-GGE295 DC-DC Converter 12V-10A & 5V-1A | Jalaj Mathur | Sobhag Prajapat | BUG | Reliability | Modified Implementation | Project Management | 2022-09-08 - resolved . Location defined in sheet . | 2022-09-08 - resolved . Location defined in sheet . | Non Functional | Fixed | 0 | 0 | 0
162 | Metrics report | Sep 07, 2022 | metrics report- corrective actions are not filled phase wise, inappropriate, | metrics report at SVN server | metrics report at SVN | Sep 13, 2022 | Sep 14, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-09-14 - GGS151_MESRPT REV_44 | 2022-09-14 - GGS151_MESRPT REV_49 | Functional | Fixed | 0 | 0 | 0
163 | Review | Sep 07, 2022 | Updated RTT, HTCAS, code review checklist are not available at SVN server but on a local computer, | RTT, HWTCAS, CODRVW at svn | SVN server | Sep 13, 2022 | Sep 26, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Project Management | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | Non Functional | Fixed | 0 | 0 | 0
164 | Defect analysis | Sep 07, 2022 | Defect analysis is not done | defect analysis missing | defect analysis missing | Sep 13, 2022 | Sep 26, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | 2022-09-26 - http://192.168.100.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | Non Functional | Fixed | 0 | 0 | 0
165 | Logs | Sep 07, 2022 | testing defects are logged in issue category. | incident management - testing defects log for this proect | incident management | Sep 13, 2022 | - | 24 Days | Open | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | - | - | - | - | null | null | Observation
178 | Logs | Sep 17, 2022 | time sheet for few task-person is missing, ex. Sobhag for plan review is missed | time sheet not available | time sheet is missed | Sep 17, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Documentation | 3rd Party Component | Project Management | 2022-09-19 - audit phase during time sheet captured | 2022-09-19 - audit phase during time sheet captured | Observation | Fixed | 0 | 0 | 0
179 | Metrics report | Sep 17, 2022 | product & process defect density to be calculated at the end of project only as per QMS. | Metrics report-defect density calculation is not required. | metrics report- product defect density | Sep 17, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Documentation | 3rd Party Component | Project Management | 2022-09-19 - matrix report during RD phase 2022-09-19 - During Audit in RD phase | 2022-09-19 - SVN-DC-DC converter-Revision 582022-09-19 - SVN-DC-DC converter-Revision 58 | Observation | Fixed | 0 | 0 | 0
180 | MINMET | Sep 17, 2022 | Kick off meeting- project major requirements should be briefly discussed with the team, eg. IP test, product ratings | kick off meeting MOM | MIMET- kick off meeting | Sep 17, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Documentation | 3rd Party Component | Project Management | 2022-09-19 - audit phase in RD phase2022-09-19 - During Audit in R&D phase | 2022-09-19 - further will take care in mom making2022-09-19 - SVN-DC-DC converter -Revision 59 | Observation | Will Fix in Future | 0 | 0 | 0
181 | MINMET | Sep 17, 2022 | MOM does not show any discussion on pending or previous action item which in turn may lead to miss that action item if not mentioned in MOM. | MINMET meetings, action items | MINMET | Sep 19, 2022 | Sep 19, 2022 | - | Closed | Project RelatedSP10-GGE302 DC DC Synchronous Auto Grade | Shweta Aggarwal | Sobhag Prajapat | BUG | Protections | Modified Implementation | Project Management | 2022-09-19 - Audit during RD phase | 2022-09-19 - Audit during RD phase | Observation | Will Fix in Future | 0 | 0 | 0
201 | MINMET | Sep 21, 2022 | MOM- kick off shall concerned about project basic requirements, action items are not discussed in further meetings as per MOM | GGE289_MINMET, action items | GGE289_MINMET | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | BUG | Charging Profile | New Implementation | Project Management | 2022-09-22 - it is found in current version of MOM. which is lying in project repository dated 22 sep 22 15:40PM | 2022-09-22 - No need to fix the problem so version will not change. | Observation | Fixed | 0 | 0 | 0
202 | Review | Sep 21, 2022 | no findings are observed for RTT review in incident log. | no log for RTT review | RTT review incident | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | BUG | Charging Profile | New Implementation | Systems Engineering | 2022-09-22 - found in EIN frame --> defect logs | 2022-09-22 - no need to fix. Same EIN frame --> defect logs | Observation | Fixed | 0 | 0 | 0
203 | Project plan | Sep 21, 2022 | sequence of project task- validation defect closure (1615) BOM finalization (1618) shall come before validation phase end, | project task sequence | project task sequence | Sep 22, 2022 | Sep 22, 2022 | - | Closed | Project RelatedGGE289 Proton Q 1500 12V 25A | Shweta Aggarwal | Deepesh Jain | BUG | Charging Profile | Modified Implementation | Project Management | 2022-09-22 - EIN frame:- Sep 20, 2022 12:08:25 (UTC) | 2022-09-22 - EIN frame:- Sep 22, 2022 11:07:15 (UTC) | Non Functional | Fixed | 0 | 0 | 0
204 | Project plan | Sep 22, 2022 | CM plan, Plan review checklist, reviewer time sheet, review defect log are not available at project site but on a local computer. | plan review documents missed at SVN | plan review | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - CM plan, Plan review checklist, reviewer time sheet, review defect log are not available at project site updated | Non Functional | Fixed | 0 | 0 | 0
205 | Review | Sep 22, 2022 | FS review checklist, defect log for FS& RTT review are not available at project site. | FS & RTT review logs | FS& RTT | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - FS review checklist, defect log & RTT review are updated on svn | Non Functional | Fixed | 0 | 0 | 0
206 | Metrics report | Sep 22, 2022 | measurement goals of schedule variance are conflicting in project plan and MOM | schedule variance mismatch | SV mismatch | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | Modified Implementation | Testing | 2022-09-24 - Project published - plan updated after plan review issue resolve Sep 21, 2022 07:07:18 (UTC) | 2022-09-24 - Updated schedule variance instead of measurement goals in project description. | Non Functional | Fixed | 0 | 0 | 0
207 | others | Sep 22, 2022 | manage mails at separate folder "MAILS" instead of keeping them separately in individual folder | management of mails in separate folder | mails management | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - managed mails at separate folder "MAILS" | Observation | Fixed | 0 | 0 | 0
209 | Project plan | Sep 22, 2022 | sequence of project task- validation defect closure (1592) BOM finalization (1596) shall come before validation phase end, | project task sequence | project task sequence | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - In project plan, sequence of project task updated - | Non Functional | Fixed | 0 | 0 | 0
210 | MINMET | Sep 22, 2022 | MINMET-project name has typing error kick off meeting, no action item is addressed in action items sheet, nor discussed in later meetings | team meetings, kick off meeting | MINMET | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolveSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - MINMET-project name has typing error kick off meeting corrected. | Non Functional | Fixed | 0 | 0 | 0
211 | Project plan | Sep 22, 2022 | effort estimation task shall include all relevant core team members | effort estimation members | members in effort estimation | Sep 22, 2022 | Sep 24, 2022 | - | Closed | Project RelatedOBH012 Combo-Z 3200 48V | Shweta Aggarwal | Syojiram Sharma | BUG | Documentation | 3rd Party Component | Testing | 2022-09-24 - plan updated after plan review issue resolvesSep 21, 2022 07:07:18 (UTC) | 2022-09-24 - included relevant team member in effort estimation task in project plan. | Observation | Fixed | 0 | 0 | 0
213 | Logs | Sep 24, 2022 | no defect is logged for RTT review. | incident of no finding of RTT review | incident RTT review | Sep 24, 2022 | - | 14 Days | Open | Project RelatedGNE114 | Shweta Aggarwal | Chandrashekhar Sharma | - | - | - | - | null | null | Observation
214 | Review | Sep 24, 2022 | FS review checklist is not updated at SVN server | FS review checklist at SVN | FS review checklist not available | Sep 24, 2022 | Nov 01, 2022 | - | Closed | Project RelatedGNE114 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-10-01 - http://10.141.1.9:8080/svn/HKVA_inv/GNE114/RD%20Phase/ | 2022-10-01 - http://10.141.1.9:8080/svn/HKVA_inv/GNE114/RD%20Phase/ | Non Functional | Fixed | 0 | 0 | 0

## Analysis
Count of Area | Column Labels
Row Labels | Functional | Non Functional | Observation | (blank) | Grand Total
Closure report |  | 2 |  |  | 2
Defect analysis | 2 | 1 |  |  | 3
Documentation |  | 2 |  |  | 2
HWTCAS |  | 2 |  |  | 2
Logs |  |  | 3 |  | 3
Metrics report | 3 | 1 | 1 |  | 5
MINMET |  | 3 | 3 |  | 6
others |  |  | 1 |  | 1
Project plan |  | 7 | 1 |  | 8
Review |  | 3 | 3 |  | 6
RTT |  | 2 |  |  | 2
SYSCAS |  | 2 |  |  | 2
VALRPT |  | 2 |  |  | 2
(blank)
Grand Total | 5 | 27 | 12 |  | 44
| Problem | Elaboration |  |  |  | Impacts | Suggestions
| Metrics report | Corrective actions, process & product defect density are not mentioned in final metrics report while calculated separately in draft report at local computer. |  |  |  | locally data management may impact loss of data and other teammates can not take ref data for other projects also | Keep daily habit of SVN commit, a minor software can be installed in all computers to remind everyone at 5:25 to do this job.
|  | metrics report- corrective actions are not filled phase wise, inappropriate, |  |  |  | -
| Defect analysis | no formal defect analysis is seen |  |  |  | Defect analysis can help in prevention of re-occurrence of the defects and by reaching at root cause of the defects may help in prevention of new type of potential defects | Defect analysis to be done for testing defects (every stage), review defects at least. (incident ID - 237, Process improvement)