## Slide 1
INTRODUCTION (GGE302)
Project Name:
SP10-GGE302 DC DC Synchronous Auto Grade
.
Objective- To Development Electronics part (DC Supply ) for with auto grade components
Scope- DC DC Converter is converter which converter High DC voltage in to Low voltage with below Spec.
Input -35-90V ,Output Rating 12V-10A and 5V 1A DC ,Enclosure- IP 66.
Hardware side - Designing part of his Converter using Synchronous buck converter
Software side- No any scope of work.
Mechanical Side- To develop IP 67 Enclosure in Aluminum casing
Measurement Goals - SV: ±20% , PDD: 0.10±0.02 , PPDD : 0.20±0.02
Link to Project Data : http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302
Team Size: 10 Nos. Effort Size: 201.04 hrs. Time Line : 07-09-2022 to 31-10-2022
Actual Scheduled Start to planed Finish Date: 19-7-2022 to 01-11-2022

## Slide 2
Estimating and Planning
High Level Estimation in start meeting with Sr. Management.
Complexity -Medium Type
Cost approx 400-450 Rs ( assumption with 2 nos Mosfet -160Rs , 2 Inductor 50Rs , 6 nos capacitor -60 ,enclosure-30rs and harness 30rs ,PWM controller-80rs and converter-25Rs )
Duration-35-40 day (design-7 days, design implementation - 15 days,Testing 10days,validation 5days , other activity-5 days )
effort- high level reference of GGE295 approx 180-190persone hours
S. No. | Reference Project Name | Why Selected as Reference | Actual Efforts in RD Phase & Planning Phase | Actual Efforts in Design and Implementation | Actual Efforts in Testing and integration | Actual Efforts in Validation Phase , Closure | Actual Efforts in End
1 | GGE295 DC-DC Converter 12V-10A & 5V-1A | Capacity Rating is approx equal and input na d output spec. also approx equal. | 27 | 45 | 27 | 53 | 22
 |  | Average Efforts in person hours | 27 | 45 | 27 | 53 | 22
 | Difference from reference in detail | Impact in person hours due to the difference | Complexity | Remarks (Optional)
1 | Enclosure Design | -8 | H | First time development in Reference Project
2 | Auto grade components selection and arrangement | 8 | H | First time development
3 | Synchronous Buck converter Design | 10 | H | First time development
4 | PCB layout and new component footprint making | 8 | H | First time development
5 | 5V design | 4 | M | First time development
6 | 5V PCB layout | 4 | M | First time development
7 | Testing | 10 | H | First time testing
8 | Readability of Power device and Inductor | -4 | M | Reuse components
9 | Testing Ids | -4 | M | Reuse components
 | Total Impact | 28 |  | 
 |  |  | Size | 5H+4M+0L
 | Estimated Efforts in RD Phase & Planning Phase | Estimated Efforts in Design and Implementation | Estimated Efforts in Testing and integration | Estimated Efforts in Validation Phase , Closure | Estimated Efforts in End | 
Past Projects | 27 | 45 | 27 | 53 | 22 | 
Differences from reference projects | 4 | 7 | 4 | 9 | 4 | Total
Final estimates | 31 | 52 | 31 | 62 | 26 | 202

## Slide 3
Project Planning in Einframe - Project Plan Link-https://gil.einframe.com/rptprojectoverview.aspx
Project Team
Project Manager- SP
Hardware Designer- SP,AK
Mechanical Designer- BK
PCB Designer- RP
Validation Manager- JM
Integrator- RJ
Validator- RS
Material Management- SJ
Reviewer- SJ,SRS,SP,JM
Auditor- SW
Senior Management- TG
Assembler- PK,RK
Task list making
Team assign in task with tools (asset and work environment )
Task approval (Time sheet approval)
Deployment of plan with team
Operation and support transition plan
Team Meeting Planning ( 6 Times)
Sr. Management review (8 times)
Critical dependency ( two )
Audit planning (3 times)
Review planning at significant task
CM planning

## Slide 5
Record task completion

## Slide 6
Identify issues and resolution
Tacking review defect and status.
Managing upcoming task due to delay in last task

## Slide 7
Weeks | No of Week | Name of Phase | Planned Value | Earned Value | Actual Cost | Schedule variance (EV-PV/PV)*100 | Cost Variance (AC-EV/EV)*100
1st | 07-09-22 to 14-09-22 | RD Phase, Planning Phase | 43 | 34 | 20 | -20.93% | -41.17%
2nd | 14-09-22 to 21-09-22 | Design and Implementation | 74 | 61 | 39 | -17.56% | -36.06%
3rd | 21-09-22 to 28-09-22 | Design and Implementation | 106 | 77 | 59 | -27.35% | -23.37%
4th | 28-09-22 to 05-10-22 | Testing and integration | 122 | 110 | 120 | -9.83% | -9.09%
5th | 05-10-22 to 12-10-22 | Testing and integration | 122 | 110 | 120 | -9.83% | -9.09%
6th | 13-10-22 to 19-10-22 | Validation Phase , Closure | 163 |  |  |  | 
7th | 20-10-22 to 26-10-22 | Validation Phase , Closure | 163 |  |  |  | 
8th | 27-10-22 to 01-11-22 | Validation Phase , Closure | 201.2 |  |  |  | 
EVMS CHART
Causal Analysis,Corrective action,Preventive action

## Slide 8
Project is Running in Module testing
GGE302_HWTCAS
GGE302_MCTCAS
GGE302_INTCAS