## Sheet1
Reports > Incident Management :: EinFrame
Id | Identification Date | Description | Reproduction Steps | Configuration Info | Logged On | Resolved On | Ageing | Status | Type | Assignor / Assignee | Report Type | Product KPI Affected | Source | Task Category | Resolution Type | Effort Spent | Material Cost | Schedule Impact
1 | Aug 11, 2021 | test data to check function of this feature | test data to check function of this feature | test data to check function of this feature | Aug 11, 2021 | Aug 11, 2021 | - | Closed | Project RelatedSUPPORT ACTIVITIES | Jalaj MathurVikash Sharma | BUG | Tuning | Modified Implementation | Hardware | Fixed | 1 | 0 | 1
2 | Aug 11, 2021 | to test to check functality in software | to test to check functality in software | to test to check functality in software | Aug 11, 2021 | - | 272 Days | Open | Project Related10KW/120V MPPT PCU Kaizen | Jalaj MathurUmesh Likhitkar | BUG | Tuning | Regression in untouched module | Hardware |  | 1 | 0 | 1
4 | Aug 11, 2021 | Vce Saturation Signal Have more Noise so that this circuit not proper working with Opto-cupler 4N35 | please take reference to 10KW MPPT Existing | add circuit and connect with controller Pin no. 5 | Aug 12, 2021 | Aug 13, 2021 | - | Closed | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarUmesh Likhitkar | New Feature | Tuning | New Implementation | Hardware | Will Fix in Future
5 | Aug 06, 2021 | Inverter heat sink heating up to 85deg. Cen. in 4hrs with solar and 37Aac load | please use air channel than Re-testing of heating | used 10KVA Surja Power PCB and new Solar charger | Aug 12, 2021 | - | 272 Days | Open | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarUmesh Likhitkar | - | - | - | -
6 | Aug 06, 2021 | The Booster at the time of high Grid voltage take decision after 10 msec. | To provide the high grid voltage above 280V. | CRO was placed on the Mosfet to check the voltage pulse. | Aug 12, 2021 | Mar 04, 2022 | - | Closed | Project RelatedSUPPORT ACTIVITIES | Abhishek GuptaAbhishek Gupta | BUG | Display | Regression in untouched module | Firmware | Fixed | 1 | 0 | 0
7 | Aug 14, 2021 | Actual Data and LCD Data not match. like batt. volt actual 122 but LCD show 212V, Dis charging curr. actula 0A but LCD show 5.6A, PV Volt Actual 157V but LCD show 560V etc. | During LCD Testing With Product | During LCD Testing With Product | Aug 14, 2021 | Aug 16, 2021 | - | Closed | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarRajashekhar K | BUG | Tuning | New Implementation | Firmware | Fixed | 4 | 0 | 4
9 | Aug 13, 2021 | The System is reading the lower voltage range as a positive difference of PV and Battery | Connect 12/24 V battery and connect the <10 V PV the system will reconnect the realay. | The hardware and software are same that are connected in the working range. | Aug 16, 2021 | Aug 17, 2021 | - | Closed | Project RelatedSUPPORT ACTIVITIES | Abhishek GuptaSyojiram Sharma | BUG | Tuning | Modified Implementation | Hardware | Platform / Design Limitations | 4 | 0
10 | Aug 17, 2021 | Tuning tool observations below. 1. mains volt not show. 2. solar charging current not come on place of total charging current. 3. Tuning option not enable, 4. Enable option of ES1/ES2/ES3/NoHy moe 5. add address of Tool Rev. and Software Rev. For Production | During testing with New LCD software | 10KW_MPPT_MOSFET_Rev0_16_08_21 | Aug 17, 2021 | - | 266 Days | Open | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarBharti Sharma | BUG | Tuning | Modified Implementation | Software |  | 1 | 0 | 0
11 | Aug 17, 2021 | Observations are Below. 1. Mains LED not ON 2. Battery LED not blinking During Charging 3. LCD show Mains Fuse blow instead of Mains MCB Trip | During LCD PCB Testing With Mains charging | Software Rev 14 | Aug 18, 2021 | - | 266 Days | Open | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarRajashekhar K | - | - | - | -
12 | Aug 17, 2021 | Observations are Below. 1. Mains LED not ON 2. Battery LED not blinking During Charging 3. LCD show Mains Fuse blow instead of Mains MCB Trip | During LCD PCB Testing With Mains charging | Software Rev 14 | Aug 18, 2021 | Sep 25, 2021 | - | Closed | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarRajashekhar K | New Feature | Display | New Implementation | Requirements, Design, Integration, Testing | Fixed | 1 | 0
13 | Aug 18, 2021 | test bug for check to test... | test bug for check to test... | test bug for check to test... | Aug 18, 2021 | Mar 03, 2022 | - | Closed | Project Related10KW/120V MPPT PCU Kaizen | Jalaj MathurJalaj Mathur | BUG | Display | Regression in untouched module | Firmware | Fixed | 1 | 0 | 0
14 | Aug 20, 2021 | Front switch Function not Working in Software Rev 14LCD.S1. UPS/Nor mode and ES Function found OK | During testing of 10 KW MPPT NLCD14 S1.elf | 10 KW MPPT NLCD14 S1.elf | Aug 20, 2021 | Aug 20, 2021 | - | Closed | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarTarun Gupta | New Feature | Display | New Implementation | Firmware | Fixed | 2 | 0 | 0
18 | Sep 03, 2021 | System does not share mains and Solar charging current properly. | System does not share mains and Solar charging current properly During mains and solar Both Available | Software Rev 14_S6 | Sep 08, 2021 | - | 244 Days | Open | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarTarun Gupta | - | - | - | -
19 | Sep 03, 2021 | Tuning Tool +/- button not working properly. Solar Charging current not show | Tuning Tool +/- button not working properly . Solar Charging current not show | 10kw_MPPT_LCD_REV2 | Sep 08, 2021 | - | 244 Days | Open | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarBharti Sharma | - | - | - | -
20 | Sep 21, 2021 | If we want to change any globally defined variable by GUI, for this firstly we should define that variable in flash. by this method we can change the variable value by GUI. | If we want to change any globally defined variable by GUI, for this firstly we should define that variable in flash. by this method we can change the variable value by GUI. | Configured | Oct 09, 2021 | - | 214 Days | Open | Project RelatedBMS 50A/48V | Raghvendra ThakurRaghvendra Thakur | - | - | - | -
21 | Oct 18, 2021 | testing workflow with this | testing the workflow | first version of testing | Oct 18, 2021 | - | 205 Days | Open | Project RelatedDummy Demo | Jalaj MathurJalaj Mathur | - | - | - | -
24 | Mar 10, 2022 | System take 5-6 sec time for Mains Recovery in invertor high cutt mode | During High cutt mode Recovery in normal mode 300v to 270V | 1 KW 48V MPPT Assam15.elf | Mar 11, 2022 | - | 60 Days | Open | Project Related1250VA MPPT PCU for APDCL | Umesh LikhitkarFTarun Gupta | - | - | - | -
25 | Mar 14, 2022 | The validation report should have some pics of testing. | Validation report regarding CRO waveforms etc. | Validation report rev.0 | Mar 14, 2022 | - | 58 Days | Open | Project Related10KW/120V MPPT PCU Kaizen | Umesh LikhitkarVikash Sharma | - | - | - | -
26 | Apr 01, 2022 | Because of unavailability of proper inductive load, charger and proper cells/battery pack, testing for the voltage spikes on the MOSFETs are not done. Need the higher management to make arrangements for the same so that proper testing can be done. | None available with us. | The test is not conducted, as there is unavailability of the resources. | Apr 01, 2022 | - | 40 Days | Open | Project RelatedBMS DEVELOPMENT AND TESTING | Abhishek KumarFTarun Gupta | - | - | - | -