## Sheet1
Improvement / Addition Features in Einframe
S. NO. | Point | From Vendor |  | Internal Team
27-07-21
|  | Clarification / Suggestions -1 | Clarification / Suggestions -2 | Decisions / Actions | Status
1 | Time Sheet Capture – Additional Activity types: | As per the current practice in GIPL, you can create action items for all the custom categories with extended start/end dates like April 1st to March 31st. Thereafter, you can capture timesheet against these action items (by selection Action Items in the first dropdown). | we also use a project called Misc Activities with a long time-span and all these activities. We log efforts against that project for the specific task. If there are specific resources/employees for a particular activity, you can assign before hand and then the timesheets can be filled. This also enables all kinds of reporting that is built into the system, in addition to emails, alerts, resource loading etc to work as it is. Action items can only be assigned to one person at a time. So, if there is a specific “single person” task, you can use action items. For example, Tarun ji can use the same for regular management meetings etc. | Decision : OK, we'll follow actions items concept mainly, Project concept will apply when some planned activities need to do with 2 ar more persons. Actions : Jalaj will share wordings of headers from KRA sheets till 28-07-21 | Pending
2 | Machine Tools loading on project tasks, similar to person loading: | You can define machines/tools as employees with a specific naming convention like ‘Assets’ in First Name and machine name in last name. Same as employees, you can select these machines as project team members and allocate tasks, loading onto them. This will automatically facilitate all types of resource loading reports and no additional reports will be required. |  | Decision : OK, team agreed Actions : Shweta Ma'am & Sobhag provide list of all tool, machines & softwares etc. | Pending
3 | Assigned tasks in Project/ Project plan view: | can use the Action Item page (landing page after login) for this purpose. This page lists all action items (each task of a published project is also an action item) |  | OK
4 | Document Upload with Timesheet Entry: | Can you please double-check with your legal team regarding uploading documents to a 3rd party cloud. If there is no objection from your side, we can facilitate this feature. | document uploading, I was asked not to allow uploading documents to a cloud service. You may further check. | Actions : 1. Tarun sir confirm this statement with CEO. 2. Meanwhile explore locations of Project data | Pending
5 | Projects to be taken |  |  | Decision : All persons will take their corresponding projects after completion of point 1 & 2 actions tentatively from 2nd August 2021 | Pending
6 | Remaining Persons Training |  |  | Action : Jalaj will call training this week | Pending
7 | Existing Process like google forms |  |  | Decisions : For time being run as it is
8 | Non Mail ID users |  |  | Decision : Make them users and assign tasks in project and convey them verbally or one upcoming week tasks list provide in advance