## Project-0
Project Name | [5 empty] | Project Team
Project Manager
Objective & Scope | [5 empty] | Designers
Reviewers
Integration & Testing Persons
Vaidation Member
S. No. | TG | Key Task | Activitiy Description | Plan Start Target | Plan End Target | Resp'ble | Actual Start date | Actual Finish date | Actual Work (%) | Status
| Market Feasibility Stage TG-0 | Idea Vetting & (Voice of Customer) VOC | Mail receipt, verbal communication, Export requirements sheet, Export PO
|  | Business Case is filled by Requester | Target Selling price, Target BOM pirce, Anual Qty etc.
|  | Feasibility is checked with the help of Business Case and presented to Management for approval. | Understand basic requirement
Calculate tentative BOM cost
Submit BOM cost to Commercial dept. for further pricing
|  | Toll Gate 0 Review & Approval | Project kill or Project go ahead in next stage
| Product Feasibility Stage TG-1 | Kickoff Meeting is held to select Project Manager and Cross Function Team (CFT)
Design Team Selection
|  | K-1 Kaizen on VOC with CFT | Find competitiors products
Analysis via website or online
Arrange product for deep analysis
Testing of competitor product
BOM analysis of competitor product
Make House of Quality
|  | Customer Requirements (Functional Specification) | Home work to collect requirements
Meeting to consolidated all requirements
Review of FS
Approval of FS
|  | Long Lead Time Raw Material Items identification Start | Brainstorming
|  | Project Planning | Identify the Target complete date
Identify the required resources
Arrange and manage the resources
Note down all required activities
Schedule all activities according to resopurces availabity and target end date
Review of Planning
Approval of Planning
|  | Toll Gate 1 Review & Approval | Project kill or Project go ahead in next stage
| Product Design Stage TG-2 | Product Design (Schematic on Paper, BOM, collection of new components data sheet) | Collect all reference design details
Make block diagram
Distribute work to all three verticals like firmware, hardware & Mechanical
Make circuits
Design Review
Modules Testing
PCB layout
Mechanical design
Review
Modules Integration and testing on board
Review
Modules Integration in Chassis
|  | Kaizen K2 is applied for final Design Inputs related to DFMA | With production Quality & Servicing
Design testing in Chassis
PCB, Power Components, Heat Sink, Harness and Chassis Modification IF REQUIRED
Development of Jig and Fixtures, Action for User Manual, Packaging, Documents, and Art work
Review
Design Validation (Internal)
Changes done (if necessary) and affected areas are re-verified and re-validated
Documentation is prepared to support CFT.
Review
Design FMEA
Design release for Pilot Production
Toll Gate 2 Review & Approval
| Pilot Production Stage TG-3 | Conduct Pilot Production
Pilot Production MOM
Review
Necessary changes are done (If Required)
Toll Gate 3 Review & Approval
| Mass production Stage TG-4 | Field Validation
Customer feedback and Improvement
Review
Toll Gate 4 Review & Approval