## Projects Summary
Project Name | Project Manager | Creatred On | Time Line | Status | Last Published | Project Tasks Status | Last Timesheet Details | Remarks
10KW/120V MPPT PCU Kaizen | Umesh Likhitkar | 2021-08-04 | 02-08-2021 31-08-2021 | In Progress | 7th Oct | Link | Link
Android Application Design | Bharti Sharma | 2021-10-19 | 19-10-2021 30-04-2022 | In Progress | 29th Oct | Link | Link
Charger Discharger CD1233 | Abhishek Gupta | 2021-08-24 | 24-08-2021 30-11-2021 | In Progress | 13th Oct | Link | Link
Different Types Of Tuning Tool Design | Bharti Sharma | 2021-10-14 | 14-10-2021 30-04-2022 | In Progress | 25th Nov | Link | Link
EV CHARGER 3KW (30A) | Jalaj Mathur | 2021-10-28 | 28-10-2021 31-01-2022 | In Progress | 30th Nov | Link | Link
SUPPORT ACTIVITIES | Jalaj Mathur | 2021-08-03 | 03-08-2021 31-03-2022 | In Progress | 3rd Dec
Tuning tool Data save in Excel format | Bharti Sharma | 2021-11-13 | 15-11-2021 20-11-2021 | In Progress | 25th Nov | Link | Link
1000w 24V (USING 4 NO. CORE TX.) UPS | Syojiram Sharma | 2021-11-30 | 23-11-2021 20-12-2021 | Draft
Android Application Development | Bharti Sharma | 2021-09-01 | 01-09-2021 30-09-2021 | Draft
BMS 12V 10A | Shweta Aggarwal | 2021-10-23 | 23-10-2021 20-11-2021 | Draft
BMS 50A/48V | Raghvendra Thakur | 2021-08-04 | 01-08-2021 04-10-2021 | Draft | 20th Oct |  | Link | It is un published on 24th Nov.21 for re-planning, but still not re published
MPPT20A/12V | Syojiram Sharma | 2021-11-24 | 15-11-2021 15-12-2021 | Draft
Prototype Smart Switch Concept | Sobhag Prajapat | 2021-10-08 | 08-10-2021 30-10-2021 | Draft
Solar charger with FM | Syojiram Sharma | 2021-11-16 | 16-11-2021 15-12-2021 | Draft
800 Watt 12 V 18Amp | Deepesh Jain | 2021-08-17 | 19-08-2021 11-09-2021 | Completed
Booster 48/60V 15/12A | Sobhag Prajapat | 2021-08-24 | 24-08-2021 30-09-2021 | Completed
Invo charger 12/24 15A | Sobhag Prajapat | 2021-08-24 | 24-08-2021 30-09-2021 | Completed

## EV Charger 3KW
EV CHARGER 3KW (30A)
Task | Oct 28, 2021 |  |  | Oct 30, 2021 |  |  | Nov 13, 2021 |  |  | Nov 30, 2021
| Planned Start | Planned End | Approved | Planned Start | Planned End | Approved | Planned Start | Planned End | Approved | Planned Start | Planned End | Approved
Start | Oct 28, 2021 | Oct 28, 2021 | No | Oct 28, 2021 | Oct 28, 2021 | Yes | Oct 28, 2021 | Oct 28, 2021 | Yes | Oct 28, 2021 | Oct 28, 2021 | Yes
Toll Gate 0 | Oct 28, 2021 | Oct 29, 2021 | No | Oct 28, 2021 | Oct 29, 2021 | Yes | Oct 28, 2021 | Oct 29, 2021 | Yes | Oct 28, 2021 | Oct 29, 2021 | Yes
Toll Gate 1 | Oct 29, 2021 | Oct 30, 2021 | No | Nov 12, 2021 | Nov 13, 2021 | No | Nov 12, 2021 | Nov 13, 2021 | Yes | Nov 12, 2021 | Nov 13, 2021 | Yes
Toll Gate 2 | Oct 30, 2021 | Nov 01, 2021 | No | Jan 29, 2022 | Jan 31, 2022 | No | Jan 29, 2022 | Jan 31, 2022 | No | Feb 08, 2022 | Feb 09, 2022 | No
Functional Specification finalization and approval | Oct 28, 2021 | Oct 29, 2021 | No | Oct 28, 2021 | Oct 29, 2021 | Yes | Oct 28, 2021 | Oct 29, 2021 | Yes | Oct 28, 2021 | Oct 29, 2021 | Yes
Meeting with Senior Management for further planning | Oct 28, 2021 | Oct 29, 2021 | No | Oct 28, 2021 | Oct 29, 2021 | No | Oct 28, 2021 | Oct 29, 2021 | Yes | Oct 28, 2021 | Oct 29, 2021 | Yes
Work to Collect data for Development Cost | - | - | - | Oct 29, 2021 | Nov 08, 2021 | No | Oct 29, 2021 | Nov 08, 2021 | Yes | Oct 29, 2021 | Nov 08, 2021 | Yes
Calculate & Review the Development Cost | - | - | - | Nov 08, 2021 | Nov 12, 2021 | No | Nov 08, 2021 | Nov 12, 2021 | Yes | Nov 08, 2021 | Nov 12, 2021 | Yes
Work to collect data for BOM costing | - | - | - | Oct 29, 2021 | Nov 08, 2021 | No | Oct 29, 2021 | Nov 08, 2021 | Yes | Oct 29, 2021 | Nov 08, 2021 | Yes
Calculate & Review the BOM cost | - | - | - | Nov 08, 2021 | Nov 12, 2021 | No | Nov 08, 2021 | Nov 12, 2021 | No | Nov 08, 2021 | Nov 12, 2021 | No
Competitors products identification | - | - | - | Oct 29, 2021 | Nov 01, 2021 | No | Oct 29, 2021 | Nov 01, 2021 | Yes | Oct 29, 2021 | Nov 01, 2021 | Yes
Competitors Product detailed analysis via website and other sources | - | - | - | Nov 01, 2021 | Nov 08, 2021 | No | Nov 01, 2021 | Nov 08, 2021 | Yes | Nov 01, 2021 | Nov 08, 2021 | Yes
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | - | - | - | Nov 08, 2021 | Nov 09, 2021 | No | Nov 08, 2021 | Nov 09, 2021 | Yes | Nov 08, 2021 | Nov 09, 2021 | Yes
Take necessary actions like sourcing, PR & PO & approval to arrange competitor's products | - | - | - | Nov 09, 2021 | Nov 12, 2021 | No | Nov 13, 2021 | Nov 17, 2021 | No | Nov 13, 2021 | Nov 17, 2021 | No
K1 Kaizen (House of Quality) | - | - | - | Nov 09, 2021 | Nov 11, 2021 | No | Nov 15, 2021 | Nov 22, 2021 | No | Nov 15, 2021 | Nov 22, 2021 | No
Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | - | - | - | Nov 11, 2021 | Nov 12, 2021 | No | Nov 13, 2021 | Nov 15, 2021 | No | Nov 13, 2021 | Nov 15, 2021 | Yes
Planning and Monitoring | - | - | - | Oct 29, 2021 | Jan 29, 2022 | No | Oct 29, 2021 | Jan 29, 2022 | No | Oct 29, 2021 | Jan 29, 2022 | No
Block Diagram Making & Review | - | - | - | - | - | - | Nov 13, 2021 | Nov 15, 2021 | No | Nov 13, 2021 | Nov 15, 2021 | Yes
Modules Wise Component Selection 1. Talk to companies 2. Datasheet Analysis 3. DAR to select components | - | - | - | - | - | - | Nov 15, 2021 | Nov 17, 2021 | No | Nov 15, 2021 | Nov 17, 2021 | Yes
Circuit Making on Paper and on zero board, testing | - | - | - | - | - | - | Nov 17, 2021 | Nov 22, 2021 | No | Nov 17, 2021 | Nov 22, 2021 | Yes
Team Meeting : 1. Project Status 2. I/P for Sample arrangement 3. Risk Status | - | - | - | - | - | - | Nov 22, 2021 | Nov 23, 2021 | No | Nov 22, 2021 | Nov 23, 2021 | Yes
Necessary action to arrange components samples | - | - | - | - | - | - | Nov 23, 2021 | Nov 25, 2021 | No | Nov 23, 2021 | Nov 25, 2021 | No
Circuit making on Altium and Review | - | - | - | - | - | - | Nov 23, 2021 | Nov 25, 2021 | No | Dec 03, 2021 | Dec 08, 2021 | No
PCB layout on Altium and Review | - | - | - | - | - | - | Nov 25, 2021 | Nov 30, 2021 | No | Dec 10, 2021 | Dec 16, 2021 | No
Mechanical, aesthetic concept input collection | - | - | - | - | - | - | Nov 23, 2021 | Nov 25, 2021 | No | Nov 29, 2021 | Dec 03, 2021 | No
Competitors product evaluation -Overview -Testing -BOM | - | - | - | - | - | - | Nov 30, 2021 | Dec 07, 2021 | No | Dec 10, 2021 | Dec 20, 2021 | No
Mechanical drawings making and Review | - | - | - | - | - | - | Dec 04, 2021 | Dec 11, 2021 | No | Dec 14, 2021 | Dec 21, 2021 | No
Necessary action to arrange PCB samples from vendor | - | - | - | - | - | - | Nov 30, 2021 | Dec 02, 2021 | No | Dec 16, 2021 | Dec 18, 2021 | No
Firmware making preparations | - | - | - | - | - | - | Nov 23, 2021 | Nov 27, 2021 | No | Nov 23, 2021 | Nov 27, 2021 | No
Module test cases preparation for PCBs (Hardware & Firmware) | - | - | - | - | - | - | Nov 30, 2021 | Dec 06, 2021 | No | Dec 16, 2021 | Dec 22, 2021 | No
Team Meeting : 1. PCB & Test case status 2. Mechanical drawings status 3. Competitors product evaluation status. 4. Long Lead Items updation 5. Risk Management status. | - | - | - | - | - | - | Dec 11, 2021 | Dec 13, 2021 | No | Dec 22, 2021 | Dec 23, 2021 | No
Necessary actions to arrange mechanical items samples | - | - | - | - | - | - | Dec 13, 2021 | Dec 15, 2021 | No | Dec 23, 2021 | Dec 25, 2021 | No
BOM update in SAP | - | - | - | - | - | - | Dec 13, 2021 | Dec 15, 2021 | No | Dec 23, 2021 | Dec 25, 2021 | No
PCBs assembly | - | - | - | - | - | - | Dec 16, 2021 | Dec 18, 2021 | No | Dec 27, 2021 | Dec 29, 2021 | No
PCB testing with available hardware, firmware and software. | - | - | - | - | - | - | Dec 18, 2021 | Dec 23, 2021 | No | Dec 29, 2021 | Jan 03, 2022 | No
Mechanical items verification according to test cases | - | - | - | - | - | - | Dec 23, 2021 | Dec 28, 2021 | No | Jan 03, 2022 | Jan 07, 2022 | No
Integration test cases making | - | - | - | - | - | - | Dec 15, 2021 | Dec 17, 2021 | No | Dec 25, 2021 | Dec 28, 2021 | No
Integration and testing 1. Assembled whole product 2. Integrate firmware, and hardware. 3. Testing | - | - | - | - | - | - | Dec 28, 2021 | Jan 05, 2022 | No | Jan 07, 2022 | Jan 15, 2022 | No
Artwork related inputs collection and given to branding team for preparation and check. | - | - | - | - | - | - | Dec 28, 2021 | Jan 01, 2022 | No | Jan 07, 2022 | Jan 12, 2022 | No
After testing BOM updation in SAP | - | - | - | - | - | - | Jan 05, 2022 | Jan 07, 2022 | No | Jan 15, 2022 | Jan 18, 2022 | No
Team Meeting : 1. Project status. 2. Validation handover 3. Risk and issues. 4. DFMA 5. BOM cost | - | - | - | - | - | - | Jan 07, 2022 | Jan 08, 2022 | No | Jan 18, 2022 | Jan 19, 2022 | No
Resolution steps for DFMA points | - | - | - | - | - | - | Jan 08, 2022 | Jan 11, 2022 | No | Jan 19, 2022 | Jan 21, 2022 | No
Validation : 1. BOM verification 2. Functional testing 3. Reliability Testing 4. Destructive Testing 5. Documents making and verification | - | - | - | - | - | - | Jan 08, 2022 | Jan 26, 2022 | No | Jan 19, 2022 | Feb 05, 2022 | No
DFMA Activity with Production, Quality & Resolutions | - | - | - | - | - | - | Jan 11, 2022 | Jan 18, 2022 | No | Jan 21, 2022 | Jan 28, 2022 | No
Team Meeting : 1. FMEA with design team. 2. DFMA status 3. Documents status 4. BOM status 5. Release schedule. | - | - | - | - | - | - | Jan 22, 2022 | Jan 25, 2022 | No | Feb 02, 2022 | Feb 04, 2022 | No
BOMs updation in SAP, Review and Release | - | - | - | - | - | - | Jan 26, 2022 | Jan 28, 2022 | No | Feb 05, 2022 | Feb 08, 2022 | No
Documents finalize and upload in SAP (Artworks, QA, LT, specs, testing/troubleshooting/operating procedures etc.) | - | - | - | - | - | - | Jan 25, 2022 | Jan 28, 2022 | No | Feb 04, 2022 | Feb 08, 2022 | No
End | Nov 01, 2021 | Nov 01, 2021 | No | Jan 31, 2022 | Jan 31, 2022 | No | Jan 31, 2022 | Jan 31, 2022 | No | Feb 09, 2022 | Feb 09, 2022 | No
Task ID & Description | Planned Start/End | Actual Start/End | Sch. Variance | Planned Efforts | Actual Efforts | Effort Variance | Planned Cost | Actual Cost | Cost Variance
[370] Start | Oct 28, 2021 | Oct 28, 2021 | 0% | 0 | 0.08 | 100% | 0 | 1.2 | 100%
Latest Comments: | Oct 28, 2021 | Oct 28, 2021
OK lets start
Jalaj Mathur [1%]
[371] Toll Gate 0 | Oct 28, 2021 | Oct 28, 2021 | -50% | 0.32 | 0.34 | 6% | 34.4 | 19.55 | -43%
Latest Comments: | Oct 29, 2021 | Oct 28, 2021
30/10/21 : Toll gate review completed and go with some action items
Jalaj Mathur [2%]Tarun Gupta [2%]
[375] Functional Specification finalization and approval | Oct 28, 2021 | Oct 28, 2021 | -50% | 1.6 | 0.75 | -53% | 181.6 | 32 | -82%
Latest Comments: | Oct 29, 2021 | Oct 28, 2021
30/10/21 : FS final view done and approved by TG
Jalaj Mathur [5%]Sobhag Prajapat [10%]Tarun Gupta [5%]
[376] Meeting with Senior Management for further planning | Oct 28, 2021 | Oct 28, 2021 | 50% | 2.4 | 3.85 | 60% | 272.8 | 112.52 | -59%
Latest Comments: | Oct 29, 2021 | Oct 30, 2021
30/10/21 : Draft planning finalized, and till TG1 planning released.
Jalaj Mathur [10%]Sobhag Prajapat [10%]Tarun Gupta [10%]
[382] Competitors products identification | Oct 29, 2021 | Nov 01, 2021 | 0% | 0.8 | 1.17 | 46% | 10.4 | 15.21 | 46%
Latest Comments: | Nov 01, 2021 | Nov 01, 2021
01/11/21 : Identification completed 31/10/21 : Working and see Okaya as competitors, will complete on 1st Nov.21
Sobhag Prajapat [5%]
[378] Work to Collect data for Development Cost | Oct 29, 2021 | Nov 11, 2021 | 27.27% | 3.2 | 1 | -69% | 41.6 | 13 | -69%
Latest Comments: | Nov 08, 2021 | Nov 11, 2021
11/11/21 : Raw data captured for calculate. 09/11/21 : Sobhag please convey the status. 01/11/21 : Will start work from today; Sobhag please confirm the status
Sobhag Prajapat [10%]
[380] Work to collect data for BOM costing | Oct 29, 2021 | Nov 02, 2021 | -54.55% | 9.6 | 3.17 | -67% | 270.4 | 45.55 | -83%
Latest Comments: | Nov 08, 2021 | Nov 02, 2021
09/11/21 : The BOM sheet received from Sobhag for further costing. 01/11/21 : Will start work from today; Sobhag please confirm the status
Jalaj Mathur [5%]Rohit Kumar Sachan [10%]Shweta Aggarwal [5%]Sobhag Prajapat [10%]
[388] Planning and Monitoring | Oct 29, 2021 | Oct 30, 2021 | 0% | 30 | 7.84 | -74% | 450 | 117.6 | -74%
Jalaj Mathur [5%] | Jan 29, 2022 | -
[383] Competitors Product detailed analysis via website and other sources | Nov 01, 2021 | Nov 01, 2021 | -87.5% | 3.2 | 1.5 | -53% | 54.4 | 19.5 | -64%
Latest Comments: | Nov 08, 2021 | Nov 01, 2021
01/11/21 : According to competitors specs, some spec parameter of our model updated.
Rohit Kumar Sachan [10%]Sobhag Prajapat [10%]
[384] Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Nov 08, 2021 | Nov 02, 2021 | -50% | 3.6 | 7 | 94% | 230.8 | 84.75 | -63%
Latest Comments: | Nov 09, 2021 | Nov 08, 2021
02/11/21 : Meeting done. 01/11/21 : Meeting called on 2nd Nov.21 morning.
Abhishek Gupta [5%]Bharti Sharma [5%]Deepesh Jain [5%]Dhirendra Rai [5%]Jalaj Mathur [5%]Rohit Kumar Sachan [5%]Sandeep Jain [5%]Shweta Aggarwal [5%]Sobhag Prajapat [5%]
[379] Calculate & Review the Development Cost | Nov 08, 2021 | Nov 11, 2021 | -20% | 3.84 | 1 | -74% | 449.6 | 15 | -97%
Latest Comments: | Nov 12, 2021 | Nov 11, 2021
11/11/21 : Calculated and keep in process folder as TG0 folder.
Jalaj Mathur [5%]Sobhag Prajapat [5%]Tarun Gupta [2%]
[381] Calculate & Review the BOM cost | Nov 08, 2021 | Nov 09, 2021 | 0% | 5.44 | 5.01 | -8% | 654.4 | 75.15 | -89%
Latest Comments: | Nov 12, 2021 | -
17/11/21 : Pending as unable to spare time for this. 12/11/21 : Some part calculated, created on google sheet. 09/11/21 : Will calculate from today.
Jalaj Mathur [10%]Sobhag Prajapat [5%]Tarun Gupta [2%]
[372] Toll Gate 1 | Nov 12, 2021 | Nov 13, 2021 | 0% | 0.32 | 0.34 | 6% | 34.4 | 19.55 | -43%
Latest Comments: | Nov 13, 2021 | Nov 13, 2021
13//11/21 : Reviewed, and go with action items 12/11/21 : Will do second half of 13th.
Jalaj Mathur [2%]Tarun Gupta [2%]
[387] Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | Nov 13, 2021 | Nov 12, 2021 | 0% | 2 | 6.5 | 225% | 79.6 | 87.31 | 10%
Latest Comments: | Nov 15, 2021 | Nov 15, 2021
15/11/21 : Meeting done, 2 risks identified, planning communicated and discussed, for long lead items, HOQ team will work.
Abhishek Gupta [5%]Jalaj Mathur [5%]Rohit Kumar Sachan [5%]Sandeep Jain [5%]Sobhag Prajapat [5%]
[389] Block Diagram Making & Review | Nov 13, 2021 | Nov 15, 2021 | 0% | 0.4 | 4 | 900% | 45.44 | 42 | -8%
Latest Comments: | Nov 15, 2021 | Nov 15, 2021
16/11/21 : Block diagram made more professionally, using some online tool, so some more efforts spent.
Rohit Kumar Sachan [2%]Sobhag Prajapat [2%]Tarun Gupta [1%]
[385] Take necessary actions like sourcing, PR & PO & approval to arrange competitor's products | Nov 13, 2021 | Nov 10, 2021 | 0% | 2.4 | 1 | -58% | 43.2 | 18 | -58%
Latest Comments: | Nov 17, 2021 | -
04/12/21 : No further update received 20/11/21 : No further update received. 17/11/21 : No update received. 12/11/21 : Tarun ji conveyed that information passed to Harsh for his help to arrange the product. 11/11/21 : Sandeep ji asked to Tarun ji for sourcing 09/11/21 : Model name already conveyed to Sandeep sir, for procuring process.
Sandeep Jain [10%]
[390] Modules Wise Component Selection 1. Talk to companies 2. Datasheet Analysis 3. DAR to select components | Nov 15, 2021 | Nov 16, 2021 | 0% | 1.92 | 4.17 | 117% | 37.76 | 33.36 | -12%
Latest Comments: | Nov 17, 2021 | Nov 17, 2021
20/11/21 : Its completed on 17th Nov.21.
Rohit Kumar Sachan [10%]Sobhag Prajapat [2%]
[386] K1 Kaizen (House of Quality) | Nov 15, 2021 | Nov 12, 2021 | 0% | 12.96 | 5.16 | -60% | 1800 | 143.69 | -92%
Latest Comments: | Nov 22, 2021 | -
04/12/21 : Competitors products not received, so not completed. 20/11/21 : No further update. 16/11/21 : Customer requirements, and technical terms and their weights put in format. 12/11/21 : Understand the format by example, will fill for this project. 11/11/21 : Due to DRM, it will schedule on 12th Nov.21 morning. 09/11/21 : Will schedule on 11th second half.
Abhishek Gupta [5%]Dhirendra Rai [5%]Jalaj Mathur [5%]Sandeep Jain [5%]Sobhag Prajapat [5%]Tarun Gupta [2%]
[391] Circuit Making on Paper and on zero board, testing | Nov 17, 2021 | Nov 20, 2021 | 33.33% | 8 | 4 | -50% | 155.2 | 32 | -79%
Latest Comments: | Nov 22, 2021 | Nov 24, 2021
25/11/21 : On paper its done. 20/11/21 : This task delayed due to Rohit one day not available and now busy in other project, it will start either today or from Monday (22/11).
Rohit Kumar Sachan [20%]Sobhag Prajapat [5%]
[392] Team Meeting : 1. Project Status 2. I/P for Sample arrangement 3. Risk Status | Nov 22, 2021 | Nov 15, 2021 | 300% | 0.96 | 2.74 | 185% | 43.68 | 27.63 | -37%
Latest Comments: | Nov 23, 2021 | Nov 29, 2021
25/11/21 : Delayed due to all stack holders not available.
Abhishek Gupta [2%]Dhirendra Rai [2%]Jalaj Mathur [2%]Rohit Kumar Sachan [2%]Sandeep Jain [2%]Sobhag Prajapat [2%]
[393] Necessary action to arrange components samples | Nov 23, 2021 | - | 0% | 1.6 | 0 | -100% | 28.8 | 0 | -100%
Latest Comments: | Nov 25, 2021 | -
04/12/21 : List not provided to Sandeep ji. 25/11/21 : Depend upon team meeting, will do after or parallel that.
Sandeep Jain [10%]
[400] Firmware making preparations | Nov 23, 2021 | Nov 29, 2021 | 0% | 12.8 | 9.58 | -25% | 102.4 | 76.64 | -25%
Latest Comments: | Nov 27, 2021 | -
04/12/21 : No further update received.
Abhishek Gupta [40%]
[396] Mechanical, aesthetic concept input collection | Nov 29, 2021 | Dec 03, 2021 | 0% | 12.8 | 2 | -84% | 432 | 36 | -92%
Latest Comments: | Dec 03, 2021 | -
04/12/21 : No further update received. 25/11/21 : Will do when Sandeep ji & Bharat will come from tour.
Bharat Kakra [10%]Rohit Kumar Sachan [10%]Sandeep Jain [10%]Sobhag Prajapat [10%]
[394] Circuit making on Altium and Review | Dec 03, 2021 | - | 0% | 35.2 | 0 | -100% | 953.6 | 0 | -100%
Latest Comments: | Dec 08, 2021 | -
04/12/21 : Yesterday Rakesh ji was on leave, today will try to reach him.
Rakesh Pandey [50%]Rohit Kumar Sachan [50%]Sobhag Prajapat [10%]
[395] PCB layout on Altium and Review | Dec 10, 2021 | - | 0% | 48 | 0 | -100% | 1424 | 0 | -100%
Latest Comments: | Dec 16, 2021 | -
04/12/21 : It will delay as circuit not made yet.
Rakesh Pandey [80%]Rohit Kumar Sachan [20%]Sobhag Prajapat [20%]
[397] Competitors product evaluation -Overview -Testing -BOM | Dec 10, 2021 | - | 0% | 196.48 | 0 | -100% | 8840.32 | 0 | -100%
Latest Comments: | Dec 20, 2021 | -
04/12/21 : It will delay as no update received regarding products arrangement.
Bharat Kakra [5%]CRO 4 CHANNELS TEKTRONIX TPS2024 [50%]Dhirendra Rai [40%]IR THERMO METER [50%]Jalaj Mathur [2%]LCR METER [10%]POWER ANALYZER WT 330 [40%]POWER SUPPLY CHROMA 62100H-450 [20%]Rohit Kumar Sachan [40%]Sandeep Jain [10%]Sobhag Prajapat [20%]TEMPERATURE SENSOR TOOL [20%]
[398] Mechanical drawings making and Review | Dec 14, 2021 | - | 0% | 76.8 | 0 | -100% | 3168 | 0 | -100%
Bharat Kakra [80%]Rohit Kumar Sachan [40%]Sandeep Jain [20%]Sobhag Prajapat [20%] | Dec 21, 2021 | -
[399] Necessary action to arrange PCB samples from vendor | Dec 16, 2021 | - | 0% | 1.6 | 0 | -100% | 28.8 | 0 | -100%
Sandeep Jain [10%] | Dec 18, 2021 | -
[401] Module test cases preparation for PCBs (Hardware & Firmware) | Dec 16, 2021 | - | 0% | 16 | 0 | -100% | 416 | 0 | -100%
Abhishek Gupta [10%]Dhirendra Rai [10%]Rohit Kumar Sachan [10%]Sobhag Prajapat [10%] | Dec 22, 2021 | -
[402] Team Meeting : 1. PCB & Test case status 2. Mechanical drawings status 3. Competitors product evaluation status. 4. Long Lead Items updation 5. Risk Management status. | Dec 22, 2021 | - | 0% | 2.8 | 0 | -100% | 145.2 | 0 | -100%
Abhishek Gupta [5%]Bharat Kakra [5%]Dhirendra Rai [5%]Jalaj Mathur [5%]Rohit Kumar Sachan [5%]Sandeep Jain [5%]Sobhag Prajapat [5%] | Dec 23, 2021 | -
[403] Necessary actions to arrange mechanical items samples | Dec 23, 2021 | - | 0% | 1.6 | 0 | -100% | 28.8 | 0 | -100%
Sandeep Jain [10%] | Dec 25, 2021 | -
[404] BOM update in SAP | Dec 23, 2021 | - | 0% | 11.2 | 0 | -100% | 296 | 0 | -100%
Rohit Kumar Sachan [20%]Shweta Aggarwal [40%]Sobhag Prajapat [10%] | Dec 25, 2021 | -
[408] Integration test cases making | Dec 25, 2021 | - | 0% | 18.4 | 0 | -100% | 516 | 0 | -100%
Abhishek Gupta [5%]Dhirendra Rai [80%]Rohit Kumar Sachan [20%]Sobhag Prajapat [10%] | Dec 28, 2021 | -
[405] PCBs assembly | Dec 27, 2021 | - | 0% | 18.4 | 0 | -100% | 660 | 0 | -100%
Pawan Kumar Sharma [80%]Rakesh Pandey [10%]Rohit Kumar Sachan [20%]Sobhag Prajapat [5%] | Dec 29, 2021 | -
[406] PCB testing with available hardware, firmware and software. | Dec 29, 2021 | - | 0% | 56 | 0 | -100% | 1041.6 | 0 | -100%
Abhishek Gupta [20%]Bharti Sharma [10%]CRO 4 CHANNELS TEKTRONIX TPS2024 [40%]POWER SUPPLY CHROMA 62100H-450 [20%]Rohit Kumar Sachan [40%]Sobhag Prajapat [5%]TEMPERATURE SENSOR TOOL [40%] | Jan 03, 2022 | -
[407] Mechanical items verification according to test cases | Jan 03, 2022 | - | 0% | 25.6 | 0 | -100% | 1228.8 | 0 | -100%
Bharat Kakra [30%]Dhirendra Rai [20%]Rohit Kumar Sachan [20%]Sandeep Jain [5%]Sobhag Prajapat [5%] | Jan 07, 2022 | -
[410] Artwork related inputs collection and given to branding team for preparation and check. | Jan 07, 2022 | - | 0% | 19.2 | 0 | -100% | 736 | 0 | -100%
Jalaj Mathur [20%]Rohit Kumar Sachan [20%]Sandeep Jain [10%]Sobhag Prajapat [10%] | Jan 12, 2022 | -
[409] Integration and testing 1. Assembled whole product 2. Integrate firmware, and hardware. 3. Testing | Jan 07, 2022 | - | 0% | 274.4 | 0 | -100% | 7117.6 | 0 | -100%
Abhishek Gupta [20%]CRO 4 CHANNELS TEKTRONIX TPS2024 [40%]CRO FLUKE 190-204 [20%]Dhirendra Rai [80%]Heat Chamber Setup [50%]IR THERMO METER [70%]POWER ANALYZER WT 330 [40%]POWER SUPPLY CHROMA 62100H-450 [30%]Ramashish Kumar [50%]Rohit Kumar Sachan [20%]Sobhag Prajapat [10%]Stabilizer Test Setup [20%]TEMPERATURE SENSOR TOOL [40%] | Jan 15, 2022 | -
[411] After testing BOM updation in SAP | Jan 15, 2022 | - | 0% | 12 | 0 | -100% | 343.2 | 0 | -100%
Dhirendra Rai [10%]Rohit Kumar Sachan [10%]Shweta Aggarwal [50%]Sobhag Prajapat [5%] | Jan 18, 2022 | -
[412] Team Meeting : 1. Project status. 2. Validation handover 3. Risk and issues. 4. DFMA 5. BOM cost | Jan 18, 2022 | - | 0% | 6.8 | 0 | -100% | 485.2 | 0 | -100%
Abhishek Gupta [10%]Bharat Kakra [10%]Bharti Sharma [5%]Deepesh Jain [10%]Dhirendra Rai [10%]Jalaj Mathur [5%]Rohit Kumar Sachan [10%]Sandeep Jain [10%]Shweta Aggarwal [5%]Sobhag Prajapat [10%] | Jan 19, 2022 | -
[413] Resolution steps for DFMA points | Jan 19, 2022 | - | 0% | 6.4 | 0 | -100% | 219.2 | 0 | -100%
Rakesh Pandey [10%]Rohit Kumar Sachan [10%]Sandeep Jain [10%]Sobhag Prajapat [10%] | Jan 21, 2022 | -
[414] Validation : 1. BOM verification 2. Functional testing 3. Reliability Testing 4. Destructive Testing 5. Documents making and verification | Jan 19, 2022 | - | 0% | 511.2 | 0 | -100% | 20377.2 | 0 | -100%
Abhishek Gupta [20%]CRO 4 CHANNELS TEKTRONIX TPS2024 [50%]CRO FLUKE 190-204 [20%]Deepesh Jain [70%]Dhirendra Rai [10%]Heat Chamber Setup [50%]Jalaj Mathur [1%]Pawan Kumar Sharma [10%]POWER ANALYZER WT 330 [30%]POWER SUPPLY CHROMA 62100H-450 [40%]Ramashish Kumar [10%]Rohit Kumar Sachan [20%]Sobhag Prajapat [5%]Stabilizer Test Setup [40%]TEMPERATURE SENSOR TOOL [50%] | Feb 05, 2022 | -
[415] DFMA Activity with Production, Quality & Resolutions | Jan 21, 2022 | - | 0% | 51.84 | 0 | -100% | 8015.52 | 0 | -100%
Bharat Kakra [10%]Deepesh Jain [5%]Dhirendra Rai [10%]Jalaj Mathur [2%]Rakesh Pandey [10%]Rohit Kumar Sachan [20%]Sandeep Jain [20%]Shweta Aggarwal [10%]Sobhag Prajapat [20%]Tarun Gupta [1%] | Jan 28, 2022 | -
[416] Team Meeting : 1. FMEA with design team. 2. DFMA status 3. Documents status 4. BOM status 5. Release schedule. | Feb 02, 2022 | - | 0% | 9.6 | 0 | -100% | 516 | 0 | -100%
Abhishek Gupta [0%]Deepesh Jain [10%]Dhirendra Rai [10%]Jalaj Mathur [5%]Rohit Kumar Sachan [10%]Sandeep Jain [10%]Shweta Aggarwal [5%]Sobhag Prajapat [10%] | Feb 04, 2022 | -
[418] Documents finalize and upload in SAP (Artworks, QA, LT, specs, testing/troubleshooting/operating procedures etc.) | Feb 04, 2022 | - | 0% | 15.6 | 0 | -100% | 495.6 | 0 | -100%
Deepesh Jain [20%]Jalaj Mathur [5%]Shweta Aggarwal [20%]Sobhag Prajapat [20%] | Feb 08, 2022 | -
[417] BOMs updation in SAP, Review and Release | Feb 05, 2022 | - | 0% | 12.8 | 0 | -100% | 377.6 | 0 | -100%
Deepesh Jain [20%]Pawan Kumar Sharma [10%]Shweta Aggarwal [40%]Sobhag Prajapat [10%] | Feb 08, 2022 | -
[373] Toll Gate 2 | Feb 08, 2022 | - | 0% | 0.8 | 0 | -100% | 86 | 0 | -100%
Jalaj Mathur [5%]Tarun Gupta [5%] | Feb 09, 2022 | -
[374] End | Feb 09, 2022 | - | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Jalaj Mathur [1%] | Feb 09, 2022 | -
TASK NAME / ACTION ITEM | PROJECT MANAGER | OWNER | FROM | TO | ACTIVITY DESCRIPTION | ACTIVITY DESCRIPTION
Start | Jalaj Mathur | Jalaj Mathur | Oct 28,2021 05:30:00 PM | Oct 28,2021 05:35:00 PM | Made and start the project | Made and start the project
Toll Gate 0 | Jalaj Mathur | Jalaj Mathur | Oct 28,2021 05:45:00 PM | Oct 28,2021 05:55:00 PM | Review done with Tarun sir | Review done with Tarun sir
Functional Specification finalization and approval | Jalaj Mathur | Jalaj Mathur | Oct 28,2021 05:55:00 PM | Oct 28,2021 06:10:00 PM | Finalize specs shown to Tarun sir, and take confirmation as approval | Finalize specs shown to Tarun sir, and take confirmation as approval
Meeting with Senior Management for further planning | Jalaj Mathur | Jalaj Mathur | Oct 28,2021 06:10:00 PM | Oct 28,2021 06:35:00 PM | Note down the tasks / steps need to do in project | Note down the tasks / steps need to do in project
Meeting with Senior Management for further planning | Jalaj Mathur | Sobhag Prajapat | Oct 28,2021 06:10:00 PM | Oct 28,2021 06:35:00 PM | team meeting with tarun sir | team meeting with tarun sir
Functional Specification finalization and approval | Jalaj Mathur | Sobhag Prajapat | Oct 28,2021 05:55:00 PM | Oct 28,2021 06:10:00 PM | making FS | making FS
Toll Gate 0 | Jalaj Mathur | Tarun Gupta | Oct 28,2021 05:45:00 PM | Oct 28,2021 05:55:00 PM | Reviewed | Reviewed
Functional Specification finalization and approval | Jalaj Mathur | Tarun Gupta | Oct 28,2021 05:55:00 PM | Oct 28,2021 06:10:00 PM | Discussed and finalized | Discussed and finalized
Meeting with Senior Management for further planning | Jalaj Mathur | Jalaj Mathur | Oct 30,2021 10:40:00 AM | Oct 30,2021 11:20:00 AM | Discussed the possible activities for planning | Discussed the possible activities for planning
Meeting with Senior Management for further planning | Jalaj Mathur | Jalaj Mathur | Oct 30,2021 12:00:00 PM | Oct 30,2021 01:00:00 PM | As per discussion made draft plan on paper and put in Einframe | As per discussion made draft plan on paper and put in Einframe
Meeting with Senior Management for further planning | Jalaj Mathur | Tarun Gupta | Oct 30,2021 10:40:00 AM | Oct 30,2021 11:20:00 AM | Discussed the possible activities for planning | Discussed the possible activities for planning
Meeting with Senior Management for further planning | Jalaj Mathur | Sobhag Prajapat | Oct 30,2021 10:40:00 AM | Oct 30,2021 11:20:00 AM | meeting with tarun sir | meeting with tarun sir
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Oct 30,2021 04:15:00 PM | Oct 30,2021 05:00:00 PM | Till TG1 planning feed in Einframe and published | Till TG1 planning feed in Einframe and published
Competitors products identification | Jalaj Mathur | Sobhag Prajapat | Nov 01,2021 09:20:00 AM | Nov 01,2021 10:30:00 AM | find out the compititor name and product details . and share to PM on mail | find out the compititor name and product details . and share to PM on mail
Competitors Product detailed analysis via website and other sources | Jalaj Mathur | Sobhag Prajapat | Nov 01,2021 10:30:00 AM | Nov 01,2021 12:00:00 PM | campititor products spec cmpared and make analysis sheet and update our technical spec. .all data sheet stor at common drive formder share to PM | campititor products spec cmpared and make analysis sheet and update our technical spec. .all data sheet stor at common drive formder share to PM
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 01,2021 09:25:00 AM | Nov 01,2021 09:40:00 AM | Saw people timesheet, update the status of running tasks | Saw people timesheet, update the status of running tasks
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Abhishek Gupta | Nov 02,2021 11:30:00 AM | Nov 02,2021 12:15:00 PM | Discussion of the competitor and specs | Discussion of the competitor and specs
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Deepesh Jain | Nov 02,2021 11:30:00 AM | Nov 02,2021 12:30:00 PM | Attend meeting, gave product related suggestions | Attend meeting, gave product related suggestions
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Shweta Aggarwal | Nov 02,2021 11:30:00 AM | Nov 02,2021 12:15:00 PM | kick off meeting to understand project and related tasks | kick off meeting to understand project and related tasks
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Jalaj Mathur | Nov 02,2021 11:30:00 AM | Nov 02,2021 12:30:00 PM | Discussed with team and MOM created | Discussed with team and MOM created
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Sobhag Prajapat | Nov 02,2021 11:45:00 AM | Nov 02,2021 12:15:00 PM | kick off meeting ,compititor product request done wia request google form | kick off meeting ,compititor product request done wia request google form
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Bharti Sharma | Nov 02,2021 11:30:00 AM | Nov 02,2021 12:30:00 PM | attend the meeting of new project "EV Charger 3KW (30A).Tuning tool related task has assigned to me . | attend the meeting of new project "EV Charger 3KW (30A).Tuning tool related task has assigned to me .
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Rohit Kumar Sachan | Nov 02,2021 11:30:00 AM | Nov 02,2021 12:15:00 PM | Attend | Attend
Work to collect data for BOM costing | Jalaj Mathur | Sobhag Prajapat | Nov 02,2021 02:00:00 PM | Nov 02,2021 03:00:00 PM | Bom sheet making | Bom sheet making
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Bharti Sharma | Nov 08,2021 02:30:00 PM | Nov 08,2021 03:00:00 PM | I have studied of EV Charger 3KW Projects. | I have studied of EV Charger 3KW Projects.
Kick Off Meeting : 1. Select CFT & Design Team 2. Discuss the Planning 3. Give inputs for arrangement of competitors product | Jalaj Mathur | Sandeep Jain | Nov 02,2021 11:30:00 AM | Nov 02,2021 12:15:00 PM | Discussed Project overview | Discussed Project overview
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 09,2021 11:00:00 AM | Nov 09,2021 11:15:00 AM | Monitored the timesheets, follow up on task and timesheet entries and update the status of running and upcoming tasks | Monitored the timesheets, follow up on task and timesheet entries and update the status of running and upcoming tasks
Calculate & Review the BOM cost | Jalaj Mathur | Jalaj Mathur | Nov 09,2021 11:15:00 AM | Nov 09,2021 12:00:00 PM | Worked on BOM cost arrangements. | Worked on BOM cost arrangements.
Calculate & Review the BOM cost | Jalaj Mathur | Jalaj Mathur | Nov 09,2021 12:45:00 PM | Nov 09,2021 01:10:00 PM | Worked on BOM cost arrangements. | Worked on BOM cost arrangements.
Calculate & Review the BOM cost | Jalaj Mathur | Jalaj Mathur | Nov 09,2021 02:10:00 PM | Nov 09,2021 04:50:00 PM | Worked on BOM cost arrangements. | Worked on BOM cost arrangements.
Work to collect data for BOM costing | Jalaj Mathur | Jalaj Mathur | Nov 02,2021 02:00:00 PM | Nov 02,2021 04:10:00 PM | Discussion, help to make sheet, further working | Discussion, help to make sheet, further working
Calculate & Review the BOM cost | Jalaj Mathur | Jalaj Mathur | Nov 10,2021 02:30:00 PM | Nov 10,2021 03:00:00 PM | DC DC Section BOM cost working | DC DC Section BOM cost working
Take necessary actions like sourcing, PR & PO & approval to arrange competitor's products | Jalaj Mathur | Sandeep Jain | Nov 10,2021 05:00:00 PM | Nov 10,2021 06:00:00 PM | Sourcing competitor product | Sourcing competitor product
Work to Collect data for Development Cost | Jalaj Mathur | Sobhag Prajapat | Nov 11,2021 03:30:00 PM | Nov 11,2021 04:30:00 PM | Calculate development cost | Calculate development cost
Calculate & Review the Development Cost | Jalaj Mathur | Jalaj Mathur | Nov 11,2021 03:30:00 PM | Nov 11,2021 04:30:00 PM | Calculate individual cost like manpower, tools, training etc filled in the TG review doc for database | Calculate individual cost like manpower, tools, training etc filled in the TG review doc for database
Calculate & Review the BOM cost | Jalaj Mathur | Jalaj Mathur | Nov 11,2021 02:50:00 PM | Nov 11,2021 03:30:00 PM | DC DC Section BOM cost working | DC DC Section BOM cost working
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 11,2021 04:40:00 PM | Nov 11,2021 04:55:00 PM | Update the status of on going and completed tasks, and schedule mail for K1 Kaizen activity | Update the status of on going and completed tasks, and schedule mail for K1 Kaizen activity
Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | Jalaj Mathur | Abhishek Gupta | Nov 12,2021 09:40:00 AM | Nov 12,2021 09:50:00 AM | Not present but only MCU is the item from my side. | Not present but only MCU is the item from my side.
K1 Kaizen (House of Quality) | Jalaj Mathur | Jalaj Mathur | Nov 12,2021 10:30:00 AM | Nov 12,2021 11:20:00 AM | Understand the format by taking example | Understand the format by taking example
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 12,2021 11:45:00 AM | Nov 12,2021 12:00:00 PM | Updated the status of ongoing and upcoming tasks | Updated the status of ongoing and upcoming tasks
K1 Kaizen (House of Quality) | Jalaj Mathur | Jalaj Mathur | Nov 12,2021 09:50:00 AM | Nov 12,2021 10:15:00 AM | Saw format and tries to understand | Saw format and tries to understand
K1 Kaizen (House of Quality) | Jalaj Mathur | Sobhag Prajapat | Nov 12,2021 10:30:00 AM | Nov 12,2021 11:15:00 AM | understaing with ex. | understaing with ex.
K1 Kaizen (House of Quality) | Jalaj Mathur | Tarun Gupta | Nov 12,2021 10:30:00 AM | Nov 12,2021 11:20:00 AM | Format understanding with examples | Format understanding with examples
Toll Gate 1 | Jalaj Mathur | Tarun Gupta | Nov 13,2021 10:00:00 AM | Nov 13,2021 10:10:00 AM | Review | Review
Toll Gate 1 | Jalaj Mathur | Jalaj Mathur | Nov 13,2021 10:00:00 AM | Nov 13,2021 10:10:00 AM | Tool gate review with senior management and approved for next phase | Tool gate review with senior management and approved for next phase
K1 Kaizen (House of Quality) | Jalaj Mathur | Abhishek Gupta | Nov 12,2021 10:30:00 AM | Nov 12,2021 11:15:00 AM | Understanding the House of Quality format. It will further filled by team. | Understanding the House of Quality format. It will further filled by team.
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 13,2021 11:15:00 AM | Nov 13,2021 01:25:00 PM | After TG 1 approval further planning made. | After TG 1 approval further planning made.
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 13,2021 02:00:00 PM | Nov 13,2021 02:30:00 PM | After TG 1 approval further planning made. | After TG 1 approval further planning made.
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 14,2021 09:30:00 PM | Nov 14,2021 11:55:00 PM | Made Gantt chart | Made Gantt chart
- | Jalaj Mathur | Jalaj Mathur | Nov 15,2021 09:00:00 AM | Nov 15,2021 09:20:00 AM | Block diagram : support to select online tool | Block diagram : support to select online tool
K1 Kaizen (House of Quality) | Jalaj Mathur | Sandeep Jain | Nov 12,2021 10:30:00 AM | Nov 12,2021 11:20:00 AM | Meeting attend to understand house of quality process | Meeting attend to understand house of quality process
Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | Jalaj Mathur | Sandeep Jain | Nov 15,2021 11:30:00 AM | Nov 15,2021 01:00:00 PM | Meeting attend for Risk analysis, Long Lead items etc point discussion | Meeting attend for Risk analysis, Long Lead items etc point discussion
Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | Jalaj Mathur | Abhishek Gupta | Nov 15,2021 11:30:00 AM | Nov 15,2021 01:00:00 PM | Discussion on Different aspect of the product like Block diagram,BOM Costing, Long Lead item,etc | Discussion on Different aspect of the product like Block diagram,BOM Costing, Long Lead item,etc
Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | Jalaj Mathur | Jalaj Mathur | Nov 15,2021 11:30:00 AM | Nov 15,2021 01:00:00 PM | Organized and attended the team meeting | Organized and attended the team meeting
Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | Jalaj Mathur | Jalaj Mathur | Nov 15,2021 02:20:00 PM | Nov 15,2021 02:40:00 PM | MOM created and circulated | MOM created and circulated
Team Meeting : 1. Long Lead Item identification. 2. Risk Identification 3. Status Review | Jalaj Mathur | Sobhag Prajapat | Nov 15,2021 11:30:00 AM | Nov 15,2021 01:00:00 PM | Action item found for further work | Action item found for further work
Block Diagram Making & Review | Jalaj Mathur | Sobhag Prajapat | Nov 15,2021 02:00:00 PM | Nov 15,2021 04:00:00 PM | block diagram making and review with team | block diagram making and review with team
Block Diagram Making & Review | Jalaj Mathur | Rohit Kumar Sachan | Nov 15,2021 02:00:00 PM | Nov 15,2021 04:00:00 PM | block diagram making | block diagram making
K1 Kaizen (House of Quality) | Jalaj Mathur | Jalaj Mathur | Nov 16,2021 12:15:00 PM | Nov 16,2021 01:00:00 PM | Discussion and filled technical terms and their weights in format | Discussion and filled technical terms and their weights in format
Team Meeting : 1. Project Status 2. I/P for Sample arrangement 3. Risk Status | Jalaj Mathur | Rohit Kumar Sachan | Nov 15,2021 11:30:00 AM | Nov 15,2021 01:00:00 PM | Attend | Attend
Modules Wise Component Selection 1. Talk to companies 2. Datasheet Analysis 3. DAR to select components | Jalaj Mathur | Rohit Kumar Sachan | Nov 17,2021 09:20:00 AM | Nov 17,2021 11:30:00 AM | Component Selection :- 1. Driver IC 27424 TI 2. TLV222 3. Ucc28951PWR TI 4. IGBT GW30NC60WC ST and Output Filter | Component Selection :- 1. Driver IC 27424 TI 2. TLV222 3. Ucc28951PWR TI 4. IGBT GW30NC60WC ST and Output Filter
Modules Wise Component Selection 1. Talk to companies 2. Datasheet Analysis 3. DAR to select components | Jalaj Mathur | Rohit Kumar Sachan | Nov 16,2021 09:30:00 AM | Nov 16,2021 11:30:00 AM | Component Selection For PFC :- 1. Driver IC 27424 TI 2. UCC28180 ti 3. Mosfet IPW60R099P6 4. Capacitor 470uf 450V 5. diode MUR3060 ST | Component Selection For PFC :- 1. Driver IC 27424 TI 2. UCC28180 ti 3. Mosfet IPW60R099P6 4. Capacitor 470uf 450V 5. diode MUR3060 ST
- | Jalaj Mathur | Rohit Kumar Sachan | Nov 16,2021 11:30:00 AM | Nov 16,2021 01:00:00 PM | House of Quality ( Fill technical Part & relation between Customer Requirement and Technical Spec. ) | House of Quality ( Fill technical Part & relation between Customer Requirement and Technical Spec. )
Circuit Making on Paper and on zero board, testing | Jalaj Mathur | Rohit Kumar Sachan | Nov 20,2021 03:00:00 PM | Nov 20,2021 05:00:00 PM | PFC Circuit make on paper | PFC Circuit make on paper
Circuit Making on Paper and on zero board, testing | Jalaj Mathur | Rohit Kumar Sachan | Nov 24,2021 09:00:00 AM | Nov 24,2021 11:00:00 AM | circuit on paper and please collect share folder (Rohit ) | circuit on paper and please collect share folder (Rohit )
Team Meeting : 1. Project Status 2. I/P for Sample arrangement 3. Risk Status | Jalaj Mathur | Sobhag Prajapat | Nov 29,2021 02:50:00 PM | Nov 29,2021 03:10:00 PM | meeting for pending action items | meeting for pending action items
Team Meeting : 1. Project Status 2. I/P for Sample arrangement 3. Risk Status | Jalaj Mathur | Rohit Kumar Sachan | Nov 29,2021 02:50:00 PM | Nov 29,2021 03:10:00 PM | Attend | Attend
Team Meeting : 1. Project Status 2. I/P for Sample arrangement 3. Risk Status | Jalaj Mathur | Jalaj Mathur | Nov 29,2021 02:50:00 PM | Nov 29,2021 03:25:00 PM | Discussed on Project status Further revised dates And made MOM | Discussed on Project status Further revised dates And made MOM
Firmware making preparations | Jalaj Mathur | Abhishek Gupta | Nov 29,2021 03:30:00 PM | Nov 29,2021 06:15:00 PM | Discussion with jalaj sir and sobhag regarding the working in the task. The study of the refrence MCU PINs connections in the provided pdf | Discussion with jalaj sir and sobhag regarding the working in the task. The study of the refrence MCU PINs connections in the provided pdf
Planning and Monitoring | Jalaj Mathur | Jalaj Mathur | Nov 30,2021 10:30:00 PM | Nov 30,2021 11:30:00 PM | Re-plan the activities from circuit design as reschedule / revised dates received from Tarun ji and Rakesh ji also added risks and their details | Re-plan the activities from circuit design as reschedule / revised dates received from Tarun ji and Rakesh ji also added risks and their details
Firmware making preparations | Jalaj Mathur | Abhishek Gupta | Dec 02,2021 03:00:00 PM | Dec 02,2021 05:50:00 PM | Worked on the Refrence Schematic to find the Requirements for out MCU | Worked on the Refrence Schematic to find the Requirements for out MCU
Firmware making preparations | Jalaj Mathur | Abhishek Gupta | Nov 30,2021 03:30:00 PM | Nov 30,2021 05:45:00 PM | Worked on the reference schematic and understanding the TI reference schematic | Worked on the reference schematic and understanding the TI reference schematic
Firmware making preparations | Jalaj Mathur | Abhishek Gupta | Dec 02,2021 11:30:00 AM | Dec 02,2021 01:15:00 PM | Worked on the Refrence circuit and finding out the Connections and an excel sheet is making | Worked on the Refrence circuit and finding out the Connections and an excel sheet is making
Mechanical, aesthetic concept input collection | Jalaj Mathur | Sandeep Jain | Dec 03,2021 11:00:00 AM | Dec 03,2021 01:00:00 PM | Check Concepts in Internet | Check Concepts in Internet

## Android
Android Application Design
Task | Oct 19, 2021 |  |  | Oct 21, 2021 |  |  | Oct 29, 2021
| Planned Start | Planned End | Approved | Planned Start | Planned End | Approved | Planned Start | Planned End | Approved
Start | Oct 19, 2021 | Oct 19, 2021 | No | Oct 19, 2021 | Oct 19, 2021 | No | Oct 19, 2021 | Oct 19, 2021 | No
1000W 24V MPPT PEDA WIFI Android application Design | Oct 19, 2021 | Oct 25, 2021 | No | Oct 19, 2021 | Oct 25, 2021 | No | Oct 19, 2021 | Oct 25, 2021 | No
10KW MPPT MOSFET WIFI application design | Oct 19, 2021 | Oct 25, 2021 | No | Oct 19, 2021 | Oct 25, 2021 | No | Oct 19, 2021 | Oct 25, 2021 | No
To Optimize size of Images and Pdfs | - | - | - | Oct 19, 2021 | Oct 23, 2021 | No | Oct 19, 2021 | Oct 23, 2021 | No
To open images click on URL | - | - | - | - | - | - | Oct 25, 2021 | Oct 30, 2021 | No
End | Oct 25, 2021 | Oct 30, 2021 | No | Oct 25, 2021 | Oct 30, 2021 | No | Oct 30, 2021 | Nov 10, 2021 | No
Task ID & Description | Planned Start/End | Actual Start/End | Sch. Variance | Planned Efforts | Actual Efforts | Effort Variance | Planned Cost | Actual Cost | Cost Variance
[285] Start | Oct 19, 2021 | - | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Bharti Sharma [100%] | Oct 19, 2021 | -
[327] To Optimize size of Images and Pdfs | Oct 19, 2021 | Oct 21, 2021 | 0% | 32 | 28 | -12% | 320 | 280 | -12%
Bharti Sharma [100%] | Oct 23, 2021 | Oct 23, 2021
[287] 1000W 24V MPPT PEDA WIFI Android application Design | Oct 19, 2021 | Oct 15, 2021 | 200% | 40 | 30 | -25% | 400 | 300 | -25%
Bharti Sharma [100%] | Oct 25, 2021 | Nov 08, 2021
[325] 10KW MPPT MOSFET WIFI application design | Oct 19, 2021 | Oct 19, 2021 | 0% | 8 | 5 | -38% | 80 | 50 | -38%
Bharti Sharma [20%] | Oct 25, 2021 | Oct 25, 2021
[377] To open images click on URL | Oct 25, 2021 | Oct 28, 2021 | 0% | 28 | 11.75 | -58% | 280 | 117.5 | -58%
Bharti Sharma [70%] | Oct 30, 2021 | -
[286] End | Oct 30, 2021 | - | 0% | 28 | 0 | -100% | 280 | 0 | -100%
Bharti Sharma [70%] | Nov 10, 2021 | -
ACTIVITY TYPE | PROJECT NAME | TASK NAME / ACTION ITEM | PROJECT MANAGER | OWNER | FROM | TO | ACTIVITY DESCRIPTION
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Oct 19,2021 09:00:00 AM | Oct 19,2021 01:00:00 PM | dashboard has designed some parameter has added in this application
Project activity | Android Application Design | 10KW MPPT MOSFET WIFI application design | Bharti Sharma | Bharti Sharma | Oct 19,2021 01:30:00 PM | Oct 19,2021 04:30:00 PM | dashboard has designed some parameter has added in this application
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Oct 15,2021 01:30:00 PM | Oct 15,2021 05:30:00 PM | work on WIFI android application
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Oct 20,2021 09:00:00 AM | Oct 20,2021 11:00:00 AM | work on WIFI android application
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Oct 21,2021 11:00:00 AM | Oct 21,2021 01:00:00 PM | sizes of images has reduced up to 5kb to 10kb
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Oct 21,2021 01:30:00 PM | Oct 21,2021 05:30:00 PM | sizes of images has reduced up to 5kb to 10kb
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Oct 21,2021 09:00:00 AM | Oct 21,2021 11:00:00 AM | work on WIFI android application
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Oct 22,2021 09:00:00 AM | Oct 22,2021 01:00:00 PM | 1.Images size has been reduced 3mb to 10kb. pdf size also has reduced in kbs.
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Oct 22,2021 01:30:00 PM | Oct 22,2021 05:30:00 PM | 1.Images size has been reduced 3mb to 10kb. pdf size also has reduced in kbs.
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Oct 23,2021 09:00:00 AM | Oct 23,2021 10:00:00 AM | optimization of size of images and pdf has been completed
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Oct 23,2021 10:00:00 AM | Oct 23,2021 01:00:00 PM | android application MPPT PEDA has been designed only graph portion is incomplete.
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Oct 23,2021 01:30:00 PM | Oct 23,2021 02:30:00 PM | android application MPPT PEDA has been designed only graph portion is incomplete.
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Oct 23,2021 02:40:00 PM | Oct 23,2021 04:40:00 PM | MPPT PEDA has been designed only graph portion is incomplete
Project activity | Android Application Design | 10KW MPPT MOSFET WIFI application design | Bharti Sharma | Bharti Sharma | Oct 25,2021 09:00:00 AM | Oct 25,2021 11:00:00 AM | I have finished this application and validation has not done . graph is pending
Project activity | Android Application Design | To open images click on URL | Bharti Sharma | Bharti Sharma | Oct 28,2021 09:00:00 AM | Oct 28,2021 01:00:00 PM | worked on image size optimization by clicking on url
Project activity | Android Application Design | To open images click on URL | Bharti Sharma | Bharti Sharma | Oct 29,2021 09:00:00 AM | Oct 29,2021 01:00:00 PM | worked on image size optimization by clicking on url
Project activity | Android Application Design | To open images click on URL | Bharti Sharma | Bharti Sharma | Oct 29,2021 01:30:00 PM | Oct 29,2021 03:00:00 PM | read some article how to optimize opening time of android application
Project activity | Android Application Design | To open images click on URL | Bharti Sharma | Bharti Sharma | Oct 29,2021 03:15:00 PM | Oct 29,2021 05:30:00 PM | read some article how to optimize opening time of android application
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Nov 01,2021 09:00:00 AM | Nov 01,2021 01:00:00 PM | worked on optimization of images in android application
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Oct 30,2021 09:00:00 AM | Oct 30,2021 01:00:00 PM | worked on optimization of images in android application
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Oct 30,2021 04:30:00 PM | Oct 30,2021 05:30:00 PM | worked on android application
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Nov 01,2021 01:30:00 PM | Nov 01,2021 05:30:00 PM | worked on Peda and Mppt related android application
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Nov 02,2021 09:00:00 AM | Nov 02,2021 11:30:00 AM | work on this android application 24V MPPT PEDA related faults and graph
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Nov 02,2021 01:30:00 PM | Nov 02,2021 04:00:00 PM | work on this android application 24V MPPT PEDA related faults and graph
Project activity | Android Application Design | 1000W 24V MPPT PEDA WIFI Android application Design | Bharti Sharma | Bharti Sharma | Nov 08,2021 10:00:00 AM | Nov 08,2021 01:00:00 PM | Some correction has made in WIFI application Design(plotting graph)
Project activity | Android Application Design | - | Bharti Sharma | Bharti Sharma | Nov 08,2021 05:00:00 PM | Nov 08,2021 05:30:00 PM | worked on Android studio software there is facing new challenges and error and program is not executing.
Project activity | Android Application Design | To Optimize size of Images and Pdfs | Bharti Sharma | Bharti Sharma | Nov 20,2021 01:30:00 PM | Nov 20,2021 05:30:00 PM | I have worked on optimize size of images and pdfs.

## Tuning Tool Design
Different Types Of Tuning Tool Design
Task | Oct 19, 2021 |  |  | Nov 24, 2021 |  |  | Nov 25, 2021
| Planned Start | Planned End | Approved | Planned Start | Planned End | Approved | Planned Start | Planned End | Approved
Start | Oct 14, 2021 | Oct 14, 2021 | No | Oct 14, 2021 | Oct 14, 2021 | No | Oct 14, 2021 | Oct 14, 2021 | No
10KW MPPT MOSFET LCD Module | Oct 14, 2021 | Oct 18, 2021 | No | Oct 14, 2021 | Oct 18, 2021 | No | Oct 14, 2021 | Oct 18, 2021 | No
PEDA-8025 tuning tool design | Oct 14, 2021 | Oct 18, 2021 | No | Oct 14, 2021 | Oct 18, 2021 | No | Oct 18, 2021 | Oct 21, 2021 | No
PEDA 8006 MPPT Tuning Tool Design | - | - | - | - | - | - | Nov 20, 2021 | Nov 25, 2021 | No
End | Oct 18, 2021 | Oct 18, 2021 | No | Oct 18, 2021 | Oct 18, 2021 | No | Nov 25, 2021 | Nov 25, 2021 | No
Task ID & Description | Planned Start/End | Actual Start/End | Sch. Variance | Planned Efforts | Actual Efforts | Effort Variance | Planned Cost | Actual Cost | Cost Variance
[276] Start | Oct 14, 2021 | - | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Bharti Sharma [1%] | Oct 14, 2021 | -
[278] 10KW MPPT MOSFET LCD Module | Oct 14, 2021 | Oct 14, 2021 | 100% | 12 | 7.17 | -40% | 120 | 71.7 | -40%
Bharti Sharma [50%] | Oct 18, 2021 | Oct 23, 2021
[326] PEDA-8025 tuning tool design | Oct 18, 2021 | Oct 15, 2021 | 50% | 7.2 | 9.83 | 37% | 72 | 98.3 | 37%
Bharti Sharma [30%] | Oct 21, 2021 | Oct 23, 2021
[434] PEDA 8006 MPPT Tuning Tool Design | Nov 20, 2021 | Nov 23, 2021 | 0% | 32 | 9 | -72% | 320 | 90 | -72%
Bharti Sharma [100%] | Nov 25, 2021 | -
[277] End | Nov 25, 2021 | - | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Bharti Sharma [1%] | Nov 25, 2021 | -
ACTIVITY TYPE | PROJECT NAME | TASK NAME / ACTION ITEM | PROJECT MANAGER | OWNER | FROM | TO | ACTIVITY DESCRIPTION
Project activity | Different Types Of Tuning Tool Design | 10KW MPPT MOSFET LCD Module | Bharti Sharma | Bharti Sharma | Oct 14,2021 11:00:00 AM | Oct 14,2021 01:00:00 PM | work on tuning tool design for mppt mosfet
Project activity | Different Types Of Tuning Tool Design | PEDA-8025 tuning tool design | Bharti Sharma | Bharti Sharma | Oct 15,2021 09:00:00 AM | Oct 15,2021 01:00:00 PM | work on tuning tool design for PEDA 8025
Project activity | Different Types Of Tuning Tool Design | PEDA-8025 tuning tool design | Bharti Sharma | Bharti Sharma | Oct 16,2021 09:00:00 AM | Oct 16,2021 01:00:00 PM | work on tuning tool design for PEDA 8025
Project activity | Different Types Of Tuning Tool Design | 10KW MPPT MOSFET LCD Module | Bharti Sharma | Bharti Sharma | Oct 16,2021 01:30:00 PM | Oct 16,2021 05:30:00 PM | work on tuning tool design for MPPT MOSFET
Project activity | Different Types Of Tuning Tool Design | PEDA-8025 tuning tool design | Bharti Sharma | Bharti Sharma | Oct 20,2021 11:00:00 AM | Oct 20,2021 12:00:00 PM | work on tuning tool for peda for 8025 inverter
Project activity | Different Types Of Tuning Tool Design | 10KW MPPT MOSFET LCD Module | Bharti Sharma | Bharti Sharma | Oct 20,2021 04:30:00 PM | Oct 20,2021 05:30:00 PM | 10kW MPPT MOSFET 8025 LCD ,tuning addresses increase by 1 and tuning button address also increase by 1.
Project activity | Different Types Of Tuning Tool Design | 10KW MPPT MOSFET LCD Module | Bharti Sharma | Bharti Sharma | Oct 23,2021 02:30:00 PM | Oct 23,2021 02:40:00 PM | worked on mppt lcd tuning tool.in this before pressing the tuning button serial number was not clearing so resolve that issue
Project activity | Different Types Of Tuning Tool Design | PEDA-8025 tuning tool design | Bharti Sharma | Bharti Sharma | Oct 23,2021 04:40:00 PM | Oct 23,2021 05:30:00 PM | complete this tuning tool
Project activity | Different Types Of Tuning Tool Design | - | Bharti Sharma | Bharti Sharma | Nov 08,2021 03:00:00 PM | Nov 08,2021 05:00:00 PM | I have worked on some tuning tool (birthday)
Project activity | Different Types Of Tuning Tool Design | PEDA 8006 MPPT Tuning Tool Design | Bharti Sharma | Bharti Sharma | Nov 23,2021 09:00:00 AM | Nov 23,2021 01:00:00 PM | new tuning tool design for MPPT Model name is PEDA 8006 . In this tool some new parameters added and addresses also changed.
Project activity | Different Types Of Tuning Tool Design | PEDA 8006 MPPT Tuning Tool Design | Bharti Sharma | Bharti Sharma | Nov 23,2021 01:30:00 PM | Nov 23,2021 05:30:00 PM | new tuning tool design for MPPT Model name is PEDA 8006 . In this tool some new parameters added and addresses also changed.
Project activity | Different Types Of Tuning Tool Design | PEDA 8006 MPPT Tuning Tool Design | Bharti Sharma | Bharti Sharma | Nov 29,2021 09:00:00 AM | Nov 29,2021 10:00:00 AM | I have added some faults and some flags in layout of PEDA 8006 MPPT tuning tool.

## Tuning Tool in Excel
Tuning tool Data save in Excel format
Task | Nov 17, 2021 |  |  | Nov 25, 2021
| Planned Start | Planned End | Approved | Planned Start | Planned End | Approved
Start | Nov 15, 2021 | Nov 13, 2021 | No | Nov 15, 2021 | Nov 20, 2021 | No
tuning tool data save in excel format | - | - | - | Nov 23, 2021 | Nov 29, 2021 | No
End | Nov 19, 2021 | Nov 25, 2021 | No | Nov 29, 2021 | Dec 04, 2021 | No
Task ID & Description | Planned Start/End | Actual Start/End | Sch. Variance | Planned Efforts | Actual Efforts | Effort Variance | Planned Cost | Actual Cost | Cost Variance
[421] Start | Nov 15, 2021 | - | 0% | 40 | 0 | -100% | 4400 | 0 | -100%
Bharti Sharma [100%]Tarun Gupta [0%] | Nov 20, 2021 | -
[435] tuning tool data save in excel format | Nov 23, 2021 | Nov 24, 2021 | 0% | 40 | 21.75 | -46% | 400 | 217.5 | -46%
Bharti Sharma [100%] | Nov 29, 2021 | -
[422] End | Nov 29, 2021 | - | 0% | 40 | 0 | -100% | 400 | 0 | -100%
Bharti Sharma [100%] | Dec 04, 2021 | -
TASK NAME / ACTION ITEM | PROJECT MANAGER | OWNER | FROM | TO | ACTIVITY DESCRIPTION
| Bharti Sharma | Bharti Sharma | Nov 17,2021 09:00:00 AM | Nov 17,2021 01:00:00 PM | I have done work on saving data related to tuning tool in excel file.
| Bharti Sharma | Bharti Sharma | Nov 17,2021 01:30:00 PM | Nov 17,2021 05:30:00 PM | Different techniques are used to save tuning tool data in excel file .
| Bharti Sharma | Bharti Sharma | Nov 18,2021 09:00:00 AM | Nov 18,2021 01:00:00 PM | I have done work on different techniques like DAO,ADO Method to save the data in excel format.
| Bharti Sharma | Bharti Sharma | Nov 18,2021 01:30:00 PM | Nov 18,2021 05:30:00 PM | when I save data in excel file then replace old file with new file.
| Bharti Sharma | Bharti Sharma | Nov 19,2021 09:00:00 AM | Nov 19,2021 01:00:00 PM | when I save data in excel file then replace old file with new file. Every time it generate with new name .
| Bharti Sharma | Bharti Sharma | Nov 19,2021 01:30:00 PM | Nov 19,2021 05:30:00 PM | I have worked on previous defined issues regarding to save data in excel format.
| Bharti Sharma | Bharti Sharma | Nov 20,2021 09:00:00 AM | Nov 20,2021 01:00:00 PM | I have worked on previous defined issues regarding to save data in excel format.
| Bharti Sharma | Bharti Sharma | Nov 22,2021 01:00:00 PM | Nov 22,2021 05:30:00 PM | Data save in excel file but data is not updating so there are some issues occur.
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 24,2021 11:00:00 AM | Nov 24,2021 01:00:00 PM | All tuning parameter data save in Excel format
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 24,2021 01:30:00 PM | Nov 24,2021 04:15:00 PM | All tuning parameter data save in Excel format
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 24,2021 09:00:00 AM | Nov 24,2021 11:00:00 AM | All tuning parameter data save in Excel format
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 25,2021 09:00:00 AM | Nov 25,2021 01:00:00 PM | All tuning parameter data save in Excel format
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 25,2021 01:30:00 PM | Nov 25,2021 03:00:00 PM | All tuning parameter data save in Excel format
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 25,2021 04:00:00 PM | Nov 25,2021 05:30:00 PM | All tuning parameter data save in Excel format
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 26,2021 09:00:00 AM | Nov 26,2021 12:00:00 PM | I have worked the issues regarding save the data in excel file.
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 26,2021 12:00:00 PM | Nov 26,2021 01:00:00 PM | I have worked the issues regarding save the data in excel file.
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 26,2021 04:00:00 PM | Nov 26,2021 05:30:00 PM | I have resolved the issues regarding save the data in excel file. I have designed a separate button as name as save data. It is used to store the data in excel file.
tuning tool data save in excel format | Bharti Sharma | Bharti Sharma | Nov 26,2021 01:30:00 PM | Nov 26,2021 04:00:00 PM | I have worked on the issues regarding save the data in excel file. I have designed a separate button as name as save data. It is used to store the data in excel file.

## 10KW
10KW/120V MPPT PCU Kaizen
Task ID & Description | Planned Start/End | Actual Start/End | Sch. Variance | Planned Efforts | Actual Efforts | Effort Variance | Planned Cost | Actual Cost | Cost Variance
[32] Start | Aug 02, 2021 | - | 0% | 0.32 | 0 | -100% | 19.2 | 0 | -100%
Latest Comments: | Aug 03, 2021 | -
Project start from integration phase.
Tarun Gupta [2%]Umesh Likhitkar [2%]
[33] Toll Gate 0 | Aug 03, 2021 | Aug 10, 2021 | 300% | 8 | 0.5 | -94% | 480 | 0.5 | -100%
Tarun Gupta [50%]Umesh Likhitkar [50%] | Aug 04, 2021 | Aug 10, 2021
[34] Toll Gate 1 | Aug 04, 2021 | Aug 10, 2021 | 250% | 3.2 | 1 | -69% | 192 | 1 | -99%
Latest Comments: | Aug 05, 2021 | Aug 10, 2021
OK, Project start from Integration phase
Tarun Gupta [20%]Umesh Likhitkar [20%]
[64] Integration design | Aug 05, 2021 | Aug 02, 2021 | -150% | 4 | 3 | -25% | 40 | 3 | -92%
Latest Comments: | Aug 06, 2021 | Aug 02, 2021
ok
Umesh Likhitkar [50%]
[65] Integration | Aug 06, 2021 | Aug 02, 2021 | -125% | 16 | 10.5 | -34% | 208 | 10.5 | -95%
Latest Comments: | Aug 09, 2021 | Aug 03, 2021
ok
Pawan Kumar Sharma [20%]Ramashish Kumar [20%]Umesh Likhitkar [60%]
[69] Software Integration with main product | Aug 09, 2021 | Aug 06, 2021 | 0% | 12 | 13.17 | 10% | 920 | 13.17 | -99%
Latest Comments: | Aug 14, 2021 | -
Ok . Task 90% done
Tarun Gupta [20%]Umesh Likhitkar [10%]
[86] New LCD PCB Testing on Zero Board | Aug 09, 2021 | Aug 09, 2021 | 0% | 61.6 | 38.83 | -37% | 6759.2 | 38.83 | -99%
Latest Comments: | Aug 17, 2021 | -
90% Work Done. LCD Change By Sr. Management
Bharat Kakra [10%]Bharti Sharma [10%]Rajashekhar K [60%]Tarun Gupta [20%]Umesh Likhitkar [10%]
[66] Integration testing | Aug 12, 2021 | Aug 09, 2021 | 200% | 28 | 92.88 | 232% | 392 | 128.73 | -67%
CRO 4 CHANNELS TEKTRONIX TPS2024 [5%]Pawan Kumar Sharma [5%]POWER SUPPLY CHROMA 62100H-450 [10%]POWER SUPPLY CHROMA 62150H-100S [5%]Ramashish Kumar [5%]Umesh Likhitkar [20%] | Aug 20, 2021 | Sep 07, 2021
[202] TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Aug 17, 2021 | Aug 24, 2021 | 0% | 17.28 | 20.08 | 16% | 469.44 | 48.7 | -90%
Sandeep Jain [2%]Tarun Gupta [10%]Umesh Likhitkar [60%] | Aug 20, 2021 | -
[182] Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Aug 17, 2021 | Aug 23, 2021 | 488.9% | 56 | 174.67 | 212% | 5986.4 | 323.175 | -95%
Pawan Kumar Sharma [10%]Rajashekhar K [70%]Tarun Gupta [10%]Umesh Likhitkar [10%] | Aug 25, 2021 | Oct 08, 2021
[44] Plan Development incl. Long Lead identification | Aug 20, 2021 | Sep 07, 2021 | 0% | 2.4 | 2 | -17% | 198.4 | 14 | -93%
Sandeep Jain [10%]Tarun Gupta [10%]Umesh Likhitkar [10%] | Aug 21, 2021 | -
[53] All PCB review and revision | Aug 25, 2021 | Sep 07, 2021 | 2700% | 8 | 14.83 | 85% | 253.6 | 58.16 | -77%
Pawan Kumar Sharma [20%]Rajashekhar K [10%]Rakesh Pandey [20%]Sandeep Jain [10%]Umesh Likhitkar [40%] | Aug 26, 2021 | Oct 19, 2021
[188] Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Aug 25, 2021 | Aug 25, 2021 | 1475% | 19.2 | 52.59 | 174% | 2198.4 | 113.745 | -95%
Abhishek Gupta [30%]Bharti Sharma [30%]Rajashekhar K [5%]Tarun Gupta [5%]Umesh Likhitkar [10%] | Aug 28, 2021 | Oct 26, 2021
[63] Mechanical Chassis Review | Aug 27, 2021 | - | 0% | 5.6 | 0 | -100% | 135.2 | 0 | -100%
Bharat Kakra [30%]Chandrashekhar Sharma [10%]Umesh Likhitkar [30%] | Aug 28, 2021 | -
[67] Final Design Review After Testing | Aug 28, 2021 | Sep 06, 2021 | 233.3% | 7.28 | 1.08 | -85% | 847.84 | 4.45 | -99%
Latest Comments: | Aug 30, 2021 | Sep 06, 2021
Task Done with team
Bharat Kakra [20%]Chandrashekhar Sharma [10%]Jalaj Mathur [5%]Ramashish Kumar [16%]Sandeep Jain [10%]Tarun Gupta [10%]Umesh Likhitkar [20%]
[87] Final PCB Design of LCD and other PCB Modification | Aug 30, 2021 | Aug 21, 2021 | 50% | 42.8 | 73.5 | 72% | 5094.4 | 272.54 | -95%
Latest Comments: | Sep 04, 2021 | Sep 07, 2021
Work Finished by all team
Pawan Kumar Sharma [10%]Rajashekhar K [20%]Rakesh Pandey [50%]Sandeep Jain [2%]Tarun Gupta [5%]Umesh Likhitkar [20%]
[85] Final Testing With Product and Validation | Sep 27, 2021 | Sep 02, 2021 | 22.22% | 184.8 | 353.67 | 91% | 10438.4 | 2262.6 | -78%
Latest Comments: | Oct 14, 2021 | Oct 18, 2021
Running Testing with New Chassis
Abhishek Gupta [10%]CRO 4 CHANNELS TEKTRONIX TPS2024 [10%]POWER SUPPLY CHROMA 62100H-450 [10%]Rajashekhar K [10%]Ramashish Kumar [10%]SOLAR PANELS SETUP [10%]Tarun Gupta [5%]Umesh Likhitkar [20%]Vikash Sharma [80%]
[56] Mechanical Drawings | Oct 08, 2021 | Aug 30, 2021 | 0% | 26.4 | 34.17 | 29% | 2956.8 | 137.43 | -95%
Latest Comments: | Oct 12, 2021 | Oct 12, 2021
Chassis Drawing Done. some harness, bus-bar and Solar heat sink Drawing are Pending
Bharat Kakra [60%]Sandeep Jain [20%]Tarun Gupta [10%]Umesh Likhitkar [20%]
[49] BOM creation, optimization and SAP Update in draft version | Oct 08, 2021 | Sep 06, 2021 | 0% | 28.8 | 12.25 | -57% | 668.8 | 36.65 | -95%
Jalaj Mathur [10%]Shweta Aggarwal [30%]Umesh Likhitkar [30%]Vikash Sharma [20%] | Oct 13, 2021 | -
[72] Support documentation, tools. jigs, fixtures | Oct 13, 2021 | - | 0% | 12.8 | 0 | -100% | 144 | 0 | -100%
Ramashish Kumar [20%]Umesh Likhitkar [60%] | Oct 15, 2021 | -
[73] BOM update in SAP After Review | Oct 14, 2021 | Oct 22, 2021 | 0% | 8 | 0.08 | -99% | 187.2 | 1.2 | -99%
Latest Comments: | Oct 15, 2021 | -
Pending BOM Graphical LCD Assy, GBT Driver card Assy and Chassis Assy
Jalaj Mathur [20%]Shweta Aggarwal [60%]Umesh Likhitkar [20%]
[35] Toll Gate 2 | Oct 15, 2021 | - | 0% | 0.16 | 0 | -100% | 9.6 | 0 | -100%
Tarun Gupta [1%]Umesh Likhitkar [1%] | Oct 16, 2021 | -
[36] End | Oct 15, 2021 | - | 0% | 8 | 0 | -100% | 480 | 0 | -100%
Tarun Gupta [50%]Umesh Likhitkar [50%] | Oct 16, 2021 | -
ACTIVITY TYPE | PROJECT NAME | TASK NAME / ACTION ITEM | PROJECT MANAGER | OWNER | FROM | TO | ACTIVITY DESCRIPTION
Project activity | 10KW/120V MPPT PCU Kaizen | Integration design | Umesh Likhitkar | Umesh Likhitkar | Aug 02,2021 10:00:00 AM | Aug 02,2021 01:00:00 PM | Integration Design 10 KW MPPT PCU in New Chassis
Project activity | 10KW/120V MPPT PCU Kaizen | Integration | Umesh Likhitkar | Umesh Likhitkar | Aug 02,2021 02:30:00 PM | Aug 02,2021 05:30:00 PM | Integration Design 10 KW MPPT PCU in New Chassis
Project activity | 10KW/120V MPPT PCU Kaizen | Integration | Umesh Likhitkar | Umesh Likhitkar | Aug 03,2021 10:00:00 AM | Aug 03,2021 05:30:00 PM | Integration Design 10 KW MPPT PCU in New Chassis
Project activity | 10KW/120V MPPT PCU Kaizen | - | Umesh Likhitkar | Umesh Likhitkar | Aug 05,2021 10:00:00 AM | Aug 05,2021 12:30:00 PM | Planing 10KW MPPT Kaizen PCU
Project activity | 10KW/120V MPPT PCU Kaizen | - | Umesh Likhitkar | Umesh Likhitkar | Aug 05,2021 02:00:00 AM | Aug 05,2021 04:30:00 AM | Planing 10KW MPPT Kaizen PCU
Project activity | 10KW/120V MPPT PCU Kaizen | Software Integration with main product | Umesh Likhitkar | Umesh Likhitkar | Aug 06,2021 10:00:00 AM | Aug 06,2021 01:30:00 PM | Software Test with System Rev4 , Rev5
Project activity | 10KW/120V MPPT PCU Kaizen | Software Integration with main product | Umesh Likhitkar | Umesh Likhitkar | Aug 06,2021 02:00:00 PM | Aug 06,2021 06:30:00 PM | Software Test with System Rev6 , Rev7
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 09,2021 11:30:00 AM | Aug 09,2021 06:30:00 PM | Design the Zero PCB for LCD and Firmware for Operating the LCD(16*2))
Project activity | 10KW/120V MPPT PCU Kaizen | Toll Gate 0 | Umesh Likhitkar | Umesh Likhitkar | Aug 10,2021 10:00:00 AM | Aug 10,2021 10:30:00 AM | Review with Tarun Sir
Project activity | 10KW/120V MPPT PCU Kaizen | Toll Gate 1 | Umesh Likhitkar | Umesh Likhitkar | Aug 10,2021 10:30:00 AM | Aug 10,2021 11:30:00 AM | Review with Tarun Sir
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 10,2021 09:00:00 AM | Aug 10,2021 03:00:00 PM | Firmware management of LCD
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 11,2021 09:00:00 AM | Aug 11,2021 01:00:00 PM | Firmware management of LCD
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 11,2021 01:30:00 PM | Aug 11,2021 04:00:00 PM | Firmware management of LCD
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Umesh Likhitkar | Aug 11,2021 11:30:00 AM | Aug 11,2021 12:15:00 PM | New LCD home made PCB testing with Product 10KW kaizen
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 09,2021 02:00:00 AM | Aug 09,2021 06:00:00 AM | Set Vce Saturation of Solar IGBT
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 11,2021 10:00:00 AM | Aug 11,2021 10:30:00 AM | Check control card PCB 1088 and PCB 913 Circuit for Vce saturation of IGBT and System short circuit with Pandey ji
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 11,2021 10:40:00 AM | Aug 11,2021 11:30:00 AM | Check Vce Saturation Signal in open circuit for Testing of IGBT short Circuit
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 11,2021 02:15:00 PM | Aug 11,2021 03:40:00 PM | Check System short circuit signal and Ac current sensing Circuit.
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 11,2021 05:40:00 AM | Aug 11,2021 06:00:00 AM | Project status Discuss with tarun sir
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Ramashish Kumar | Aug 12,2021 02:30:00 PM | Aug 12,2021 04:00:00 PM | Jark load Testing support for short circuit testing up to 15KW with umesh
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 12,2021 09:15:00 AM | Aug 12,2021 11:00:00 AM | Firmware management of LCD ,Setting the Pattern of LCD display
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 12,2021 02:15:00 PM | Aug 12,2021 05:00:00 PM | Firmware management of LCD ,Adding Tuning tool to LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 12,2021 09:40:00 AM | Aug 12,2021 10:30:00 AM | Discuss some issue regarding Einframe software and Jalaj sir Resolve all issue
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 12,2021 11:00:00 AM | Aug 12,2021 11:40:00 AM | Change new LCD for Providing some data to Rajashekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 12,2021 11:40:00 AM | Aug 12,2021 12:10:00 PM | Testing of Boost voltage with solar
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 12,2021 12:25:00 PM | Aug 12,2021 01:10:00 PM | Connect loop with Q19 Mosfet in Power PCB and Re- Connect power PCB for jark load Testing
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 12,2021 02:10:00 PM | Aug 12,2021 03:30:00 PM | Connect parallel battery Setup and Extra load connection Setup for Short ckt and Jark load Testijng
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 12,2021 03:40:00 PM | Aug 12,2021 06:15:00 PM | Testing of Jark load and short circuit Upo to 60Aac current
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 12,2021 06:15:00 PM | Aug 12,2021 06:30:00 PM | Teem meting with Tarun sir and CS sir Regarding 10KW MPPT Status
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 13,2021 09:00:00 AM | Aug 13,2021 01:00:00 PM | Design of Tuninig Tool for LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 13,2021 10:00:00 AM | Aug 13,2021 12:30:00 PM | Solar IGBT VCE Saturation Circuit run with adding Transistor Circuit. output of sola Vce Saturation circuit is connected on pin no. 5 of controller for testing IGBT short Circuit. System take CKT
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 13,2021 12:30:00 PM | Aug 13,2021 01:10:00 PM | Team meeting with Tarun sir on Solar Short circuit and AC Current sense pin Configuration
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 13,2021 04:20:00 PM | Aug 13,2021 06:10:00 PM | Design AC Current sensing circuit, Solar voltage sensing Circuit, and Solar Vce saturation ckt on Zero board for Final testing With software and proper wiring connection
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Bharti Sharma | Aug 13,2021 10:00:00 AM | Aug 13,2021 12:00:00 PM | tuning tool designed for LCD PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 14,2021 10:30:00 AM | Aug 14,2021 12:00:00 PM | Design AC Current sensing circuit, Solar voltage sensing Circuit, and Solar Vce saturation ckt on Zero board for Final testing With software and proper wiring connection
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 14,2021 12:10:00 PM | Aug 14,2021 01:00:00 PM | New Design AC Current sensing circuit, Solar voltage sensing Circuit PCB Integrated with Product
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 14,2021 03:10:00 PM | Aug 14,2021 04:15:00 PM | New Design AC Current sensing circuit, Solar voltage sensing Circuit PCB Tested with Product Solar sensing OK, Solar short circuit OK, AC current sensing OK,
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 14,2021 04:20:00 PM | Aug 14,2021 05:30:00 PM | New LCD PCB Testing With Product in Backup mode , non Backup mode and Solar Mode, Report share to rajashekhar
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Bharti Sharma | Aug 16,2021 04:00:00 AM | Aug 16,2021 04:20:00 AM | Some Changes has done in LCD tuning tool
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Bharti Sharma | Aug 16,2021 02:00:00 AM | Aug 16,2021 03:00:00 AM | New tuning tool has designed for 10KW MPPT MOSFET
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 16,2021 09:00:00 AM | Aug 16,2021 11:00:00 AM | Firmware management of LCD, fixing the BUGS
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 16,2021 02:00:00 PM | Aug 16,2021 04:00:00 PM | Firmware management of LCD, fixing the BUGS
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 14,2021 04:00:00 PM | Aug 14,2021 05:30:00 PM | Firmware management of LCD
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Umesh Likhitkar | Aug 16,2021 10:30:00 AM | Aug 16,2021 10:45:00 AM | Check LCD PCB Data
Project activity | 10KW/120V MPPT PCU Kaizen | Software Integration with main product | Umesh Likhitkar | Umesh Likhitkar | Aug 16,2021 11:00:00 AM | Aug 16,2021 01:10:00 PM | Check Software Rev 4, 5, 6 With new LCD for Ac current sensing
Project activity | 10KW/120V MPPT PCU Kaizen | Software Integration with main product | Umesh Likhitkar | Umesh Likhitkar | Aug 16,2021 02:10:00 PM | Aug 16,2021 05:10:00 PM | Check Software Rev 7, 8, With new LCD for Ac current sensing. Check New Tuning tool and LCD Software also
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 09:40:00 AM | Aug 17,2021 10:10:00 AM | Discuss with tarun Sir, Regarding Ac Current circuit and share report Software rev. 7 and 8
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 10:20:00 AM | Aug 17,2021 12:10:00 PM | Testing of Software Rev.10, 11, with System, Check Signal and Control card PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 12:30:00 PM | Aug 17,2021 01:05:00 PM | Check New Tuning Tool and LCD parameter with Solar charging
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 02:30:00 PM | Aug 17,2021 03:45:00 PM | arrange set up from Mains charging, Change mains MCB, SCR card in System, Test software Rev 13
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 03:45:00 PM | Aug 17,2021 04:20:00 PM | Share Report of rev 13 with Tarun Sir, add some address for tuning tool
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 04:20:00 PM | Aug 17,2021 04:40:00 PM | Check Software Rev 14, Over load trip Ok in backup mode
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 04:45:00 PM | Aug 17,2021 05:00:00 PM | Team meeting with tarun sir and sharma ji for 10KW MPPT and Load jig Setup
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 17,2021 05:20:00 PM | Aug 17,2021 06:00:00 PM | Share finding of tuning tool to bharti madam, and check LED. Check Power PCB for TDR Option
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 18,2021 09:30:00 AM | Aug 18,2021 10:10:00 AM | working on EinFrame , Project status, Time sheet , pending tasks
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 18,2021 10:20:00 AM | Aug 18,2021 11:00:00 AM | Check tuning tool Rev 2 and LCD/ LED parameter
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 18,2021 11:10:00 AM | Aug 18,2021 12:00:00 PM | Check system on inductive load with multiple PF for Ac Current Protection Circuit
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 18,2021 12:40:00 PM | Aug 18,2021 01:20:00 PM | Check option of TD in Power PCB 964 and control card 1088, Discuss with sharma ji and tarun sir
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 18,2021 02:20:00 PM | Aug 18,2021 03:00:00 PM | Check New Tuning Tool Regarding mains Voltage and ES mode, find system working in ES mode 3
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 18,2021 05:10:00 PM | Aug 18,2021 05:35:00 PM | Review of 10KW MPPT PCU Kaizen mechanical Assy.
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 19,2021 11:00:00 AM | Aug 19,2021 11:30:00 AM | Team meeting with Tarun sir Regarding Front switch change, TDR Circuit and other point
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 19,2021 11:30:00 AM | Aug 19,2021 12:45:00 PM | Make Testing Report of Testing
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 19,2021 10:30:00 AM | Aug 19,2021 10:45:00 AM | Review of 10KW MPPT PCU Kaizen mechanical Assy. With Sharma Sir
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 19,2021 09:30:00 AM | Aug 19,2021 10:10:00 AM | working on EinFrame , Project status, Time sheet , pending tasks
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 20,2021 02:10:00 PM | Aug 20,2021 03:30:00 PM | Make hardware connection and check signal for Testing Rev 14.S1 (Change switch confutation as per 4200 Surja pro ) Software Testing
Project activity | 10KW/120V MPPT PCU Kaizen | New LCD PCB Testing on Zero Board | Umesh Likhitkar | Rajashekhar K | Aug 18,2021 04:00:00 PM | Aug 18,2021 05:00:00 PM | Implementation of switches in LCD PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Aug 21,2021 09:00:00 AM | Aug 21,2021 01:00:00 PM | Design of LCD PCB schematic and Placement of LCD,LED and switches on the Zero PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Aug 21,2021 02:00:00 PM | Aug 21,2021 06:00:00 PM | Design of LCD PCB schematic and Placement of LCD,LED and switches on the Zero PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 20,2021 04:00:00 PM | Aug 20,2021 04:30:00 PM | Check software Rev S1 with System. Resolve hardware related problem. UPS and ES switch Working Ok. Found Problem in Backup switch.
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 20,2021 04:30:00 PM | Aug 20,2021 04:55:00 PM | Discuss with Tarun sir about switch status
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 20,2021 05:10:00 PM | Aug 20,2021 05:25:00 PM | Testing of Rev S2 now backup Switch working OK
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 09:40:00 AM | Aug 21,2021 10:20:00 AM | working on EinFrame , Project status, Time sheet , pending tasks
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 10:20:00 AM | Aug 21,2021 10:40:00 AM | Discuss with Tarun sir regarding TDR circuit Pin , Select GPIO B11,
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 11:20:00 AM | Aug 21,2021 12:40:00 PM | Add TDR circuit in Power PCB and change pin connection in control card, and check system Function.
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 02:20:00 PM | Aug 21,2021 02:40:00 PM | Testing of Software S3 for TDR Testing
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 03:00:00 PM | Aug 21,2021 03:40:00 PM | Testing of Software S4 for TDR Testing.Resolve Problem during Mains ON condition
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 03:40:00 PM | Aug 21,2021 04:05:00 PM | Discuss with tarun sir Regarding Software S4 result, Share problem during Mains reconnected in 1 mint time. this time TDR Circuit Not Working
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 04:20:00 PM | Aug 21,2021 05:25:00 PM | Testing of Software S5 for TDR Testing. Testing of Resolve Problem during Mains Reconnected. Testing in Mains high and Low cutt in UPS mode
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 21,2021 05:30:00 PM | Aug 21,2021 05:50:00 PM | Discuss with tarun sir Regarding Result with software Rev 5, Tarun sir Give software Rev 6 for Final TDR
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 23,2021 09:40:00 AM | Aug 23,2021 10:30:00 AM | working on EinFrame , Project status, Time sheet , pending tasks
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 23,2021 10:30:00 AM | Aug 23,2021 12:05:00 PM | Make planning of pending work and Discuss with Tarun sir .
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 23,2021 12:10:00 PM | Aug 23,2021 01:10:00 PM | Check Mains Charging Efficiency at 15A, Check tuning tool Rev 4,
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 23,2021 02:10:00 PM | Aug 23,2021 03:00:00 PM | Check System efficiency at Backup mode with (100%,75%))
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 23,2021 03:10:00 PM | Aug 23,2021 04:35:00 PM | Working on Li-ion Comb-ability circuit With AC transformer , Discuss with Sharma ji. Circuit not working with 964 PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 23,2021 04:45:00 PM | Aug 23,2021 05:35:00 PM | Add Rocker switch Series with Battery Resistance and check System with Rocker switch 10 time ON/OFF
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 23,2021 05:35:00 PM | Aug 23,2021 06:25:00 PM | Discuss with Tarun sir, pandey ji, sobhag Ji Regarding 10kw efficiency, Rocker switch
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 24,2021 12:10:00 PM | Aug 24,2021 01:10:00 PM | Check TDR Working With Software Rev 6, and Testing
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 24,2021 09:30:00 AM | Aug 24,2021 11:00:00 AM | working on EinFrame , Project status, Time sheet , pending tasks,
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Aug 25,2021 09:30:00 AM | Aug 25,2021 09:35:00 AM | Address not not provided so it can't start now
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 23,2021 09:00:00 AM | Aug 23,2021 01:00:00 PM | Design PCB for Graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 23,2021 02:00:00 PM | Aug 23,2021 06:00:00 PM | Design PCB for Graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 24,2021 02:00:00 PM | Aug 24,2021 06:00:00 PM | Firmware management of graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 24,2021 09:00:00 AM | Aug 24,2021 01:00:00 PM | Design LCD PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 25,2021 09:00:00 AM | Aug 25,2021 01:00:00 PM | Change in the LCD Communication and Developing the tuning tool
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Pawan Kumar Sharma | Aug 23,2021 09:30:00 AM | Aug 23,2021 01:00:00 PM | Mounting of Graphical LCD on Zero PCB and made connection Accordingly
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Pawan Kumar Sharma | Aug 23,2021 02:00:00 PM | Aug 23,2021 05:30:00 PM | Mounting of Graphical LCD on Zero PCB and made connection Accordingly
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Pawan Kumar Sharma | Aug 24,2021 02:00:00 PM | Aug 24,2021 05:30:00 PM | mounting of Connectors and Switches LED's On zero PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Pawan Kumar Sharma | Aug 24,2021 09:30:00 AM | Aug 24,2021 01:00:00 PM | mounting of Connectors and Switches LED's On zero PCB
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 24,2021 02:00:00 PM | Aug 24,2021 03:45:00 PM | Repair AC /DC PCB Card for Li ion Comp-ability. R7 Remove , R11 =56K, Change IC Top, Change Diode and check output 11.7V at no load
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 24,2021 03:50:00 PM | Aug 24,2021 05:35:00 PM | Connected AC DC card with System for Li ion compatibility and Testing with Mains without battery connection
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 24,2021 05:40:00 PM | Aug 24,2021 06:00:00 PM | Discuss Li-ion compatibility point with Tarun Sir,
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 25,2021 09:30:00 AM | Aug 25,2021 10:10:00 AM | working on EinFrame , Project status, Time sheet , pending tasks,
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Aug 25,2021 10:30:00 AM | Aug 25,2021 11:20:00 AM | Graphical LCD Testing with Product
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 26,2021 09:00:00 AM | Aug 26,2021 01:00:00 PM | Solved the Issue in Graphical LCD PCB (Power supply Issue)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 26,2021 02:00:00 PM | Aug 26,2021 03:00:00 PM | Firmware management of graphical LCD and implementation of Switches
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Aug 25,2021 11:40:00 AM | Aug 25,2021 12:40:00 PM | Check Mains Boost and float voltage at mains and Testing of TDR with low and high cutt
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Aug 25,2021 02:10:00 PM | Aug 25,2021 02:55:00 PM | Check Graphical LCD data with system and check LCD Supply Noise
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 25,2021 05:05:00 PM | Aug 25,2021 06:10:00 PM | Check Change over Time and ups/ nor mode, Synchronization with Mains
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 26,2021 09:15:00 AM | Aug 26,2021 09:35:00 AM | working on EinFrame , Project status, Time sheet , pending tasks,
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 26,2021 09:35:00 AM | Aug 26,2021 10:10:00 AM | Make circuit of Ac current sensing and control card changes
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Aug 26,2021 11:10:00 AM | Aug 26,2021 12:15:00 PM | Design control card PCB 1088 Rev 1.1 with pandey ji
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 26,2021 12:15:00 PM | Aug 26,2021 01:20:00 PM | Remove Set up of 10KW MPPT PCU For Jig Transfer
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Ramashish Kumar | Aug 27,2021 09:30:00 AM | Aug 27,2021 04:00:00 PM | Power Wiring in Jig
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 28,2021 10:15:00 AM | Aug 28,2021 01:00:00 PM | firmware management of graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 28,2021 02:15:00 PM | Aug 28,2021 05:00:00 PM | firmware management of graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 27,2021 09:15:00 AM | Aug 27,2021 05:30:00 PM | firmware management of graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Aug 26,2021 02:45:00 PM | Aug 26,2021 04:00:00 PM | Design AC Current sensing Schematic With Pandey ji
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Sandeep Jain | Aug 30,2021 10:30:00 AM | Aug 30,2021 11:30:00 AM | work on chassis & part selection
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Pawan Kumar Sharma | Aug 30,2021 03:05:00 PM | Aug 30,2021 03:30:00 PM | Repair IGBT Driver card
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 27,2021 09:30:00 AM | Aug 27,2021 10:10:00 AM | Discuss Tarun Sir Regarding Higher KVA Jig, Project status, Driver Card IGBT
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 27,2021 10:25:00 AM | Aug 27,2021 01:15:00 PM | Arrange Set up of Higher KVA Jig, computer , Table fot Testing
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 27,2021 02:00:00 PM | Aug 27,2021 03:30:00 PM | Arrange Set up of Higher KVA Jig, computer , Table for Testing
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 27,2021 04:00:00 PM | Aug 27,2021 05:45:00 PM | Connect system with Jig for Testing and Testing with Test Format
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Aug 30,2021 04:30:00 PM | Aug 30,2021 06:00:00 PM | Firmware management added the protection and warning features
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Aug 31,2021 11:30:00 AM | Aug 31,2021 01:30:00 PM | Design of Schematic for Graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Aug 31,2021 02:30:00 PM | Aug 31,2021 03:00:00 PM | Design of Schematic for Graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Aug 28,2021 11:10:00 AM | Aug 28,2021 11:30:00 AM | Check Project status and Time sheet on Einframe
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 28,2021 12:00:00 PM | Aug 28,2021 01:15:00 PM | Change MOSFET into Transistor TIP 122 and 127 and Testing with System
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 28,2021 02:10:00 PM | Aug 28,2021 05:55:00 PM | Check IGBT Driver With TIP 122 , 127 and Testing with System
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Aug 28,2021 05:55:00 PM | Aug 28,2021 06:15:00 PM | Check LCD data and actual data with Product
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 30,2021 09:10:00 AM | Aug 30,2021 09:30:00 AM | Study of Datasheet TIP 122, TIP 127 and its use
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Umesh Likhitkar | Aug 30,2021 09:30:00 AM | Aug 30,2021 12:30:00 PM | Mechanical Design of Chassis with Bharat Kakra
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 30,2021 12:35:00 PM | Aug 30,2021 01:15:00 PM | Repair Driver Card for Check TIP 122, 127 transistor
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Aug 30,2021 02:10:00 PM | Aug 30,2021 03:10:00 PM | Planing of Final LCD PCB Design with Sundeep sir and Rajashekshar
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 30,2021 03:15:00 PM | Aug 30,2021 05:45:00 PM | Working of Driver Circuit, Transistor Damaged During testing of Driver with System.. This transistor working not properly
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Aug 31,2021 09:30:00 AM | Aug 31,2021 09:45:00 AM | Discuss LCD PCB planing with tarun sir and Pandey ji
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Aug 31,2021 09:50:00 AM | Aug 31,2021 10:20:00 AM | Review and provided Component full print data for AC Current sensing PCB Design
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Umesh Likhitkar | Aug 31,2021 11:10:00 AM | Aug 31,2021 12:20:00 PM | Discuss with Jalaj sir and Sundeep Regarding terminal block , cost for 10KVA kaizen Model
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Aug 31,2021 02:10:00 PM | Aug 31,2021 05:00:00 PM | Arrange setup for IGBT driver card testing with Transistor, repair Diver card, analysis of TIP 122 Transistor regarding Frequency working, Discuss data with sobhag prajapat
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Aug 31,2021 05:10:00 PM | Aug 31,2021 05:30:00 PM | check transistor and PCB track of AC current sensing
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Aug 31,2021 05:45:00 PM | Aug 31,2021 06:10:00 PM | Discuss PCB status with Tarin Sir
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Sep 01,2021 09:35:00 AM | Sep 01,2021 10:40:00 AM | Discuss PCB Status with tarun sir and Pandey ji, Review AC Current sense PCB for send to Vendor
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Sep 01,2021 11:00:00 AM | Sep 01,2021 12:10:00 PM | Discuss and finalize LCD Schematic with Raja shekhar and share data to Pandey ji
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 01,2021 12:10:00 PM | Sep 01,2021 12:45:00 PM | Work on Einframe project status, time sheet,
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 01,2021 12:45:00 PM | Sep 01,2021 01:05:00 PM | Discuss with tarun sir and syoji ram sharma regarding Mains sensing with 1K Resistance, 10K and 3200surja
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 01,2021 10:00:00 AM | Sep 01,2021 01:00:00 PM | Firmware management(Arranging the LCD Display pattern and Implementing the tuning tool)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 01,2021 02:00:00 PM | Sep 01,2021 05:30:00 PM | Firmware management(Arranging the LCD Display pattern and Implementing the tuning tool)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 02,2021 02:00:00 PM | Sep 02,2021 05:30:00 PM | Firmware management(Address verification and Preparing the Tuning tool ang fixing the bugs)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 02,2021 10:00:00 AM | Sep 02,2021 01:30:00 PM | Firmware management(Address verification and Preparing the Tuning tool ang fixing the bugs)
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Sep 03,2021 02:00:00 PM | Sep 03,2021 03:00:00 PM | Schematic Verification and made the changes in schematic power supply section
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 03,2021 10:00:00 AM | Sep 03,2021 01:00:00 PM | Correction and new Changes done in Tuning tool of LCD and verifying TOOL with systemsytem
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Sep 03,2021 03:00:00 PM | Sep 03,2021 05:30:00 PM | Implementation of Tuning Parameters and verifying
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 01,2021 02:00:00 PM | Sep 01,2021 03:30:00 PM | replace Diode 4148 into 1K Resistance and check mains Problem. Mains sensing OK and other data regarding Tuning tool is OK. Data share with Tarun sir and Syoji ram Sharma
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 02,2021 09:30:00 AM | Sep 02,2021 10:25:00 AM | Check LCD data with raja sheskhar and tunning Tool
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 02,2021 10:30:00 AM | Sep 02,2021 11:35:00 AM | Team meeting regarding tuning tool, LCD, Wify with Tarun sir, Bharti sharma, Raja shekhar, Abhishek gupta
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Sep 02,2021 11:35:00 AM | Sep 02,2021 01:20:00 PM | Check ES mode function and add one more fan and TDR Circuit proper connection setup arrange for Testing
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 01,2021 05:00:00 PM | Sep 01,2021 06:00:00 PM | Testing with Tesing Farmet and LCD Data with Raja shekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 02,2021 03:20:00 PM | Sep 02,2021 06:30:00 PM | Check LCD and Tunnig tool and testing of system( Mains charging range, ES mode Function) Tunning Data , Max charging, solar+mains sharing
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 03,2021 09:30:00 AM | Sep 03,2021 10:10:00 AM | Check LCD Schematic with Controller Pin and Power supply, With raja shekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Sep 03,2021 10:20:00 AM | Sep 03,2021 11:20:00 AM | LCD PCB Circuit Design With pandey ji and rajashekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 03,2021 11:30:00 AM | Sep 03,2021 12:10:00 PM | Check New Tuning tool with Graphical LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 03,2021 12:20:00 PM | Sep 03,2021 01:25:00 PM | Compare shunt Position in exiting 10KW and 10KW Kaizen for Mains Current + Solar current sharing Problem
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Sep 04,2021 10:05:00 AM | Sep 04,2021 12:45:00 PM | Graphical LCD PCB Schematic Changes According to Design and Placement of LCD and Switches on LCD
Project activity | 10KW/120V MPPT PCU Kaizen | Final Design Review After Testing | Umesh Likhitkar | Jalaj Mathur | Sep 06,2021 01:00:00 PM | Sep 06,2021 01:30:00 PM | Discussion about LCD capability and use menu concept instead of giving 9 switches, suggested to minimize switches on front
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 06,2021 09:00:00 AM | Sep 06,2021 11:00:00 AM | worked on solar voltage and solar current tuning button. There is some problem related to tuned button that data is not according to press on tuned button.
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 04,2021 02:00:00 PM | Sep 04,2021 04:00:00 PM | Implementation of new features like Battery Status, Mains status ...
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 04,2021 04:00:00 PM | Sep 04,2021 06:00:00 PM | Resolving the issues of Tuning tool
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 04,2021 09:00:00 AM | Sep 04,2021 11:00:00 AM | new tuning tool design for 10kw mppt lcd model.
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 04,2021 04:30:00 PM | Sep 04,2021 05:30:00 PM | some changes related to tuning tool has been done .
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Sep 04,2021 09:30:00 AM | Sep 04,2021 10:00:00 AM | Updating the Addresses for WIFI and Tuning tool
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 06,2021 09:30:00 AM | Sep 06,2021 01:00:00 PM | Resolving the Issue of Tuning Parameters of Solar volt and Current
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 06,2021 02:00:00 PM | Sep 06,2021 03:00:00 PM | Serial Number Implementation in TT
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 06,2021 04:00:00 PM | Sep 06,2021 05:30:00 PM | serial number address has been changed and some data write on address .
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 02,2021 09:00:00 AM | Sep 02,2021 01:30:00 PM | New tuning tool design for 10KW MPPT LCD module
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 03,2021 09:00:00 AM | Sep 03,2021 11:00:00 AM | worked on 10KW MPPT LCD module there are some problem to show data on screen
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 03,2021 03:00:00 PM | Sep 03,2021 04:00:00 PM | worked on 10KW MPPT LCD tuning tool there are some problem in tuning button.
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 03,2021 04:10:00 PM | Sep 03,2021 05:30:00 PM | worked on 10KW MPPT LCD tuning tool there are some problem in tuning button.
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 03,2021 02:10:00 PM | Sep 03,2021 04:30:00 PM | Check System with old Software M4R8 for Mains and Solar sharing working issue, Testing with Old LCD and tuning tool, Check ES mode Function. it is Found OK.
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 03,2021 04:30:00 PM | Sep 03,2021 04:40:00 PM | Discuss with tarun sir Regarding mains and solar Current Sharing Issue with Sharma ji
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 03,2021 04:50:00 PM | Sep 03,2021 06:10:00 PM | Check LCD Data and Tuning tool with raja shekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 04,2021 09:35:00 AM | Sep 04,2021 12:20:00 PM | Discuss wit tarun sir Regarding Mains + Solar Current sharing Issue, Check with Software Rev14S_6. Check address on tuning tool, Check Software MOS Rev 8 for finding Problem
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 04,2021 12:20:00 PM | Sep 04,2021 12:40:00 PM | check Project Status and time sheet on Einframe
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Sep 04,2021 02:00:00 PM | Sep 04,2021 04:00:00 PM | check LCD PCB(LCD full frint, LED and switch position )
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 04,2021 04:00:00 PM | Sep 04,2021 04:40:00 PM | check Software Rev14_S7 For mains and solar current Problem resolved issue. Issue resolved
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 04,2021 04:50:00 PM | Sep 04,2021 06:10:00 PM | check Tunnig tool and graphical LCD data with rajashekhar and bharti Madam
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Sep 06,2021 03:00:00 PM | Sep 06,2021 05:30:00 PM | Switch Modification in PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 07,2021 10:30:00 AM | Sep 07,2021 01:00:00 PM | New Implementation In Graphical LCD like Flow graph and Slides Updatations
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Pawan Kumar Sharma | Sep 07,2021 09:30:00 AM | Sep 07,2021 11:00:00 AM | Mounting of control card 1088 rev1.1 for 10KW MPPT PCU and Harness
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rajashekhar K | Sep 07,2021 09:00:00 AM | Sep 07,2021 10:30:00 AM | Verification of PCB connection According to Schematic
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 07,2021 02:00:00 PM | Sep 07,2021 04:30:00 PM | Firmware management added New Features (Switch Control Implementation and backlight brightness control))
Project activity | 10KW/120V MPPT PCU Kaizen | Final Design Review After Testing | Umesh Likhitkar | Umesh Likhitkar | Sep 06,2021 01:00:00 PM | Sep 06,2021 01:35:00 PM | Final Design Review with Team
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 06,2021 12:30:00 PM | Sep 06,2021 12:55:00 PM | BOM Creation of 10KW MPPT PCU with Reference of 10KVA Surja BOM
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Sep 06,2021 02:30:00 PM | Sep 06,2021 04:10:00 PM | LCD PCB Verification with Pandey ji
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 06,2021 04:20:00 PM | Sep 06,2021 05:30:00 PM | Testing of graphical LCD with tuning Tool
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 06,2021 05:30:00 PM | Sep 06,2021 06:25:00 PM | LCD PCB Verification with Pandey ji and Sundeep Sir
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Sep 06,2021 11:10:00 AM | Sep 06,2021 12:30:00 PM | Verify and check LCD PCB of 10 KW mounting and PCB size Discuss with Sundeep sir and raja shekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Umesh Likhitkar | Sep 07,2021 11:00:00 AM | Sep 07,2021 11:30:00 AM | Discuss to sundeep sir regarding 10KW Chassis and PCB
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 07,2021 11:40:00 AM | Sep 07,2021 12:10:00 PM | Provide Legend to Pawan Sharma for Control card 1088Rev 1.1 mounting.
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 07,2021 12:20:00 PM | Sep 07,2021 01:10:00 PM | Working on BOM 10KW MPPT PCU
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 07,2021 02:00:00 PM | Sep 07,2021 05:00:00 PM | Working on BOM 10KW MPPT PCU
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 07,2021 05:10:00 PM | Sep 07,2021 06:00:00 PM | System Testing With New control card 1088 Rev 1.1
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 07,2021 06:05:00 PM | Sep 07,2021 06:35:00 PM | work on einframe software Project status , time sheet
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Sandeep Jain | Sep 06,2021 03:00:00 PM | Sep 06,2021 05:00:00 PM | Discussed with designer for PCB Design mechanical layout
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Sandeep Jain | Sep 08,2021 11:00:00 AM | Sep 08,2021 12:00:00 PM | Chassis Drawing concept review
Project activity | 10KW/120V MPPT PCU Kaizen | Plan Development incl. Long Lead identification | Umesh Likhitkar | Sandeep Jain | Sep 07,2021 11:00:00 AM | Sep 07,2021 01:00:00 PM | Discussion on Electro-mechanical component selection
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Sandeep Jain | Sep 07,2021 03:00:00 PM | Sep 07,2021 05:00:00 PM | PCB Design review
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Bharat Kakra | Sep 08,2021 09:00:00 AM | Sep 08,2021 01:00:00 PM | chassis making
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Bharat Kakra | Sep 01,2021 09:00:00 AM | Sep 01,2021 01:00:00 PM | chassis making
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Bharti Sharma | Sep 08,2021 09:00:00 AM | Sep 08,2021 10:00:00 AM | tuning tool work has completed
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Aug 31,2021 09:30:00 AM | Aug 31,2021 02:30:00 PM | contral card PCB 1088Rev 1.1 design and check with Umesh
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Aug 31,2021 02:45:00 PM | Aug 31,2021 06:00:00 PM | AC current sense PCB CKT design with Umesh
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 01,2021 09:30:00 AM | Sep 01,2021 01:30:00 PM | AC current sense PCB design with Umesh and Sundeep sir
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 01,2021 02:10:00 PM | Sep 01,2021 06:00:00 PM | AC current sense PCB design with Umesh and Sundeep sir
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 03,2021 02:10:00 PM | Sep 03,2021 06:00:00 PM | LCD PCB Scamatic Design with umesh and RAjashekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 04,2021 09:30:00 AM | Sep 04,2021 12:00:00 PM | LCD PCB Scamatic Design with umesh and RAjashekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 04,2021 12:00:00 PM | Sep 04,2021 01:00:00 PM | LCD PCB Scamatic Design with umesh and RAjashekhar
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 04,2021 02:00:00 PM | Sep 04,2021 06:00:00 PM | LCD PCB Design with Graphical LCD Full print With umesh & Raja
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 06,2021 09:35:00 AM | Sep 06,2021 01:00:00 PM | LCD PCB Design with Graphical LCD Full print With umesh & Raja
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 06,2021 02:00:00 PM | Sep 06,2021 06:30:00 PM | LCD PCB Design with Graphical LCD Full print With umesh & Raja
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Rakesh Pandey | Sep 07,2021 09:20:00 AM | Sep 07,2021 12:45:00 PM | LCD PCB Review With Umesh and Sundeep sir, PCB file send to Sundeep sir
Project activity | 10KW/120V MPPT PCU Kaizen | Final PCB Design of LCD and other PCB Modification | Umesh Likhitkar | Umesh Likhitkar | Sep 07,2021 09:30:00 AM | Sep 07,2021 11:00:00 AM | Verify and Check LCD PCB with pandey ji
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 08,2021 04:30:00 PM | Sep 08,2021 06:00:00 PM | Firmware management.
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Bharat Kakra | Sep 08,2021 01:30:00 PM | Sep 08,2021 05:30:00 PM | mechanical drawing
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Sandeep Jain | Sep 09,2021 10:45:00 AM | Sep 09,2021 12:00:00 PM | 10KW Chassis Design Review
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 08,2021 09:45:00 AM | Sep 08,2021 10:10:00 AM | Check Project status on Einframe
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Umesh Likhitkar | Sep 08,2021 10:20:00 AM | Sep 08,2021 12:40:00 PM | Provide dimension of TB, LCD PCB location, Rotary , Ac current PCB Location and check in 3D
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 08,2021 02:25:00 PM | Sep 08,2021 03:00:00 PM | Make BOM of 10KW MPPT PCU Kaizen
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Umesh Likhitkar | Sep 08,2021 05:25:00 PM | Sep 08,2021 05:50:00 PM | Approve project task and Review time sheet
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Bharat Kakra | Sep 09,2021 09:00:00 AM | Sep 09,2021 01:00:00 PM | Drawings
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Bharat Kakra | Sep 09,2021 01:30:00 PM | Sep 09,2021 05:25:00 PM | Drawings
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Sandeep Jain | Sep 10,2021 04:00:00 PM | Sep 10,2021 04:30:00 PM | Chassis Review and sent to vendor for development
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Sandeep Jain | Sep 09,2021 03:00:00 PM | Sep 09,2021 05:30:00 PM | LCD PCB/ Control PCB/ AC Current Sensing Review & sent to vendor for development
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 10,2021 05:20:00 PM | Sep 10,2021 06:00:00 PM | make BOM
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 10,2021 04:30:00 PM | Sep 10,2021 05:00:00 PM | Check LCD data and very control card
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 10,2021 09:30:00 AM | Sep 10,2021 11:00:00 AM | make BOM
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 10,2021 11:30:00 AM | Sep 10,2021 01:30:00 PM | make BOM and sent to Shweta madam for update in SAP 1st version
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Sep 09,2021 02:00:00 PM | Sep 09,2021 04:30:00 PM | make BOM
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 10,2021 09:10:00 AM | Sep 10,2021 01:00:00 PM | Firmware management added Menu implementation
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 10,2021 02:00:00 PM | Sep 10,2021 06:00:00 PM | Firmware management added Menu implementation
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 11,2021 09:00:00 AM | Sep 11,2021 01:00:00 PM | Firmware management added Menu implementation
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Bharat Kakra | Sep 10,2021 11:00:00 AM | Sep 10,2021 02:00:00 PM | 2D drawing
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 15,2021 09:00:00 AM | Sep 15,2021 01:00:00 PM | Firmware management.(MENU Implementation )
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 14,2021 02:00:00 PM | Sep 14,2021 06:00:00 PM | Firmware management.(MENU Implementation )
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 15,2021 04:00:00 PM | Sep 15,2021 06:00:00 PM | Firmware management.(MENU Implementation )
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 13,2021 09:30:00 AM | Sep 13,2021 01:00:00 PM | Firmware management.(MENU Implementation )
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 16,2021 09:30:00 AM | Sep 16,2021 01:00:00 PM | Firmware management.(Communication Handling )
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 16,2021 02:00:00 PM | Sep 16,2021 03:00:00 PM | Firmware management.(Communication Handling )
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 17,2021 09:00:00 AM | Sep 17,2021 01:30:00 PM | Firmware management.(Communication(SCI) Time Management )
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Rajashekhar K | Sep 21,2021 11:00:00 AM | Sep 21,2021 01:00:00 PM | Arranging the Material for Graphical LCD PCB and Fill Legend and Creation BOM for LCD PCB
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Rajashekhar K | Sep 21,2021 02:00:00 PM | Sep 21,2021 03:00:00 PM | Arranging the Material for Graphical LCD PCB and Fill Legend and Creation BOM for LCD PCB
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Rajashekhar K | Sep 21,2021 03:00:00 PM | Sep 21,2021 05:30:00 PM | Verifying the PCB 1118 REV 1.0 and Firmware management(Changes in PIN config) According to the NEW PCB
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Rajashekhar K | Sep 22,2021 09:25:00 AM | Sep 22,2021 11:00:00 AM | resolving the Issue in New graphical LCD PCB(1118 Rev1.0) and noted the changes in PCB to update in next revision
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Rajashekhar K | Sep 22,2021 12:00:00 PM | Sep 22,2021 01:00:00 PM | resolving the Issue in New graphical LCD PCB(1118 Rev1.0) and noted the changes in PCB to update in next revision
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Rajashekhar K | Sep 22,2021 02:00:00 PM | Sep 22,2021 03:15:00 PM | resolving the Issue in New graphical LCD PCB(1118 Rev1.0) and noted the changes in PCB to update in next revision
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 22,2021 04:15:00 PM | Sep 22,2021 06:00:00 PM | Firmware management.(LED's Functionality Implementation and buzzer Implementation ) in New PCB 1118 Rev 1.0
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 23,2021 10:20:00 AM | Sep 23,2021 01:20:00 PM | Firmware management.(Screen Saver implementation)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 23,2021 02:20:00 PM | Sep 23,2021 06:30:00 PM | Firmware management.(Screen Saver implementation)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 24,2021 09:30:00 AM | Sep 24,2021 01:00:00 PM | Firmware management.(Decrease the size of code to save flash memory)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 24,2021 02:00:00 PM | Sep 24,2021 06:30:00 PM | Firmware management.(Decrease the size of code to save flash memory)
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Umesh Likhitkar | Sep 22,2021 12:40:00 PM | Sep 22,2021 01:20:00 PM | Check LCD PCB and resolve supply problem
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Sep 27,2021 09:00:00 AM | Sep 27,2021 06:00:00 PM | Firmware management.(MENU Implementation )
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Sep 29,2021 02:00:00 PM | Sep 29,2021 03:40:00 PM | WiFi Prgraming
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Sep 30,2021 02:00:00 PM | Sep 30,2021 05:55:00 PM | WiFi software testing and changes
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Sep 28,2021 12:35:00 PM | Sep 28,2021 01:30:00 PM | working on New IR IGBT Driver
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Sep 28,2021 03:10:00 PM | Sep 28,2021 05:30:00 PM | working on Driver with Vikash for 15v and -12V
Project activity | 10KW/120V MPPT PCU Kaizen | TDR, Li-ion Comp-ability, 15V and -5V Driver Voltage , Inverter Heat sink Heating issue | Umesh Likhitkar | Umesh Likhitkar | Sep 29,2021 09:40:00 AM | Sep 29,2021 10:20:00 AM | Check 10KW driver IR Circuit with jig and CRO
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Sep 29,2021 03:00:00 PM | Sep 29,2021 06:00:00 PM | Firmware management. Testing the WIFI with System
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Sep 30,2021 02:00:00 PM | Sep 30,2021 06:00:00 PM | Firmware management
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Sep 30,2021 09:35:00 AM | Sep 30,2021 01:00:00 PM | Firmware management
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Oct 01,2021 03:00:00 PM | Oct 01,2021 06:00:00 PM | Firmware management (Switch control through WIFI)
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Sep 29,2021 12:10:00 PM | Sep 29,2021 01:20:00 PM | Working with Vikash in 10KW MPPT PCU
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Sep 29,2021 04:30:00 PM | Sep 29,2021 05:15:00 PM | Working with Vikash in 10KW MPPT PCU
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Oct 04,2021 11:10:00 AM | Oct 04,2021 11:40:00 AM | working with vikash on 10kw regarding solar range
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Oct 04,2021 04:30:00 PM | Oct 04,2021 05:20:00 PM | Check LCD with Wifi, MPPT range data on 260V , shaort circuit problem and VCE voltage
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Oct 05,2021 09:30:00 AM | Oct 05,2021 11:00:00 AM | Firmware management
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Oct 05,2021 02:00:00 PM | Oct 05,2021 05:00:00 PM | Firmware management
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Oct 06,2021 02:00:00 PM | Oct 06,2021 06:00:00 PM | Software testing and switch communication implementation
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Oct 06,2021 11:05:00 AM | Oct 06,2021 01:15:00 PM | Switch functionality check and some issues with LCD resolve
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Sep 30,2021 09:30:00 AM | Sep 30,2021 05:00:00 PM | Adjust AC current protection on 45A
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 01,2021 02:00:00 PM | Oct 01,2021 06:00:00 PM | Solar sensing connection and discussion with sir
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 01,2021 09:30:00 AM | Oct 01,2021 11:00:00 AM | Test plan making and discussion
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 01,2021 11:10:00 AM | Oct 01,2021 01:00:00 PM | Voltage peak measurement with VOC 250V
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 04,2021 09:30:00 AM | Oct 04,2021 01:00:00 PM | IGBT Voltage peak measurement with VOC 250V
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 04,2021 02:00:00 PM | Oct 04,2021 05:00:00 PM | IGBT Voltage and Current peak measurement with VOC 250V
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 05,2021 09:30:00 AM | Oct 05,2021 10:30:00 AM | discussion of Result with sir and further plan
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 05,2021 10:35:00 AM | Oct 05,2021 06:00:00 PM | IGBT current and voltage peak measurement with VOC 328V
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 06,2021 09:30:00 AM | Oct 06,2021 06:00:00 PM | Snubber adjustment as peak reaching upto 584V
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 07,2021 09:30:00 AM | Oct 07,2021 06:00:00 PM | MPPT point checking with resistive and inductive load
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 08,2021 09:30:00 AM | Oct 08,2021 01:00:00 PM | Tunning Tool and untunned condition resolution
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Oct 07,2021 09:00:00 AM | Oct 07,2021 10:00:00 AM | Firmware management
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Oct 07,2021 12:00:00 PM | Oct 07,2021 01:00:00 PM | Firmware management
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Oct 07,2021 02:00:00 PM | Oct 07,2021 06:00:00 PM | Firmware management (Switch control through WIFI) and testing with product
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Rajashekhar K | Oct 08,2021 02:00:00 PM | Oct 08,2021 06:00:00 PM | Firmware management (Switch control through WIFI) and testing with product and time and date implementation
Project activity | 10KW/120V MPPT PCU Kaizen | Graphical LCD Implementation and Replace by 16X2 LCD, Testing With Product | Umesh Likhitkar | Rajashekhar K | Oct 08,2021 09:00:00 AM | Oct 08,2021 01:00:00 PM | issue resolved regarding the untuned condition LCD handling
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Oct 07,2021 03:35:00 PM | Oct 07,2021 05:20:00 PM | Switch functona;lity with LCD since LCD is not working properly on the switch commands
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Oct 07,2021 05:25:00 PM | Oct 07,2021 06:05:00 PM | WiFi software testing and some changes
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 09,2021 09:10:00 AM | Oct 09,2021 03:20:00 PM | System assemble in new chassis
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 11,2021 09:30:00 AM | Oct 11,2021 05:50:00 PM | System assembly in New Chassis
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 12,2021 09:30:00 AM | Oct 12,2021 01:00:00 PM | System assembled and run checked on backup, solar, Mains
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 13,2021 11:00:00 AM | Oct 13,2021 04:20:00 PM | Identified problem in LCD are relsolved and new screen saver Designed
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Abhishek Gupta | Oct 14,2021 09:30:00 AM | Oct 14,2021 09:45:00 AM | Depending on the LCD firmware then WiFi will be taken care and also i have done the wifi work vikas will tell the points not running properly
Project activity | 10KW/120V MPPT PCU Kaizen | Integration testing | Umesh Likhitkar | Ramashish Kumar | Oct 08,2021 09:35:00 AM | Oct 08,2021 04:00:00 PM | assemble sistem
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Ramashish Kumar | Oct 11,2021 09:35:00 AM | Oct 11,2021 04:00:00 PM | assemble sistem
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 14,2021 02:00:00 PM | Oct 14,2021 06:30:00 PM | Work done Regarding MPPT output current as having issue in energy saver mode time
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 14,2021 09:30:00 AM | Oct 14,2021 01:00:00 PM | LCD contrast adjustment and arrow working
Project activity | 10KW/120V MPPT PCU Kaizen | Mechanical Drawings | Umesh Likhitkar | Bharat Kakra | Oct 12,2021 09:00:00 AM | Oct 12,2021 09:30:00 AM | harness drawings
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Rajashekhar K | Oct 15,2021 09:00:00 AM | Oct 15,2021 01:00:00 PM | Firmware management resolving the issue like battery state
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 18,2021 09:00:00 AM | Oct 18,2021 01:00:00 PM | LCD energy saver mode arrows and tunning tool error added
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 16,2021 11:00:00 AM | Oct 16,2021 06:00:00 PM | IGBT changed and Driver pulse verified after burnt
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 15,2021 11:00:00 AM | Oct 15,2021 12:00:00 PM | Tunning Checking with LCD tunning Tool and inverter tool
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 15,2021 10:00:00 AM | Oct 15,2021 10:40:00 AM | Discussion on remaing problems and their respective action
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 15,2021 02:00:00 PM | Oct 15,2021 04:00:00 PM | Solar section driver repair as got damaged
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 15,2021 04:05:00 PM | Oct 15,2021 06:00:00 PM | Inverter Testing regarding parameter other than solar
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Abhishek Gupta | Oct 18,2021 03:35:00 PM | Oct 18,2021 05:40:00 PM | Serial number address was not correct so correction are done and further put on testing
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Rajashekhar K | Oct 20,2021 11:00:00 AM | Oct 20,2021 01:00:00 PM | Resolved the issues like Solar current battery state
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Rajashekhar K | Oct 19,2021 11:00:00 AM | Oct 19,2021 01:00:00 PM | ARROW Design
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Rajashekhar K | Oct 19,2021 02:00:00 PM | Oct 19,2021 03:00:00 PM | ARROW Design
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 19,2021 09:00:00 AM | Oct 19,2021 06:00:00 PM | Solar charger on and Soalr output current variable data reading addded
Project activity | 10KW/120V MPPT PCU Kaizen | All PCB review and revision | Umesh Likhitkar | Rajashekhar K | Oct 19,2021 04:00:00 PM | Oct 19,2021 05:00:00 PM | Updated the PCB 1118
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Rajashekhar K | Oct 19,2021 05:00:00 PM | Oct 19,2021 06:00:00 PM | Firmware management
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Rajashekhar K | Oct 18,2021 02:00:00 PM | Oct 18,2021 06:00:00 PM | Firmware management and testing WIFi
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Jalaj Mathur | Oct 22,2021 08:00:00 AM | Oct 22,2021 08:05:00 AM | No inputs received to do this task, please confirm about task
Project activity | 10KW/120V MPPT PCU Kaizen | BOM update in SAP After Review | Umesh Likhitkar | Jalaj Mathur | Oct 22,2021 08:05:00 AM | Oct 22,2021 08:10:00 AM | No inputs received to do this task, please confirm about task
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 22,2021 02:00:00 PM | Oct 22,2021 06:00:00 PM | Testing of MOSFET duty cycle with respect to charging current
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 22,2021 09:30:00 AM | Oct 22,2021 01:00:00 PM | Testing Regarding mains overvoltage and lower voltage protection
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 21,2021 09:30:00 AM | Oct 21,2021 01:00:00 PM | Verification of LCD screen saver and scrolling data
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 20,2021 09:30:00 AM | Oct 20,2021 01:00:00 PM | LCD identified problem resolution
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 20,2021 02:00:00 PM | Oct 20,2021 06:00:00 PM | Time format and screen saver arrows redesigned having error
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Oct 23,2021 10:10:00 AM | Oct 23,2021 12:10:00 PM | Check Testing report with Vikash, Check pending work of 10KW MPPT PCU, Testing Support with Vikash
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 25,2021 11:10:00 AM | Oct 25,2021 06:00:00 PM | Validation format testing
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 26,2021 11:10:00 AM | Oct 26,2021 06:00:00 PM | Design document left one testing checked
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 23,2021 09:10:00 AM | Oct 23,2021 06:00:00 PM | Current sensor output voltage with respect to current measured and discussion regarding status
Project activity | 10KW/120V MPPT PCU Kaizen | Wi-Fi Software implantation for 10 KVA and Final Tuning tool Design | Umesh Likhitkar | Abhishek Gupta | Oct 26,2021 02:50:00 PM | Oct 26,2021 02:55:00 PM | From my side all the changes are done and no observation shared now
Project activity | 10KW/120V MPPT PCU Kaizen | BOM creation, optimization and SAP Update in draft version | Umesh Likhitkar | Umesh Likhitkar | Oct 27,2021 09:40:00 AM | Oct 27,2021 10:20:00 AM | make bom of 10kw mppt pcu
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Oct 29,2021 10:00:00 AM | Oct 29,2021 10:40:00 AM | Check heat run set up of 10KW MPPT with Vikash
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Oct 29,2021 01:00:00 PM | Oct 29,2021 01:35:00 PM | Check solar voltage and current sensing problem of 10kw MPPT PCU
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Oct 29,2021 05:00:00 PM | Oct 29,2021 05:35:00 PM | Check Heat run report and Setup of 10kw MPPT PCU
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 29,2021 02:00:00 PM | Oct 29,2021 04:00:00 PM | Issue clearance regarding solar over current and by default solar reading
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 29,2021 04:05:00 PM | Oct 29,2021 06:00:00 PM | Discharging profile at solar 40Amp for 2 hours
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 29,2021 09:40:00 AM | Oct 29,2021 12:30:00 PM | Setup for Heat run of system
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 28,2021 09:40:00 AM | Oct 28,2021 06:00:00 PM | Testing according to test format of validation
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Oct 30,2021 09:30:00 AM | Oct 30,2021 01:00:00 PM | Heat run discharging profile with solar at 40-41Amp 310VOC
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 01,2021 09:30:00 AM | Nov 01,2021 01:00:00 PM | Replaced damaged parts during heat run(Capacitor snubber input wire)
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 01,2021 02:00:00 PM | Nov 01,2021 05:30:00 PM | Make system on and general check after damage
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Nov 01,2021 12:30:00 PM | Nov 01,2021 01:15:00 PM | team meeting with Tarun sir Regarding heat run Report of 10KW
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Nov 01,2021 01:15:00 PM | Nov 01,2021 01:30:00 PM | Check 10kw MPPT PCU Re-assy. for ripple current measurements
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Nov 01,2021 05:20:00 PM | Nov 01,2021 06:00:00 PM | check Snubber data sheet and Analysis of ripple current
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Nov 01,2021 06:00:00 PM | Nov 01,2021 06:20:00 PM | fill time sheet on einframe
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 02,2021 11:10:00 AM | Nov 02,2021 01:00:00 PM | system setup on zig
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 09,2021 11:00:00 AM | Nov 09,2021 05:30:00 PM | Wire Process sheet Made
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 10,2021 10:00:00 AM | Nov 10,2021 05:30:00 PM | BOM Prepared
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 11,2021 09:00:00 AM | Nov 11,2021 05:30:00 PM | Ripple measured for Input filter Capacitor of Solar with wire Jointer
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 12,2021 11:00:00 AM | Nov 12,2021 12:00:00 PM | Capacitor Heating check at 10Amp solar
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 12,2021 02:00:00 PM | Nov 12,2021 05:30:00 PM | Capacitor ripple check With solar
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 13,2021 09:00:00 AM | Nov 13,2021 05:30:00 PM | Capacitor ripple check With solar VOc 310 V and 210V panel +Power supply
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 15,2021 09:30:00 AM | Nov 15,2021 06:00:00 PM | Capacitor is changed and Ripple measured at 10 amp
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 16,2021 09:30:00 AM | Nov 16,2021 06:00:00 PM | Ripple measured at 20 AMp
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 17,2021 09:30:00 AM | Nov 17,2021 01:00:00 PM | Ripple measured at 25 amp with IGBT collector emitter peak
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Nov 16,2021 05:00:00 PM | Nov 16,2021 05:30:00 PM | Check report with vikash
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 17,2021 02:00:00 PM | Nov 17,2021 06:00:00 PM | Voltage peak with3uF 1000V Snubber
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 18,2021 09:30:00 AM | Nov 18,2021 01:00:00 PM | MPPT input wire isssue at 20Amp solar
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 18,2021 02:00:00 PM | Nov 18,2021 06:00:00 PM | Ripple and peak data with Mppt input Capacitor 20000 MFD and snubber 2 uf 1000V
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 19,2021 09:00:00 AM | Nov 19,2021 11:00:00 AM | Inductor is changed as heating issue in input wire
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 19,2021 11:30:00 AM | Nov 19,2021 12:00:00 PM | ininput wire changed igbt to capacitor and negative
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 19,2021 12:00:00 PM | Nov 19,2021 01:00:00 PM | Wire changed from 16 sqmm to 25 sqmm
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 19,2021 02:00:00 PM | Nov 19,2021 06:00:00 PM | Checked heating of wire with 20 amp panel+ Supply
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 20,2021 09:30:00 AM | Nov 20,2021 01:00:00 PM | Heating checked with Wire is changed with 25 sqmm 2 nos as per plate in 10 kw
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 22,2021 09:30:00 AM | Nov 22,2021 01:00:00 PM | (wire changed )Heating checked with wire 35Sqmm double at 10 and 25Amp at no load and full load condition.
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 23,2021 02:00:00 PM | Nov 23,2021 04:00:00 PM | Snubber 2uf 1000 V is run with system 35Sqmm double wire(Snubber got damage in running condition after 20Minutes)
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 23,2021 04:05:00 PM | Nov 23,2021 06:00:00 PM | Worked for driver pulses check due to snubber Driver also malfunctioned.
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 25,2021 04:00:00 PM | Nov 25,2021 06:00:00 PM | Input capacitor reassembled with 3uF 1000V snubber and heating checked with no load at 5-10Amp(Power Supply)
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 26,2021 02:00:00 PM | Nov 26,2021 04:40:00 PM | Inductor calculation regarding buck converter for 210 VOc and 300 Voc
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 29,2021 09:40:00 AM | Nov 29,2021 05:50:00 PM | Inductor saturation current waveform sample measurement with 216uH and 336 uH inductor.
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Nov 30,2021 09:30:00 AM | Nov 30,2021 05:45:00 PM | Worked for input wire heating of IGBT with 10000MFD in place of 20000MFD
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Dec 01,2021 09:30:00 AM | Dec 01,2021 11:00:00 AM | Peda 500W control card problem for output and mains fluctution solved. with 8006 DSP
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Dec 01,2021 11:20:00 AM | Dec 01,2021 05:30:00 PM | Peda 500W battery of Sunvaru power checked
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Dec 02,2021 09:20:00 AM | Dec 02,2021 05:30:00 PM | Peda 500W with 8025 DSP worked for charging control for nohy and ES1 mode
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Vikash Sharma | Dec 03,2021 09:20:00 AM | Dec 03,2021 05:30:00 PM | Peda 500W with 8025 DSP worked for charging control for nohy and ES1 mode
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Nov 11,2021 11:30:00 AM | Nov 11,2021 01:30:00 PM | check report and testing of 10kw mmpt pcu regarding heating problem of MPPT .
Project activity | 10KW/120V MPPT PCU Kaizen | Final Testing With Product and Validation | Umesh Likhitkar | Umesh Likhitkar | Nov 11,2021 02:30:00 PM | Nov 11,2021 04:30:00 PM | check report and testing of 10kw mmpt pcu regarding heating problem of MPPT .

## CD
Charger Discharger CD1233
Task ID & Description | Planned Start/End | Actual Start/End | Sch. Variance | Planned Efforts | Actual Efforts | Effort Variance | Planned Cost | Actual Cost | Cost Variance
[151] Start | Aug 24, 2021 | - | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Latest Comments: | Aug 24, 2021 | -
Started OK
Abhishek Gupta [1%]
[152] Toll Gate 1 | Aug 24, 2021 | - | 0% | 0.8 | 0 | -100% | 80 | 0 | -100%
Latest Comments: | Aug 25, 2021 | -
Passed by tarun sir
Tarun Gupta [10%]
[155] Gravity measurement in software and testing | Aug 25, 2021 | Aug 24, 2021 | 100% | 8 | 10.34 | 29% | 155.2 | 19.68 | -87%
Latest Comments: | Aug 26, 2021 | Aug 28, 2021
29/10/21:- Also Tested when developed code accordingly and now removed again from customer feedback.. Verified from software
Abhishek Gupta [80%]Sobhag Prajapat [20%]
[158] requirment of resistive load , chassis and PCBs | Aug 25, 2021 | Aug 26, 2021 | -84.62% | 80 | 0.5 | -99% | 2336 | 2 | -100%
Latest Comments: | Sep 06, 2021 | Aug 26, 2021
ok
Sandeep Jain [90%]Sobhag Prajapat [10%]
[156] Wifi develkopement | Aug 26, 2021 | Sep 02, 2021 | 100% | 21.6 | 11.67 | -46% | 172.8 | 23.34 | -86%
Latest Comments: | Aug 30, 2021 | Sep 04, 2021
1/10/21:- All development are done but some changes are needed from costumer side. Final Check and give some comments from sobhag sir.
Abhishek Gupta [90%]
[157] wifi report developemnt | Aug 30, 2021 | Sep 03, 2021 | -13.33% | 85.84 | 19.67 | -77% | 2347.28 | 53.34 | -98%
Latest Comments: | Oct 13, 2021 | Oct 07, 2021
07/10/21:-The report was developed before the customer feedback. First draft is completed . After meeting need to develop new web page and WiFi reports
Abhishek Gupta [25%]Rohit Kumar Sachan [2%]Sobhag Prajapat [2%]
[267] material received | Sep 06, 2021 | Oct 13, 2021 | 0% | 17.36 | 2.5 | -86% | 513.36 | 5 | -99%
Latest Comments: | Oct 13, 2021 | Oct 13, 2021
material received for 4 nos system dated :13-10-21
Rohit Kumar Sachan [1%]Sandeep Jain [5%]Sobhag Prajapat [1%]
[159] assembly of 4 nos new system | Sep 06, 2021 | Sep 09, 2021 | 0% | 47.52 | 53.08 | 12% | 1182.72 | 96.24 | -92%
Latest Comments: | Oct 15, 2021 | Oct 15, 2021
29/10/21:- Testing running on those system and results are noted 15/10/21:- Assembled on 15 Oct 2021
Bharat Kakra [1%]Pawan Kumar Sharma [5%]Ramashish Kumar [1%]Rohit Kumar Sachan [10%]Sobhag Prajapat [1%]
[161] art work development and mechanical developement | Sep 06, 2021 | Aug 26, 2021 | 0% | 21.6 | 5.58 | -74% | 655.2 | 42.64 | -93%
Latest Comments: | Oct 29, 2021 | -
30-11-21 Art working related data pending from badri and nisha side 18-11-21 art work nmbr relsed from jalaj sir 16-11-21 write up for user manual and top sticker under dev in R&D ,packing drawing pending(already Request is given to mech team) 15-11-2021:-Follow up and processed by Rohit sachan in absence of sobhag sir 12Oct-21 follow up & no answer 26-07-2021:-Artwork Request has been mailed to Respective team
Abhishek Gupta [1%]Rohit Kumar Sachan [2%]Sandeep Jain [1%]Sobhag Prajapat [2%]
[268] HTML Page/ dash board Finalization from Customer side | Oct 13, 2021 | Nov 02, 2021 | 342.9% | 1.2 | 2.59 | 116% | 22 | 20.72 | -6%
Latest Comments: | Oct 19, 2021 | Nov 12, 2021
02 Nov 2021 The html page received with 10 times size 27-Oct-2021 waiting for the customer response to final confirm the given page. Waiting for the customer response
Abhishek Gupta [2%]Sobhag Prajapat [1%]
[271] Design Review Hardware ,Software And testing Data | Oct 15, 2021 | Nov 18, 2021 | 0% | 34 | 0.17 | -100% | 4030 | 1.36 | -100%
Abhishek Gupta [5%]Rohit Kumar Sachan [5%]Sobhag Prajapat [5%]Tarun Gupta [2%] | Nov 18, 2021 | -
[269] Interfacing HTML /Dashboard with System with actual data and final review from customer | Oct 19, 2021 | Oct 19, 2021 | 200% | 9.12 | 10.08 | 11% | 252.96 | 90.64 | -64%
Latest Comments: | Oct 21, 2021 | Oct 27, 2021
27/10/21Observation Resolved after testing.
Abhishek Gupta [50%]Rohit Kumar Sachan [5%]Sobhag Prajapat [2%]
[270] WiFi report development and WiFi report testing | Oct 21, 2021 | Oct 26, 2021 | 0% | 39.2 | 29.33 | -25% | 957.6 | 237.14 | -75%
Latest Comments: | Oct 29, 2021 | -
13-11-21:- HTML page developed as provided without image.
Abhishek Gupta [40%]Rohit Kumar Sachan [20%]Sobhag Prajapat [10%]
[162] BOM First Draft developement | Oct 29, 2021 | Oct 12, 2021 | -475% | 6.72 | 10.58 | 57% | 118.08 | 25.16 | -79%
Latest Comments: | Nov 01, 2021 | Oct 12, 2021
21/10/21:- First draft mailed to shweta mam
Abhishek Gupta [2%]Rohit Kumar Sachan [20%]Sobhag Prajapat [20%]
[163] BOM first draft upload in SAP | Nov 01, 2021 | Nov 13, 2021 | 550% | 3.6 | 6.25 | 74% | 50 | 50 | 0%
Latest Comments: | Nov 02, 2021 | Nov 13, 2021
16-11-21;- Upload in sap packing and artwork is pending.
Rohit Kumar Sachan [5%]Shweta Aggarwal [40%]
[160] testing of complete system with wifi And All Supporting Documents developement | Nov 02, 2021 | Sep 06, 2021 | 0% | 88 | 36.68 | -58% | 2152 | 146.735 | -93%
Latest Comments: | Nov 18, 2021 | -
23-11-21:- Customer and service mode added in the main firmware and testing going on service mode testing and customer mode remaining, wifi development related mode is pending 18/11/21:- Testing halted because of cutomer and service mode adding 29/10/21:- Found some issues with cutt off voltage recording 21/10/21:- Pending as of now
Abhishek Gupta [20%]Bharti Sharma [10%]Rohit Kumar Sachan [70%]Sobhag Prajapat [10%]
[274] BOM Second draft developement | Nov 18, 2021 | - | 0% | 2.4 | 0 | -100% | 19.2 | 0 | -100%
Latest Comments: | Nov 19, 2021 | -
23-11-21:- Testing of customer and service mode so delay further task.
Rohit Kumar Sachan [30%]
[275] BOM second draft upload in SAP | Nov 19, 2021 | - | 0% | 3.2 | 0 | -100% | 54.4 | 0 | -100%
Latest Comments: | Nov 20, 2021 | -
30-11-21 art work related data not developed 23-11-21:- Testing of customer and service mode so delay further task.
Rohit Kumar Sachan [20%]Shweta Aggarwal [20%]
[272] Validation Handover | Nov 20, 2021 | - | 0% | 6.4 | 0 | -100% | 182.4 | 0 | -100%
Abhishek Gupta [20%]Jalaj Mathur [20%]Rohit Kumar Sachan [20%]Sobhag Prajapat [20%] | Nov 22, 2021 | -
[164] validation schedule and planing | Nov 22, 2021 | - | 0% | 2.8 | 0 | -100% | 88.8 | 0 | -100%
Latest Comments: | Nov 23, 2021 | -
23-11-21:- Delay for some days bcoz of sm addition of feature and testing.
Abhishek Gupta [5%]Jalaj Mathur [20%]Rohit Kumar Sachan [5%]Sobhag Prajapat [5%]
[273] Validation phase -System testing , issues resolve problem solution and changes implementation and Documentation and Review and SAP final documentation with QA,LT,Spec | Nov 23, 2021 | - | 0% | 125.28 | 0 | -100% | 16718.4 | 0 | -100%
Latest Comments: | Dec 14, 2021 | -
23-11-21:- Delay for some days bcoz of sm addition of feature and testing.
Abhishek Gupta [5%]Jalaj Mathur [70%]Rohit Kumar Sachan [5%]Sobhag Prajapat [5%]Tarun Gupta [2%]
[153] Toll Gate 2 | Dec 14, 2021 | - | 0% | 0.32 | 0 | -100% | 38.16 | 0 | -100%
Abhishek Gupta [1%]Jalaj Mathur [1%]Sobhag Prajapat [1%]Tarun Gupta [1%] | Dec 15, 2021 | -
[154] End | Dec 15, 2021 | - | 0% | 0.16 | 0 | -100% | 2.72 | 0 | -100%
Abhishek Gupta [1%]Sobhag Prajapat [1%] | Dec 16, 2021 | -
ACTIVITY TYPE | PROJECT NAME | TASK NAME / ACTION ITEM | PROJECT MANAGER | OWNER | FROM | TO | ACTIVITY DESCRIPTION
Project activity | Charger Discharger CD1233 | Gravity measurement in software and testing | Abhishek Gupta | Sobhag Prajapat | Aug 24,2021 10:00:00 AM | Aug 24,2021 11:00:00 AM | project planing
Project activity | Charger Discharger CD1233 | requirment of resistive load , chassis and PCBs | Abhishek Gupta | Sobhag Prajapat | Aug 26,2021 09:00:00 AM | Aug 26,2021 09:30:00 AM | request for load and chassis given to sundeep sir0
Project activity | Charger Discharger CD1233 | art work development and mechanical developement | Abhishek Gupta | Sobhag Prajapat | Aug 26,2021 09:30:00 AM | Aug 26,2021 10:00:00 AM | Asthetic Details given to sundeep sir
Project activity | Charger Discharger CD1233 | Gravity measurement in software and testing | Abhishek Gupta | Abhishek Gupta | Aug 26,2021 09:30:00 AM | Aug 26,2021 01:10:00 PM | Some learnings implemented in the code that previously not implemented
Project activity | Charger Discharger CD1233 | Gravity measurement in software and testing | Abhishek Gupta | Abhishek Gupta | Aug 28,2021 12:00:00 PM | Aug 28,2021 05:40:00 PM | Main Software part for gravity measurement and verified from the tunning tool
Project activity | Charger Discharger CD1233 | Wifi develkopement | Abhishek Gupta | Abhishek Gupta | Sep 02,2021 02:05:00 PM | Sep 02,2021 04:35:00 PM | Data receiving and address varefication.
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Sobhag Prajapat | Sep 04,2021 04:00:00 PM | Sep 04,2021 05:00:00 PM | Wifi dashboard verify and handover to service team for varification
Project activity | Charger Discharger CD1233 | Wifi develkopement | Abhishek Gupta | Abhishek Gupta | Sep 04,2021 09:30:00 AM | Sep 04,2021 06:40:00 PM | Dashboard and data receiving from main MCU of all variables.
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Sobhag Prajapat | Sep 06,2021 02:00:00 PM | Sep 06,2021 04:30:00 PM | demo testing verification
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Abhishek Gupta | Sep 03,2021 12:00:00 PM | Sep 03,2021 05:25:00 PM | Wifi Data Captured and testing on the dashboard but report are not developed
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Abhishek Gupta | Sep 06,2021 01:50:00 AM | Sep 06,2021 06:00:00 PM | Testing of the Main firmware on tunning Tool and Wifi with sobhag Sir and alone
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Pawan Kumar Sharma | Sep 09,2021 02:00:00 PM | Sep 09,2021 05:30:00 PM | Harness assly
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Sep 09,2021 09:00:00 AM | Sep 09,2021 01:00:00 PM | worked on charger and discharger tuning tool
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Abhishek Gupta | Sep 10,2021 02:00:00 PM | Sep 10,2021 03:30:00 PM | Testing of the system of the fault occuring
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Sep 16,2021 11:00:00 AM | Sep 16,2021 12:10:00 PM | worked on three parameter values display on tuning tool
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Abhishek Gupta | Sep 18,2021 10:00:00 AM | Sep 18,2021 10:45:00 AM | Testing of the System and getting the issues resolved for data capturing in WiFi
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Sep 20,2021 05:00:00 PM | Sep 20,2021 05:30:00 PM | worked on evcharger tuning tool new parameter has been added final charged time
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Sobhag Prajapat | Sep 20,2021 10:00:00 AM | Sep 20,2021 11:30:00 AM | review of testing data
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Abhishek Gupta | Sep 22,2021 10:00:00 AM | Sep 22,2021 01:05:00 PM | There is some variables whose data is not coming so rectification of that fault
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Sep 29,2021 09:25:00 AM | Sep 29,2021 02:45:00 PM | Assembly 4 Nos and Power PCB Remaining
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Sep 29,2021 02:45:00 PM | Sep 29,2021 04:00:00 PM | harness Design
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Rohit Kumar Sachan | Oct 01,2021 09:20:00 AM | Oct 01,2021 12:00:00 PM | Wi-Fi normal Testing
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Oct 05,2021 11:00:00 AM | Oct 05,2021 05:00:00 PM | One System Assemble & Program
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Abhishek Gupta | Oct 04,2021 02:00:00 PM | Oct 04,2021 04:20:00 PM | WiFi Data analysis and resolution for the problem found in testing
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Oct 07,2021 02:00:00 PM | Oct 07,2021 06:00:00 PM | One System ON with old Firmware
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Sobhag Prajapat | Oct 07,2021 11:00:00 AM | Oct 07,2021 01:00:00 PM | wifi dash board discussion
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Oct 09,2021 09:15:00 AM | Oct 09,2021 05:50:00 PM | Testing [ Take Discharging Profile With New Load PCB (R= 1.7E Load)]
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Oct 11,2021 09:15:00 AM | Oct 11,2021 06:15:00 PM | testing of New Load PCB
Project activity | Charger Discharger CD1233 | wifi report developemnt | Abhishek Gupta | Abhishek Gupta | Oct 07,2021 11:35:00 AM | Oct 07,2021 01:30:00 PM | Discussion with yash sir on the excel file provided and also with sobhag sir to implement that
Project activity | Charger Discharger CD1233 | BOM First Draft developement | Abhishek Gupta | Rohit Kumar Sachan | Oct 12,2021 09:30:00 AM | Oct 12,2021 06:05:00 PM | Done
Project activity | Charger Discharger CD1233 | material received | Abhishek Gupta | Rohit Kumar Sachan | Oct 13,2021 02:00:00 PM | Oct 13,2021 04:30:00 PM | materials Received and Planning CD1233
Project activity | Charger Discharger CD1233 | BOM First Draft developement | Abhishek Gupta | Sobhag Prajapat | Oct 12,2021 02:00:00 PM | Oct 12,2021 04:00:00 PM | Bom development
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Ramashish Kumar | Oct 06,2021 09:35:00 AM | Oct 06,2021 04:00:00 PM | assemble sistam
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Oct 14,2021 09:20:00 AM | Oct 14,2021 02:00:00 PM | Assemble of system
Project activity | Charger Discharger CD1233 | assembly of 4 nos new system | Abhishek Gupta | Rohit Kumar Sachan | Oct 15,2021 09:40:00 AM | Oct 15,2021 02:00:00 PM | Done
Project activity | Charger Discharger CD1233 | Interfacing HTML /Dashboard with System with actual data and final review from customer | Abhishek Gupta | Abhishek Gupta | Oct 19,2021 11:00:00 AM | Oct 19,2021 01:00:00 PM | Webpage of from our side is placed in the code and start testing
Project activity | Charger Discharger CD1233 | Interfacing HTML /Dashboard with System with actual data and final review from customer | Abhishek Gupta | Abhishek Gupta | Oct 19,2021 02:00:00 PM | Oct 19,2021 06:00:00 PM | Working in main firmware and WiFi for final changes as per customer
Project activity | Charger Discharger CD1233 | Interfacing HTML /Dashboard with System with actual data and final review from customer | Abhishek Gupta | Sobhag Prajapat | Oct 22,2021 11:00:00 AM | Oct 22,2021 11:30:00 AM | Data analysis with team on running cycle on deep discharge battery 1. Charger need close charging profile at 260 Ah 2. Data not rest with front switch
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Rohit Kumar Sachan | Oct 26,2021 10:30:00 AM | Oct 26,2021 12:30:00 PM | Analysis Wi-Fi report and dashBoard
Project activity | Charger Discharger CD1233 | Interfacing HTML /Dashboard with System with actual data and final review from customer | Abhishek Gupta | Abhishek Gupta | Oct 26,2021 03:30:00 PM | Oct 26,2021 05:35:00 PM | Final data inserted with some observation resolved
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Oct 26,2021 04:00:00 PM | Oct 26,2021 05:00:00 PM | work on wifi android application
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Rohit Kumar Sachan | Oct 27,2021 05:20:00 PM | Oct 27,2021 06:05:00 PM | Analysis data and note down Points
Project activity | Charger Discharger CD1233 | Interfacing HTML /Dashboard with System with actual data and final review from customer | Abhishek Gupta | Sobhag Prajapat | Oct 27,2021 05:15:00 PM | Oct 27,2021 05:45:00 PM | Review of profile after software update date 26-11-21
Project activity | Charger Discharger CD1233 | Interfacing HTML /Dashboard with System with actual data and final review from customer | Abhishek Gupta | Sobhag Prajapat | Oct 26,2021 09:30:00 AM | Oct 26,2021 10:30:00 AM | Review and software work identify
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Oct 29,2021 03:00:00 PM | Oct 29,2021 03:15:00 PM | four parameter has changed in charger and discharger tuning tool. divide by 100 has also added in it.
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Abhishek Gupta | Oct 29,2021 02:00:00 PM | Oct 29,2021 06:00:00 PM | The cuff of volatges are not coming fr cycle 2 .solution for the same is done.
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Abhishek Gupta | Oct 28,2021 04:50:00 PM | Oct 28,2021 06:15:00 PM | Some problem was discussed and finding the solution for the same
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Oct 30,2021 03:30:00 PM | Oct 30,2021 04:30:00 PM | work on tuning tool and changes some address according to requirement
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Sobhag Prajapat | Nov 01,2021 02:15:00 PM | Nov 01,2021 02:45:00 PM | discusstion for solution of customer and service report generation
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Rohit Kumar Sachan | Nov 02,2021 09:00:00 AM | Nov 02,2021 11:30:00 AM | Analysis Wi-Fi report and dashBoard
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Rohit Kumar Sachan | Nov 09,2021 05:00:00 PM | Nov 09,2021 05:40:00 PM | main firmware and wifi firmware update in System & analysis wifi data
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Nov 10,2021 12:00:00 PM | Nov 10,2021 01:00:00 PM | worked on charger discharger tuning tool in this tool checked write button in debug window. write data will shows in hex format.
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Nov 10,2021 01:30:00 PM | Nov 10,2021 02:00:00 PM | write button shows data in hex format it should be in decimal form so that we can match dashboard data and write button data. But some issues are occurring.
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Rohit Kumar Sachan | Nov 10,2021 09:15:00 AM | Nov 10,2021 05:45:00 PM | Report Analysis and assemble two system ready
Project activity | Charger Discharger CD1233 | HTML Page/ dash board Finalization from Customer side | Abhishek Gupta | Abhishek Gupta | Nov 10,2021 03:00:00 PM | Nov 10,2021 05:00:00 PM | CD1233:-development of web page as provided by IT team
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Abhishek Gupta | Nov 10,2021 02:00:00 PM | Nov 10,2021 02:55:00 PM | CD1233:-Programming of 2 set and testing of cycle and ive training for auto cycle test frm TT.
Project activity | Charger Discharger CD1233 | HTML Page/ dash board Finalization from Customer side | Abhishek Gupta | Abhishek Gupta | Nov 02,2021 12:50:00 PM | Nov 02,2021 01:15:00 PM | Get the webpage from sudhir kulhadhi and also give them the response that the new page size is incresed by 10times
Project activity | Charger Discharger CD1233 | HTML Page/ dash board Finalization from Customer side | Abhishek Gupta | Abhishek Gupta | Nov 12,2021 09:20:00 AM | Nov 12,2021 09:30:00 AM | Get the webpage from sudhir kulhadhi and also give them the response that the new page size is incresed by 10times
Project activity | Charger Discharger CD1233 | BOM first draft upload in SAP | Abhishek Gupta | Rohit Kumar Sachan | Nov 13,2021 09:10:00 AM | Nov 13,2021 03:25:00 PM | Done
Project activity | Charger Discharger CD1233 | art work development and mechanical developement | Abhishek Gupta | Rohit Kumar Sachan | Nov 16,2021 02:00:00 PM | Nov 16,2021 05:50:00 PM | Art work 1. User manual 2. Top info Sticker
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Bharti Sharma | Nov 11,2021 09:00:00 AM | Nov 11,2021 11:00:00 AM | I have resolved some issues on charger discharger with wifi
Project activity | Charger Discharger CD1233 | art work development and mechanical developement | Abhishek Gupta | Rohit Kumar Sachan | Nov 17,2021 03:00:00 PM | Nov 17,2021 04:15:00 PM | Packing Box HW_2682 & EP foam HW_2681
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Abhishek Gupta | Nov 17,2021 10:00:00 AM | Nov 17,2021 01:00:00 PM | Customer mode and service mode development in firmware side
Project activity | Charger Discharger CD1233 | Design Review Hardware ,Software And testing Data | Abhishek Gupta | Abhishek Gupta | Nov 18,2021 04:10:00 PM | Nov 18,2021 04:20:00 PM | This will be postponed because of new mode introduction to development
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Abhishek Gupta | Nov 18,2021 10:00:00 AM | Nov 18,2021 01:05:00 PM | New modes development in the system i.e. customer and service mode
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Abhishek Gupta | Nov 23,2021 09:40:00 AM | Nov 23,2021 11:55:00 AM | Analysis of customer mode and service mode and decision on the data issues
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Rohit Kumar Sachan | Nov 25,2021 09:15:00 AM | Nov 25,2021 11:20:00 AM | Analysis Wi-fi data with implemented Switch
Project activity | Charger Discharger CD1233 | testing of complete system with wifi And All Supporting Documents developement | Abhishek Gupta | Rohit Kumar Sachan | Nov 25,2021 06:20:00 PM | Nov 25,2021 06:45:00 PM | Two system Set-up for futher Wi-Fi Testing
Project activity | Charger Discharger CD1233 | WiFi report development and WiFi report testing | Abhishek Gupta | Abhishek Gupta | Nov 29,2021 10:45:00 AM | Nov 29,2021 12:05:00 PM | Report study and finding of some issues in the data.

## BMS 50A
TASK NAME / ACTION ITEM | PROJECT MANAGER | OWNER | FROM | TO | ACTIVITY DESCRIPTION
Port the code from stm3f0 to stm32g0. | Raghvendra Thakur | Raghvendra Thakur | Aug 09,2021 09:30:00 AM | Aug 09,2021 01:10:00 PM | port the code from stm32f0 to stm32g0
Port the code from stm3f0 to stm32g0. | Raghvendra Thakur | Raghvendra Thakur | Aug 09,2021 01:45:00 PM | Aug 09,2021 05:40:00 PM | port the code from stm32f0 to stm32g0
Port the code from stm3f0 to stm32g0. | Raghvendra Thakur | Raghvendra Thakur | Aug 10,2021 10:00:00 AM | Aug 10,2021 01:30:00 PM | port the code from stm32f0 to stm32g0
Port the code from stm3f0 to stm32g0. | Raghvendra Thakur | Raghvendra Thakur | Aug 10,2021 02:00:00 PM | Aug 10,2021 06:00:00 PM | port the code from stm32f0 to stm32g0
PCB Designing and delivery | Raghvendra Thakur | Sobhag Prajapat | Aug 03,2021 09:00:00 AM | Aug 03,2021 12:00:00 PM | Schemetic and PCB design
PCB Designing and delivery | Raghvendra Thakur | Sobhag Prajapat | Aug 04,2021 09:00:00 AM | Aug 04,2021 12:00:00 PM | Schemetic and PCB design
PCB Designing and delivery | Raghvendra Thakur | Sobhag Prajapat | Aug 05,2021 09:00:00 AM | Aug 05,2021 12:00:00 PM | Schemetic and PCB design
PCB Designing and delivery | Raghvendra Thakur | Sobhag Prajapat | Aug 07,2021 09:00:00 AM | Aug 07,2021 10:00:00 AM | Schemetic and PCB design
PCB Designing and delivery | Raghvendra Thakur | Sobhag Prajapat | Aug 08,2021 09:00:00 AM | Aug 08,2021 10:00:00 AM | Schemetic and PCB design
PCB Designing and delivery | Raghvendra Thakur | Sobhag Prajapat | Aug 19,2021 09:00:00 AM | Aug 19,2021 09:30:00 AM | PCB design complete
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Sobhag Prajapat | Aug 27,2021 09:00:00 AM | Aug 27,2021 12:00:00 PM | Legend entry done for DC-DC and Power Path
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Sobhag Prajapat | Aug 27,2021 02:00:00 PM | Aug 27,2021 05:00:00 PM | Legend entry done for DC-DC and Power Path
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Raghvendra Thakur | Aug 27,2021 09:00:00 AM | Aug 27,2021 01:00:00 PM | Arrange components and legend entry
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Raghvendra Thakur | Aug 27,2021 02:00:00 PM | Aug 27,2021 05:30:00 PM | Test the power suplly module
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Pawan Kumar Sharma | Aug 27,2021 11:00:00 AM | Aug 27,2021 01:00:00 PM | Assembly of PCB
PCB Designing and delivery | Raghvendra Thakur | Sobhag Prajapat | Aug 27,2021 05:00:00 PM | Aug 27,2021 06:00:00 PM | designing completed
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Sobhag Prajapat | Aug 28,2021 09:00:00 AM | Aug 28,2021 03:00:00 PM | maxIC and ST controller
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Pawan Kumar Sharma | Aug 28,2021 09:30:00 AM | Aug 28,2021 01:00:00 PM | PCB ASSEMBLE PCB NO-1070 REV-1.1
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Pawan Kumar Sharma | Aug 28,2021 02:00:00 PM | Aug 28,2021 06:00:00 PM | PCB ASSEMBLE ING NO-1070 RE-1.1
Legend Enetry and PCB Assembling and module testing. | Raghvendra Thakur | Pawan Kumar Sharma | Aug 30,2021 10:00:00 AM | Aug 30,2021 01:00:00 PM | PCB ASSEMBLING 1070_ REV_1.1
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Aug 30,2021 10:50:00 AM | Aug 30,2021 11:35:00 AM | BOM Preperation
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Aug 30,2021 05:35:00 PM | Aug 30,2021 06:00:00 PM | BOM Preperation
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Aug 31,2021 10:25:00 AM | Aug 31,2021 01:20:00 PM | Testing of 48V/50A BMS. Fault detection and its correction during programming of the Microcontroller.
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Aug 31,2021 02:20:00 PM | Aug 31,2021 04:25:00 PM | Testing with new PCB
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Aug 31,2021 04:30:00 PM | Aug 31,2021 05:25:00 PM | BOM preperation of new PCB
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Aug 31,2021 10:00:00 AM | Aug 31,2021 01:00:00 PM | test with new PCB programming is OK there was some fault in PCB, it was review fault.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Aug 31,2021 02:00:00 PM | Aug 31,2021 05:30:00 PM | test with new PCB programming is OK there was some fault in PCB, it was review fault.
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Sep 14,2021 10:00:00 AM | Sep 14,2021 10:15:00 AM | made set-up for 48V BMS
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 14,2021 10:00:00 AM | Sep 14,2021 01:00:00 PM | Resolve the issue by firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 14,2021 02:00:00 PM | Sep 14,2021 06:00:00 PM | Resolve the issue by firmware
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 16,2021 09:00:00 AM | Sep 16,2021 11:00:00 AM | worked on layout design of BMS tuning tool
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 17,2021 09:00:00 AM | Sep 17,2021 01:00:00 PM | tuning tool design for bms
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 23,2021 04:00:00 PM | Sep 23,2021 05:30:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 24,2021 11:00:00 AM | Sep 24,2021 01:00:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 24,2021 01:30:00 PM | Sep 24,2021 05:30:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 25,2021 11:00:00 AM | Sep 25,2021 01:00:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 25,2021 01:30:00 PM | Sep 25,2021 05:30:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 27,2021 09:00:00 AM | Sep 27,2021 11:00:00 AM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 27,2021 03:00:00 PM | Sep 27,2021 05:30:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 28,2021 11:00:00 AM | Sep 28,2021 01:00:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Sep 28,2021 01:30:00 PM | Sep 28,2021 05:30:00 PM | work on BMS tuning tool two buttons added in this tool for display data on click on these buttons
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 15,2021 10:00:00 AM | Sep 15,2021 01:00:00 PM | Resolve issue by firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 15,2021 02:00:00 PM | Sep 15,2021 06:00:00 PM | Resolve issue by firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 16,2021 10:00:00 AM | Sep 16,2021 01:00:00 PM | test the pcb and firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 16,2021 02:00:00 PM | Sep 16,2021 06:00:00 PM | test the pcb and firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 17,2021 10:00:00 AM | Sep 17,2021 01:00:00 PM | test the pcb and firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 17,2021 02:00:00 PM | Sep 17,2021 06:00:00 PM | test the pcb and firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 18,2021 09:30:00 AM | Sep 18,2021 01:00:00 PM | test the pcb and firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 18,2021 02:30:00 PM | Sep 18,2021 05:00:00 PM | test the pcb and firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 22,2021 10:00:00 AM | Sep 22,2021 01:00:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 22,2021 02:00:00 PM | Sep 22,2021 05:30:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 23,2021 10:00:00 AM | Sep 23,2021 01:30:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 23,2021 02:00:00 PM | Sep 23,2021 05:30:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 25,2021 10:00:00 AM | Sep 25,2021 01:00:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 25,2021 02:00:00 PM | Sep 25,2021 05:30:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 27,2021 09:30:00 AM | Sep 27,2021 01:00:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 27,2021 02:30:00 PM | Sep 27,2021 05:40:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 28,2021 09:45:00 AM | Sep 28,2021 01:05:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 28,2021 02:05:00 PM | Sep 28,2021 05:45:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 29,2021 09:40:00 AM | Sep 29,2021 01:00:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 29,2021 02:15:00 PM | Sep 29,2021 06:00:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 30,2021 09:50:00 AM | Sep 30,2021 01:00:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Sep 30,2021 02:05:00 PM | Sep 30,2021 05:45:00 PM | As per new need from customer side do the work in firmware
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 18,2021 10:30:00 AM | Oct 18,2021 01:00:00 PM | Firware work Pending: a global variable save in the flash . But when any decision is taking it is not working. solving that issue.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 18,2021 02:00:00 PM | Oct 18,2021 05:00:00 PM | Firware work Pending: a global variable save in the flash . But when any decision is taking it is not working. solving that issue.
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Oct 14,2021 01:30:00 PM | Oct 14,2021 02:30:00 PM | work on tuning tool
Port the code from stm3f0 to stm32g0. | Raghvendra Thakur | Raghvendra Thakur | Oct 20,2021 04:00:00 PM | Oct 20,2021 04:05:00 PM | test demo
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 21,2021 11:00:00 AM | Oct 21,2021 01:00:00 PM | 21_10_21: Soving the problem auto set the under voltage and over voltage by user.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 21,2021 02:00:00 PM | Oct 21,2021 05:35:00 PM | 21_10_21: Soving the problem auto set the under voltage and over voltage by user.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 22,2021 10:00:00 AM | Oct 22,2021 01:00:00 PM | 22-10-21:As per new need from customer side do the work in firmware . they want user setable UV and OV.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 22,2021 02:00:00 PM | Oct 22,2021 06:30:00 PM | 22-10-21:As per new need from customer side do the work in firmware . they want user setable UV and OV.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 23,2021 10:00:00 AM | Oct 23,2021 01:00:00 PM | 23-10-21: solve the problem user setable UV .
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 23,2021 02:00:00 PM | Oct 23,2021 05:00:00 PM | 23-10-21: problem solved now add other user setable other parameters.e
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 26,2021 11:45:00 AM | Oct 26,2021 01:00:00 PM | 25-10-21: Add othe tunable parameters
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 26,2021 02:00:00 PM | Oct 26,2021 05:30:00 PM | 25-10-21: Add othe tunable parameters
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Oct 25,2021 11:00:00 AM | Oct 25,2021 01:00:00 PM | worked on BMS tuning tool. Some new parameter has added in this tool.
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Oct 26,2021 01:30:00 PM | Oct 26,2021 04:00:00 PM | work on BMS tuning tool and resolve some issues and new address has been added
Testing With new PCB | Raghvendra Thakur | Bharti Sharma | Oct 27,2021 09:00:00 AM | Oct 27,2021 11:00:00 AM | work on BMS tuning tool ,In this tool some correctio has done and layout has prepared
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 27,2021 10:00:00 AM | Oct 27,2021 01:00:00 PM | 27-10-21: Complete the tunning tool work, and adjust the other parameters and remove some bugs.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 27,2021 02:00:00 PM | Oct 27,2021 05:30:00 PM | 27-10-21: Complete the tunning tool work, and adjust the other parameters and remove some bugs.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 28,2021 10:30:00 AM | Oct 28,2021 01:00:00 PM | 28-10-21: Work on short circuit.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 28,2021 02:25:00 PM | Oct 28,2021 05:30:00 PM | 28-10-21: Work on short circuit.
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 29,2021 11:00:00 AM | Oct 29,2021 01:30:00 PM | 29-10-21: Worked on short circuit protection
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Oct 29,2021 02:00:00 PM | Oct 29,2021 05:30:00 PM | 29-10-21: Worked on LED indication
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Nov 02,2021 10:50:00 AM | Nov 02,2021 11:45:00 AM | Testing set up
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Nov 02,2021 11:50:00 AM | Nov 02,2021 01:00:00 PM | Testing
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Nov 02,2021 02:00:00 PM | Nov 02,2021 04:25:00 PM | Testing
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Nov 09,2021 11:00:00 AM | Nov 09,2021 01:00:00 PM | Testing
Testing With new PCB | Raghvendra Thakur | Abhishek Kumar | Nov 09,2021 02:00:00 PM | Nov 09,2021 06:00:00 PM | Testing
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Nov 10,2021 10:00:00 AM | Nov 10,2021 01:00:00 PM | 10-11-21: Resolve the problem like cell balancing, auto tunning
Testing With new PCB | Raghvendra Thakur | Raghvendra Thakur | Nov 10,2021 02:00:00 PM | Nov 10,2021 06:00:00 PM | 10-11-21: Resolve the problem like cell balancing, auto tunning