## PLAN
PLAN
Level | Practice | Title | Source Reference | Link | Description | Type(Doc/ Aff) | S/W/I Description | S/W/I | Verified- Y/N | GGE200 |  |  | CHAR - GGE200-FI/LI
Level 1 | 1.1 | Develop a list of tasks. | OK | GGE302_PLAN | WBS of project consists of every tasks list | Doc | S:MPP contains top-level work breakdown structure (WBS) | S | Y |  | X | X | FM
|  |  | - |  | PM affiremd that MPP contain the list of task which has to be performed during project | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 1.2 | Assign people to tasks. | OK | GGE302_PLAN | WBS of project consists of resource plan against each task | Doc | s:Roles and responsibility section in project planning indicates the roles and responsibility of all the stakeholders | s | Y |  | X | X | FM
|  |  | OK | GGE302_MINMET | In pre planning meeting discussed the roles, and in deploy the plan meeting task conveyed. | Doc | S: In Resource Column of MPP stakeholder name against each task has been mentioned | S | Y |  | X | X
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 2 | 2.1 | Develop and keep updated the approach for accomplishing the work. | OK | GGE302_PLAN | WBS of project consists of every tasks list and it is updated on regular basis. It can be tracked through Publish log history. | Doc | s: Task in MPP have been scheduled as per project life cycle | s | Y |  | X | X | FM
|  |  | OK | GGE302_PLAN |  | Doc | s:updated project plan is available on share point | s | Y |  | X | X
|  |  | - |  | PM affirmed that they update the MPP after completion of each task | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.2 | Plan for the knowledge and skills needed to perform the work. | OK | GGE302_PLAN | Training plan section consists of required and available work experience to complete the tasks. | Doc | s: In the section of training plan of project planning, skill/experience section showing total experience of the team & project Manager. | s | Y |  | X | X | FM
|  |  | OK | GGE302_PLAN | Talent needs and gaps of project plan identified the need of training / skills. | Doc | i:training specific to the role should be given | i | Y |  | X | X
|  |  | - |  | PM affirmed that training on SMF battery has been identified in the project to meet project schedule | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.3 | Based on recorded estimates, develop and keep updated the budget and schedule. | OK | GGE302_PLAN | Budget section of project plan | Doc | s: In section of Budget Requirements: Budget planning for additional NRE has been done | s | Y |  | X | X | FM
|  |  | OK | GGE302_PLAN | WBS of project consists of every tasks list and it is updated on regular basis. It can be tracked through Publish log history. | Doc | s: In MPP schedule is updated on the bases of project progress | s | Y |  | X | X
|  |  | - |  | PM affirmed that additional NRE buget taken for SMF battery purchase and MPP updated after completion of every task | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.4 | Plan the involvement of identified stakeholders. | OK | GGE302_PLAN | Schedule of project consists of resource plan against each task | Doc | S: In Resource Column of MPP stakeholder name against each task has been mentioned | S | Y |  | X | X | FM
|  |  | OK | GGE302_PLAN | Project team identified with roles and responsibility defined in project tasks itself to involve the stakeholders. | Doc | s:Roles and responsibility section in project planning indicates the roles and responsibility of all the stakeholders | s | Y |  | X | X
|  |  | - |  | PM affirmed that in plan document all Stakeholders are identified to perform project activites | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.5 | Plan transition to operations and support. | OK | GGE302_PLAN | CM plan tells about mode of release and documents to be released for the project | Doc | s: In the section of Configuration & Data Management Plan, list of documents are mentioned which are to be released for supporting production | s | Y |  | X | X | FM
|  |  | OK | GGE302_PLAN | In Plan tasks identified to make user support documents. | Doc | s: task and schedule mentioned in the mpp | s | Y |  | X | X
|  |  | - |  | PM affirmed that document which are required for production has been mentioned in the clouser report and they have received the pilot report from production. | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.6 | Ensure plans are feasible by reconciling available and estimated resources. | OK | GGE302_MINMET | In pre planning meeting discussed the roles to involve the stackholders. | Doc | s: Minutes of Meeting depicts the involvement of stakeholder during planning | s | Y |  | X | X | FM
|  |  | OK | GGE302_MINMET | Meeting with team to deploy and discuss the finalized the plan. | Doc | s: E mail sent to senior management for plan approval and e mail sent to stakeholder for approval information | s | Y |  | X | X
|  |  | - |  | PM affirmed that SM approve the plan and MPP has been updated as per change in the schedule due to delay |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.7 | Develop the project plan, ensure consistency among its elements, and keep it updated. | OK | GGE302_PLAN | Project plan updated through out the project lifecycle whenever needed, and can be checked in publish log. | Doc | s:project plan has been updated during project lifecycle and revision history is available on SharePoint | s | Y |  | X | X | FM
|  |  | - |  | PM affirmed that Budget, schedule, risk, resources, skills ect has been done and updated during project lifecycle | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.8 | Review plans and obtain commitments from affected stakeholders. | - |  |  |  |  | -
|  |  | OK | GGE302_MINMET | Stakeholders affirmation on planned schedule, resources etc. | Doc | s: Approved project planning at share point showing the commitment of team and get the approval from senior management Stakeholder send the affirmation through email | s | Y |  | X | X | FM
|  |  | - |  | PM affirmed that SM has approved the project plan and remark of SM has been caputured in MOM. Approved planned share to all stakeholder | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 3 | 3.1 | Use the organization’s set of standard processes and tailoring guidelines to develop, keep updated, and follow the project process. | OK | GGE302_PLAN | Project life cycle showing project flow, as provided by organization. |  |  | - |  |  | X | X
|  |  | - |  |  | Doc | s: Complete life cycle has been used in GGE200 project | s | Y |  |  |  | FM
|  |  | - |  |  | Doc | s: planning template used which provided by org. | s | Y
|  |  | - |  |  | Doc | s: Estimation template used which provided by org. | s | Y
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.2 | Develop a plan and keep it updated, using the project process, the organization’s process assets, and the measurement repository. | OK | GGE302_take reference from GGE295 estimation repository | Take estimation hardware, reference to establish estimation of project GGE302 and accordingly develop plan. | Doc | s: For project related activies different template used which provided by org. | s | Y |  | X | X | FM
|  |  | OK | GGE302_PLAN |  | Doc |  | - | Y |  | X | X
|  |  | - |  | PM affirmed that they have used template available on QMS3.1and also refer guidelines provided by org. PM also affirmed that they have taken ref from old project to do estimation | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.3 | Identify and negotiate critical dependencies. | OK | GGE302_PLAN | Critical resources CREO tool, SMF Batteries etc in Asset section (resource plan) | Doc | s: Training related dependecies identified in risk matrix | s | Y |  | X | X | FM
|  |  | OK | GGE302_RSKMTX | Critical dependecies mentioned in risk matrix. | Doc | s:All Stake Holder Activity in mpp | s | Y |  | X | X
|  |  | - |  |  | Doc |  | - | Y
|  |  | - |  | PM affirmed that critical dependencies are identified in MPP and in review meeting with SM they have identified training as a risk | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.4 | Plan for the project environment and keep it updated based on the organization’s standards. | OK | GGE302_PLAN | Asset and knowledge section. | Doc | s: no additional requirement mentioned in work environment section of project plan | s | Y |  | X | X | FM
|  |  | OK | GGE302_PLAN | Project resources constitute project work environment. | Doc | s:Resources required for the project identified in the project plan. The resources include Human resources, Machine, Material resources. | s | Y |  | X | X
|  |  | - |  | PM affirmed that in resources section of project plan that they identified the resources and tools required for the project. | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
** Minimum 2 and maximum 3 evidences require for each practice