## Revision History
Genus Innovation Limited
Template Version - 1

## Review Agenda List
Senior Managment Review Agenda list for PEG Group
Date: | 2022-09-09
S. No | Checkpoint | Yes/No | Comments/ Findings
1 | Is there any change or deviation in Organizational goals? | Yes | After seen trend of Line rejection raito percentage for last 6 months, the goal revised to 2.5 instead of 0, to make more releastic. This was also feedback of IR
2 | Is there any issue regarding Stakeholder involvement? | Yes | 2 Project managers need to more align, as recenlty they started or very soon will start the projects.
3 | Is the budget and resources provided are enough for our needs? | Yes
4 | Are all activities inline with defined schedules? | No | IR-1 done and its look no need of further IR
5 | Are the Organization's processes are being appraised timely according to our needs? | Yes | IR-1 done by KPMG, its include gap analysis also. Other than this time to time Project informal review in processes context doing by PEG & PQA
6 | Are the metrics defined needs to be relooked? | No | Only goal revised.
7 | Is there any risk identified at Organizational level? If yes then what can we do to mitigate? | Yes | As CMMI apraisal due in this Nov.22, we need to more align with processes.
8 | Are there any process pilots being run? | No | -