## EST
EST
Level | Practice | Title | Source Reference | Link | Description | Type(Doc/ Aff) | S/W/I Description | S/W/I | Verified- Y/N | GGE200 |  |  | CHAR - GGE200-FI/LI
Level 1 | 1.1 | Develop high-level estimates to perform the work. | - |  |  |  |  | -
|  |  | OK | GGE302_MINMET | high level estimating done at initial phase in MOM ( | Doc | I: High level estimates should be maintained in the plan so that the accuracy of those can also be determined for future projects. | I | Y |  | X | X | FM
|  |  | OK | GGE302_ESTFNL | Final estimation sheet for efforts planning of whole project lifecycle. | Doc |  | - | Y |  | X | X
|  |  | - |  |  | Aff | I: The understanding behind formulas of automatic tools should be strengthened. | I | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 2 | 2.1 | Develop, keep updated, and use the scope of what is being estimated. | OK | GGE302_FUNSPC | FS details about need against which work is done. | Doc | S:estimation has been done against each need | S | Y |  | X | X | FM
|  |  | OK | GGE302_ESTFNL | Estimation accordinng to needs and final outcome per phase | Doc |  | - | Y |  | X | X
|  |  | - |  |  | Doc |  | - | Y
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.2 | Develop and keep updated estimates for the size of the solution. | OK | GGE302_ESTFNL | Used pre determined parameters and the resulting score to categorise the requirement in terms of size complexity. | Doc | I: Widebend delphi used but the assumptions have not been updated between estimation rounds indicating adhoc estimation. | I | Y |  | X | X | FM
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.3 | Based on size estimates, develop and record effort, duration, and cost estimates and their rationale for the solution. | OK | GGE302_ESTFNL | Reference projects actual efforts and as per size complexity of differences, efforts estimated. | Doc | S: | S | Y |  | X | X | FM
|  |  | OK | https://gil.einframe.com/data-capture/development/capprojecttasks.aspx?projectid=96 | Project Plan | Doc |  | - | Y |  | X | X
|  |  | - |  |  | Doc |  | - | Y
|  |  | - |  |  | Doc |  | - | Y
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 3 | 3.1 | Develop and keep updated a recorded estimation method. | OK | GGE302_ESTFNL | Estimation guidelines and previous similar reference project data used in the project. | Doc | W: Estimation guidelines are high level and do not provide the rationale for specific scores for complexity estimations. | W | Y |  | X | X | LM
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.2 | Use the organizational measurement repository and process assets for estimating work. | OK | GGE302_ESTFNL | Estimation guidelines and previous similar reference project (GGE295) data used in the project. | Doc | S: | S | Y |  | X | X | FM
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | S
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
** Minimum 2 and maximum 3 evidences require for each practice