## MC
MC
Level | Practice | Title | Source Reference | Link | Description | Type(Doc/ Aff) | S/W/I Description | S/W/I | Verified- Y/N | GGE200 |  |  | CHAR - GGE200-FI/LI
Level 1 | 1.1 | Record task completions. | OK | GGE302_Task Approval | Tasks approved after completion | Doc | s:MPP with actual dates of activities to monitor progress against schedule | s | Y |  | X | X | FM
|  |  | - |  | PM affirmed mpp updated after completion of task | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 1.2 | Identify and resolve issues. | OK | GGE302_MESRPT | project metrics report provide variances in measurement, their causal analysis and correction actions. | Doc | i: Issue with are identified in project should be mentioned in issue log with resolution | i | Y |  | X | X | FM
|  |  | - |  |  | Doc | s: Team meeting during the projects showing action has been taken against decision | s | Y
|  |  | - |  |  | Aff | s:Document received against affirmation | s | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 2 | 2.1 | Track actual results against estimates for size, effort, schedule, resources, knowledge and skills, and budget. | OK | GGE302_Plan | Project Plan according to effort estimation | Doc | s: | s | Y |  | X | X | FM
|  |  | OK | https://gil.einframe.com/data-capture/development/capprojecttalentmap.aspx?projectid=96 | Resource ,Knowledge and Skills | Doc | s:MPP with actual dates of activities to monitor progress against schedule | s | Y |  | X | X
|  |  | OK | FINANCIALS | Budget Deatails | Doc | s:Milestone review with senior management at the end of each phase | s | Y |  | X | X
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.2 | Track the involvement of identified stakeholders and commitments. | - | Team | Project team in Project plan | Doc | I: Action items are not consolidated at one place and tracked | I | Y |  | X | X | FM
|  |  | OK | Time Sheet | timesheet los for GGE302 | Doc | s:Monitor stakeholder involvement through Time sheet | s | Y |  | X | X
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.3 | Monitor the transition to operations and support. | - |  |  |  |  | -
|  |  | OK | GGE302_Design Data | SVN repository for project | Doc | s:Applicable design output with release items | s | Y |  | X | X | FM
|  |  | OK | http://192.168.100.9:8080/svn/DC_DC_Converter/SP10_GGE302/Testing/ | SVN repository for project | Doc | s:rivision history mentioned | s | Y |  | X | X
|  |  | - |  |  | Doc | s: Feedback from production has been mentioned in the pilot report | s | Y
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.4 | Take corrective actions when actual results differ significantly from planned results and manage to closure. | OK | GGE302_MESRPT | project metrics report provide every measurement data related to project | Doc | s: | s | Y |  | X | X | FM
|  |  | OK | GGE302_MINMET | any discrepancy/problem/issue is mentioned in MOM | Doc |  | - | Y |  | X | X
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 3 | 3.1 | Manage the project using the project plan and the project process. | OK | GGE302_Plan | project plan | Doc | s:MPP with actual dates of activities to monitor progress against schedule | s | Y |  | X | X | FM
|  |  | OK | GGE302_MINMET | continuous monitoring of project through status meetings | Doc | s: Team meeting during the projects showing project plan has been monitored | s | Y |  | X | X
|  |  | - |  | PM affirmed that plan is monitored using MPP and team meeting | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.2 | Manage critical dependencies and activities. | OK | GGE302_MINMET | Status review meetings have details about each activity and roadblocks | Doc | s: Team meeting during the projects showing that dependencies are reviewed and updated | s | Y |  | X | X | FM
|  |  | OK | GGE302_RSKMTX | risk matrix for detail | Doc | s: in risk matrix ,risk has been identified and plan for mitigation and contingency is mentioned | s | Y |  | X | X
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.3 | Monitor the work environment to identify issues. | OK | GGE302_MINMET | Status review meetings have details about each activity and roadblocks if any, critical dependency. (C69), eg. SMF battery procurement | Doc | s: Team meeting during the projects showing activities monitor during the meeting | s | Y |  | X | X | FM
|  |  | - |  |  | Aff |  | - | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.4 | Manage and resolve issues with affected stakeholders. | OK | GGE302_MESRPT | project metrics report provide every measurement data related to project an their causal analysis for the issues faced, | Doc | s:Metrics report where analysis the measurement with corrective action | s | Y |  | X | X | LM
|  |  | OK | GGE302_MINMET | any discrepancy/problem/issue is mentioned in MOM (C-100) | Doc | s: Team meeting during the projects showing action against the decision taken in previous meeting | s | Y |  | X | X
|  |  | - |  |  | Aff | W: The actions to resolve identified issues are not explicit. | W | Y
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | S
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
** Minimum 2 and maximum 3 evidences require for each practice