## Introduction
Genus Innovation Limited
Audit Reporting Tool
Template version 1

## Audit Data
Id | Identification Date | Area | Description | Reproduction Steps | Configuration Info | Logged On | Resolved On | Ageing | Status | Type | Assignor | Assignee | Report Type | Product KPI Affected | Source | Task Category | Found In | Fixed In | Classification | Resolution Type | Effort Spent | Material Cost | Schedule Impact
63 | Aug 04, 2022 | Review | Plan review checklist is not found on defined path | open project data link- no plan review checklist is found. | SVN server/GGS151 | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-08-05 - http://10.141.1.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | 2022-08-05 - GGS151_PLNREV at http://10.141.1.9:8080/svn/Solar_MPPT_inv/GGS151_3KW | Non Functional | Fixed | 0 | 0 | 0
64 | Aug 04, 2022 | MINMET | MOM_preliminary efforts are not discussed in meeting, decision/action items not mentioned in last MOM, few grammatical errors | MIMMET, last MOM decision/action items column | MINMET | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Modified Implementation | Project Management | 2022-08-05 - SVN Log History (Found in revision wrong fill)2022-08-05 - GGS151_MINMET Revision 17 | 2022-08-05 - Found In :GGS151_MINMET Revision 162022-08-05 - GGS151_MINMET Revision 18 | Non Functional | Fixed | 0 | 0 | 0
65 | Aug 04, 2022 | Review | FS baselined not communicated, RTT review not done | Finalized FS communication missing, RTT review is not seen | RTT review | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Regression in untouched module | Project Management | 2022-08-05 - Incident Management log | 2022-08-05 - Incident Management log in further | Non Functional | Will Fix in Future | 0 | 0 | 0
66 | Aug 04, 2022 | Project plan | No action against asset requirement could seen | asset/ Microsoft office/no action plan | asset plan in project plan | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | 3rd Party Component | Project Management | 2022-08-05 - Asset plan of GGS151 | 2022-08-05 - Mail to Concern department | Non Functional | Fixed | 0 | 0 | 0
67 | Aug 04, 2022 | Review | review artefact could not recognised | incident management/review log/artefact under review could not identify | review incident management | Aug 04, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | Regression in untouched module | Project Management | 2022-08-05 - Incident Log in Ein frame | 2022-08-05 - Incident Log in Ein frame further | Observation | Will Fix in Future | 0 | 0 | 0
69 | Aug 04, 2022 | Project plan | Project measurement BOM cost is not taken in tasks | project task- no task related to BOM cost | project tasks | Aug 05, 2022 | Aug 05, 2022 | - | Closed | Project RelatedGGS151 | Shweta Aggarwal | Chandrashekhar Sharma | BUG | Reliability | New Implementation | Project Management | 2022-08-05 - GGS151Plan_ Aug 03, 2022 11:09:10 (UTC) | 2022-08-05 - GGS151Plan_Aug 05, 2022 05:59:27 (UTC) | Non Functional | Fixed | 0 | 0 | 0

## Analysis
Count of Area | Column Labels
Row Labels | Non Functional | Observation | (blank) | Grand Total
MINMET | 1 |  |  | 1
Project plan | 2 |  |  | 2
Review | 2 | 1 |  | 3
(blank)
Grand Total | 5 | 1 |  | 6
Analysis
NCs are found majorly in Team meetings, plan documents and function specifications (as shown in above graph)
Area | Problem | Elaboration |  |  | Impacts | Suggestions