## onsite and team trainin
| Date | Time |  |  |  |  | ATM name
ATM training |  | 09:00 AM to 07:00 PM
ARR |  | 09:00 AM to 07:00 PM
Date | Time | Event | Participant | Actual Attendee | Session | Role | Participant Names | KPMG SPOC | Meeting location | Practice Area
1st Nov 22 | 10:00 AM-10:30 AM | Opening meeting | ATMs and LA |  |  |  | Sponser : Mr. S.N. Vijayvergia and all team. | LA | GIL R&D Conference Room
| 10:30 AM to 07:00 PM | PIID validation | ATMs and LA |  |  |  |  | LA | GIL R&D Conference Room
2nd Nov 22 | 10:30 AM -12:30 PM | SEPG+SQA | ATM,SEPG and SQA |  |  | PEG & PQA Interview | Jalaj & Shweta | LA | GIL R&D Conference Room | PAD,MPM PCM, PQA, II and GOV
| 2:30 PM to 03:00 PM | Training (OT) | LA, ATM |  |  | Training Coordinator Interview | Girija | LA | GIL R&D Conference Room | OT, II and GOV
| 03:30 PM to 04.15 PM | GNE114 Heiwa 4200 48V | LA, ATM |  |  | Project Interview | Chandrashekhar | LA | GIL R&D Conference Room | CAR, CM, DAR, GOV, II
| 04.15 PM to 07:00 PM | tagging and review and consolidation | ATM, LA |  |  |  |  | LA | GIL R&D Conference Room
3rd Nov 22 | 10:45 AM - 12:00 Noon | GGE302 DC DC Syncronous Auto Grade | LA, ATM |  |  | Project Interview | Sobhag | LA | GIL R&D Conference Room | EST, MC, PLAN , GOV, II
| 12:15 PM to 1.00 PM | Senior Management | LA, ATM |  |  | Senior Management Interview | Tarun | LA | GIL R&D Conference Room | GOV, II
| 03:00 PM to 04:00 PM | OBH012 Combo-Z 3200 48V | LA, ATM |  |  | Project Interview | Syoji | LA | GIL R&D Conference Room | PR, RDM, VV, GOV, II
| 4.15 PM to 4.45 PM | GGE300 BMS 20S 40A NMC | ATM,PM, |  | Project | Project Interview | Syoji | LA | GIL R&D Conference Room | RSK , GOV, II
| 04:45 PM to 07:00 PM | tagging, review and consolidation | ATM |  |  |  |  | LA | GIL R&D Conference Room
4th Nov 22 | 10:00 AM -11:00 AM | GGE295 DC-DC 12V 10A & 5V-1A | ATM,PM, |  | Project | Project Interview | Sobhag | LA | GIL R&D Conference Room | PI, TS, GOV, II
| 11:00 Noon to 012:00 Noon | tagging and consolidation | LA, ATMS |  |  |  |  | LA | GIL R&D Conference Room
| 02:00 PM to 04:00 PM | tagging and consolidation | LA, ATMS |  |  |  |  | LA | GIL R&D Conference Room
| 04:00 PM to 07:00 PM | preparation of draft findings and review | LA, ATMS |  |  |  |  | LA | GIL R&D Conference Room
5th Nov. 22 | 10:00 AM - 11:00 AM | draft findings review | LA, ATMs |  |  |  |  | LA | GIL R&D Conference Room
| 11:30 to 12:30 | Draft finding Dev | LA |  |  |  |  | LA | GIL R&D Conference Room
| 12:30 to 01:30 | Draft finding SVC | LA |  |  |  |  | LA | GIL R&D Conference Room
| 02:00 PM to 04:00 PM | follow up interview, if any | LA, ATM |  |  |  |  | LA | GIL R&D Conference Room
| 04:00 PM to 07:00 PM | OU characterization and review | LA, ATM |  |  |  |  | LA | GIL R&D Conference Room
7th Nov 22 | 09:00 AM to 10:30 AM | Rating | LA, ATMs |  |  |  |  | LA | GIL R&D Conference Room
| 10:30 AM to 12:00 Noon | final finding preparations | LA |  |  |  |  | LA | GIL R&D Conference Room
| 12.00 Noon to 01:00 PM | final findings 1 presentation and walkthrough of performance reports | LA |  |  |  | Sponser : Mr. S.N. Vijayvergia and all team. | LA | GIL R&D Conference Room
| 02:00 PM to 03:00 PM | final findings 2 presentation and walkthrough of performance reports | LA, ATM |  |  |  | Sponser : Mr. S.N. Vijayvergia and all team. | LA | GIL R&D Conference Room
| 04:00 PM to 05:00 PM | wrap up and submission | LA, ATM |  |  |  |  | LA | GIL R&D Conference Room

## ARR and other
Date | Time | actitivty | participants
| 08:30 AM to 07:00 PM India time | Team Training | ATM and LA
| 07:00 AM to 07:30 AM | sponsor meeting | sponsor and LA, site coordinator and Interpreter
| 07:30 AM -08:30 AM India time | site testing | LA and site coordinator
| 07:30 AM -08:30 AM India time | SEPG and QA and OT | SEPG and QA members, LA and ATMS
| 08:30 AM to 09:30 AM | project 1 | Project Mamanger and team member
| 12:00 PM to 01:00 PM | project2 | Project mamanger
| 01:00 PM to 02:00 PM | project 3 | Project manager
| 02:00 PM to 03:00 PM | meeting with sponsor to discuss readiness decision | sponsor and LA, site coordinator and Interpreter