## IR-2
Implementation Review 2 by KPMG
S. No. | Project / Function Name | Owner | PA | Observations / Feedbacks / Suggestions / Remarks
1 | GGE300 | Syojiram Sharma | RSK | How evaluate or justify the opportunity in terms of business.
Mitigation actions shown finished for Opportunity; but not able to explain about opportunity got or not.
Business case : Market size not mentioned.
Use Concept qualification module of Einframe for Opportunity.
How to identify that we need to focus on which risk out of multiple risks; RPN threshold concept
Why still liklehood not zero for mitigated risks.
Any discussion with senior management regarding risks.
How use organization data (historical data) for risk identification and how differenlty do actions on that.
2 | OBH012 | Syojiram Sharma | PR | Not able to explain defect sources in incident management. In internal document review findings source selected as 3rd party component.
How to handle deviations from design during testing.
No evidences and no affirmation found regarding PR_3.1 (Analyze results and data from peer reviews)
|  |  | RDM | Change request in requirement need to reflect in RTT via id or remarks
|  |  | V&V | What you have done in TG1; not able to open Project gates report in Einframe.
|  |  | II | What use from and what contribution to organization. Document showing that GGE202 BOM costing took as ref. for this project, but not affirmed.
|  |  | GOV | Any discussion with Senior management regarding skills required, gaps etc.
3 | GGE295 | Sobhag Prajapat | TS & PI | How auditor evalauted the technical solutions.
How alternative solutions identified and managed
Where are technical data
What are the integration environment
Technical defects not upto mark
|  |  | II | What use from and what contribution to organization.
|  |  | GOV | Any discussion with Senior management regarding skills required, gaps etc.
In metrics report schedule variance showing in negative side, while project is actually delayed.
4 | GGE302 | Sobhag Prajapat | EST | In high level estimation complexity mention medium, how identified. (Project level complexity)
Explain the complexity identification guidelines.
Any changes in efforts estimation after finalize.
|  |  | Plan | How do you manage the project dependencies ? (Persons, Tasks)
What are project environment and how do you manage that ?
Any tailoring you took, how applied ?
|  |  | MC | In some tasks schedule variance are too high say 700%..., why and what you did for this ? (rasons / discussions / corrective actions)
Schedule variances are high but efforts utilization is low, why ?
You arrnaged the external review for PCBs, have you done contract ? Why this is in critical path ? Why only one day planned for that, while actually 10 days spent ? As explained by PM, then it is directly strike that "SAM" applicable.
Have any issue faced ? Need evidences for MC 3.3 (Monitor the work environment to identify the issues)
Have any risk converted into issue ?
|  |  | II | What use from and what contribution to organization.
|  |  | GOV | Any discussion with Senior management regarding delays, skills required, gaps etc.
5 | GNE114 | Chandrashekhar Sharma | DAR | What is critical criteria ?
Any risk in decision.
How select decision authority for DAR. In this case senior management approval required.
|  |  | CAR | No implementation found
|  |  | CM | How configuration audit occurs
Any change request handled
Document type explain, what is baslined and what is controlled.
|  |  | II | What use from and what contribution to organization.
|  |  | GOV | Any discussion with Senior management regarding DAR, skills required, gaps etc.
6 | Training | Girija Singh | OT | What is the complete process.
How training identified.
What is the meaning of technical training
Pool of trainers not found
Training plan is in unpublish state, why
How take nominations for trainings.
How takes attendences
How take feedbacks
How feedback analysis do, no evidence found. Required at least last 2-3 analysis.
All docs and affirmations are not as per process and plan
Not do activites as per plan
All scheduled training not completed in system
Audit finding shwon on mail, not in system. Resolved or not; no evidence.
|  |  | GOV | Not done any review with senior management
|  |  | II | What use from and what contribution to organization.
7 | PQA | Shweta Agarwal | PQA | What are the criteria to select the NCs for analysis, why only functional selected.
Regarding SVN commit and update pop up software, till date mail shoot
When defect analysis done
In checklist if not applicable please put NA in place of NO
8 | PEG | Jalaj Mathur | PEG | To map PCM 3.1 PEG plan objective can use
PAD practices i.e. Determine, develop, buy and resue , how mapping will be done, should have discussion with SM or mails.
For MPM 3.3, demonstrate the data quality checks like SAP transcition, google sheet, Einframe etc.