## PLAN
PLAN
Level | Practice | Title | Source Reference | Link | Description | Type(Doc/ Aff) | S/W/I Description | S/W/I | Verified- Y/N | GGE302 |  |  | CHAR - GGE302-FI/LI
Level 1 | 1.1 | Develop a list of tasks. | OK | GGE302_PLAN | The level of work in project defined in terms of tasks. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | The description and timeline defined for each tasks. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 1.2 | Assign people to tasks. | OK | GGE302_MINMET | In pre planning meeting discussed the roles, and in deploy the plan meeting task conveyed. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_Project_Team | Project team as per discussion in meeting added in project, fill skills needs as per project requirements and check gaps in skills. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | All defined tasks have relevant people. And all relevant people added in project team | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 2 | 2.1 | Develop and keep updated the approach for accomplishing the work. | OK | GGE302_PLAN | project consists of every tasks list and it is updated on regular basis. It can be tracked through task comments . | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | The description section of project consists of objective of project, what outcomes expected. |  |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.2 | Plan for the knowledge and skills needed to perform the work. | OK | GGE302_PLAN | Product knowledge related activity plan and team meeting discussion in kick off meeting. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | For new member work related knowledge plan done like validation handover . | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_Talent Map And GAP | Talent needs and gaps of project plan identified the need of training / skills. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.3 | Based on recorded estimates, develop and keep updated the budget and schedule. | OK | GGE302_PLAN | Budget section of project plan | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Based on estimated efforts schedule prepared till end. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Major milestones in terms of Toll gates defined. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Predecessor and successors used for task dependencies. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Resources in terms of men and machines defined as dependencies of each task. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.4 | Plan the involvement of identified stakeholders. | OK | GGE302_PLAN | Schedule of project consists of resource plan against each task | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_Project_Team | Project team identified with roles and responsibility defined in project tasks itself to involve the stakeholders. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.5 | Plan transition to operations and support. | OK | GGE302_CM_PLAN | CM plan tells about mode of release and documents to be released for the project | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | In Plan tasks identified to make user support documents. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.6 | Ensure plans are feasible by reconciling available and estimated resources. | OK | GGE302_MINMET | In pre planning meeting discussed the roles to involve the stakeholders. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_MINMET | Meeting with team to deploy and discuss the finalized the plan. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.7 | Develop the project plan, ensure consistency among its elements, and keep it updated. | OK | GGE302_PLAN | Project plan made. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_CM_PLAN | CM plan as separate section of project plan made. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_Project_Publish_Log | Project plan updated through out the project lifecycle whenever needed, and can be checked in publish log. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 2.8 | Review plans and obtain commitments from affected stakeholders. | - |  |  |  |  | -
|  |  | OK | GGE302_MINMET | Stakeholders confirmation on planned schedule, resources etc. in project meeting.. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Review plan planned at all stage and valuable / critical artefacts -like plan ,RTT ,Requirement, design,implemetation,testing,etc. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
Level 3 | 3.1 | Use the organization’s set of standard processes and tailoring guidelines to develop, keep updated, and follow the project process. | OK | GGE302_PLAN | Project life cycle showing project flow, as provided by organization. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Project category defined for this project that is from organization processes. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Task template used as reference during task list out and planning. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.2 | Develop a plan and keep it updated, using the project process, the organization’s process assets, and the measurement repository. | OK | GGE302_take reference from GGE295 estimation repository | As organization measurement repository took reference of GGE295 actual data during estimation. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | The actual efforts automatically made / added in as measurement repository of organization. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.3 | Identify and negotiate critical dependencies. | OK | GGE302_PLAN | Critical resources CREO tool, SMF Batteries etc. in Asset section (resource plan) | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN_Risk | Critical dependencies mentioned in risk matrix. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
| 3.4 | Plan for the project environment and keep it updated based on the organization’s standards. | OK | GGE302_PLAN | Keep the project environment related things like Assets, tool and equipment that peapol need to perform their job. all testing related task (Module testing ,integration testing ,and validation) relevant environment ,equipment and tools are planed | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | Product training planed in validation handover task. | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | All relevant and required resources available so no need to plan to assign responsibility to plan to acquire resources and facilities | Doc |  | - |  | X | X | X
|  |  | OK | GGE302_PLAN | For the contingency plan if the resource and facilities and environment can not be obtained -we have been taken care all long testing related plan with effort of 30-40% at each day . In case inevitability of any thing can be managed next day or by before day. Or can be managed full effort on single day. | Doc |  | - |  | X | X | X
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
|  |  | - |  |  |  |  | -
** Minimum 2 and maximum 3 evidences require for each practice